## PROGRESS PAYMT #1
PROGRESS PAYMENT
Project Name: | City Hall Basement |  |  |  | Page: |  | 1 of 1
Project No: | N/A |  |  |  | Date of Application: |  | 2014-05-23
Resolution # | N/A |  |  |  | Invoice Date: |  | 2014-05-22
Purchase Order No's: |  | 6190 |  |  | Pay Period Through: |  | 2014-05-22
Contractor: Waterproofing Technologies
[5 empty] | Payment No : |  | 1
Purchase Order is attached
Application is made for Payment, as shown below, in connection with the Contract. Attached is the consultant's signed request for payment. Payment due date per Contract specification. The present status of the account(s) for this Contract is as follows:
THIS PAYMENT
Original Contract | Change Orders | Revised Contract | Total Due This Invoice | Total Previous Payments |  | Total Completed to Date | Balance to Finish
15850 | 0 | 15850 | 11350 | 0 |  | 11350 | 4500
PROGRESS INVOICE HISTORY |  |  |  |  | CHANGE ORDER SUMMARY
Pay No. / Date | Invoice Amount |  | % Complete |  | Change Order # | Date Approved | Total Value
1 | 11350 |  | 71.61%
2 |  |  | 0%
3 |  |  | 0%
4 |  |  | 0%
5 |  |  | 0%
6 |  |  | 0% |  |  | Total | 0
7 |  |  | 0%
8 |  |  | 0%
9 |  |  | 0%
10 |  |  | 0%
11 |  |  | 0%
12 |  |  | 0%
13 |  |  | 0% |  | CURRENT PAYMENT DUE
14 |  |  | 0%
15 |  |  | 0% |  | Account Number: 36-5150-706400
16 |  |  | 0%
17 |  |  | 0% |  | 11350
18 |  |  | 0%
19 |  |  | 0%
20 |  |  | 0%
Total | 11350 | 0 | 71.61%
Project Manager |  |  | Date
City Engineer / Interim Public Works Director |  |  | Date
City Manager (Pro-Tem) (if over $5,000.00) |  |  | Date
This certificate is not negotiable. It is payable only to the payee named herein and its issuance, payment and acceptance are without prejudice to any rights of the Owner or Contractor under their Contract.