## DATA
INPUT DATA
Project Name: |  | North Valley Reservoir Improvements
Project No: |  | 7587
Resolution No: |  | 2015-3231
Purchase Order No's: |  | 8091
Contractor |  | Ward-Henshaw Const
Resolution Information |  | The contract was approved by City Council on October 22, 2015 per Resolution No. 2015-3231 with a contract value of $1,815,165.00.
Original Contract Value |  | 1815165
Account Number Splits
[6 empty] | Water | Storm | Sanitary | Street
|  | Total Completed & Stored to Date | Date of Application | Invoice Date | Pay Period Through | 04-5150-707587
Progress Payment | 1 | 54477.02 | 2015-12-16 | 2015-11-30 | 2015-11-25 | 54477.02
Progress Payment | 2 | 160706.01 | 2016-01-21 | 2015-12-25 | 2015-12-25 | 106228.99
Progress Payment | 3 | 585934.18 | 2016-02-25 | 2016-02-05 | 2016-02-03 | 425228.17
Progress Payment | 4 | 731716.04 | 2016-03-23 | 2016-03-17 | 2016-02-29 | 145781.86
Progress Payment | 5 | 869551.99 | 2016-04-04 | 2016-03-29 | 2016-03-28 | 137835.95
Progress Payment | 6 | 1183716.72 | 2016-05-18 | 2016-04-29 | 2016-04-28 | 314164.73
Progress Payment | 7 | 1465955.37 | 2016-06-10 | 2016-05-26 | 2016-05-26 | 282238.65
Progress Payment | 8 | 1607352.99 | 2016-07-22 | 2016-06-28 | 2016-06-28 | 141397.62
Progress Payment | 9 | 1648620.34 | 2016-11-29 | 2016-10-26 | 2016-10-26 | 41267.35
Progress Payment | 10 | 1758068.63 | 2016-11-29 | 2016-11-29 | 2016-11-28 | 109448.29
Progress Payment | 11 | 1817345.47 | 2016-12-29 | 2016-12-21 | 2016-12-21 | 59276.84
Progress Payment | 12 | 1817345.47 | 2017-04-04 | 2016-12-21 | Final | 0
Progress Payment | 13 | 0 |  |  |  | -1817345.47
Progress Payment | 14 | 0 |  |  |  | 0
Progress Payment | 15 | 0 |  |  |  | 0
Progress Payment | 16 | 0 |  |  |  | 0
Progress Payment | 17 | 0 |  |  |  | 0
Progress Payment | 18 | 0 |  |  |  | 0
Progress Payment | 19 | 0 |  |  |  | 0
Progress Payment | 20 | 0 |  |  |  | 0
Note on H11: Jason Wuertz: Insert numbers from "work completed THIS PERIOD." Do not remove retention in these cells as it is removed on the progress payment page

## PROGRESS PAYMT #1
PROGRESS PAYMENT
Project Name: | North Valley Reservoir Improvements |  |  |  |  | Page: |  | 1 of 1
Project No: | 7587 |  |  |  |  | Date of Application: |  | 2015-12-16
Resolution #: | 2015-3231 |  |  |  |  | Invoice Date: |  | 2015-11-30
Purchase Order No's: |  | 8091 |  |  |  | Pay Period Through: |  | 2015-11-25
The contract was approved by City Council on October 22, 2015 per Resolution No. 2015-3231 with a contract value of $1,815,165.00. | [5 empty] | Contractor: | Ward-Henshaw Const
[6 empty] | Payment No: |  | 1
Purchase Order is attached
Application is made for Payment, as shown below, in connection with the Contract. Attached is the contractor's signed request for payment. Payment due date per Contract specification. The present status of the account(s) for this Contract is as follows:
THIS PAYMENT
Original Contract | Change Orders | Revised Contract | Total Completed & Stored To Date | Total Retainage |  | Total Earned Less Retainage | Less Previous Certificates for Payment | Balance To Finish
1815165 | 0 | 1815165 | 54477.02 | 2723.851 |  | 51753.169 | 51753.169 | 1763411.831
PROGRESS INVOICE HISTORY |  |  |  |  | CHANGE ORDER SUMMARY
Pay No. / Date | Invoice Amount | Retention | % Complete |  | Change Order # | Date Approved | PO# | Total Value
1 | 51753.169 | 2723.851 | 3.001%
2 |  |  | 0%
3 |  |  | 0%
4 |  |  | 0%
5 |  |  | 0%
6 |  |  | 0% |  |  |  | Total | 0
7 |  |  | 0%
8 |  |  | 0%
9 |  |  | 0%
10 |  |  | 0%
11 |  |  | 0%
12 |  |  | 0% |  | CURRENT PAYMENT DUE
13 |  |  | 0%
14 |  |  | 0% |  | Account #: |  | Amount:
15 |  |  | 0% |  | 04-5150-707587 |  | 51753.169
16 |  |  | 0%
17 |  |  | 0%
18 |  |  | 0% | [5 empty] | Payment Due Matches In different cells
19 |  |  | 0% |  | Total Payment: |  | 51753.169 |  | CHECKS
20 |  |  | 0% | [5 empty] | CHECKS
Total | 51753.169 | 2723.851 | 3.001%
Project Manager |  |  | Date |  | City Manager (if over $5,000.00) |  |  | Date
City Engineer |  |  | Date |  | Finance Director |  |  | Date
This certificate is not negotiable. It is payable only to the payee named herein and its issuance, payment and acceptance are without prejudice to any rights of the Owner or Contractor under their Contract.
Note on K42: Jason Wuertz: This checks that Cell H42 matches H19 which it should
Note on K43: Jason Wuertz: Checks that H42 matches H24 which it should

## PROGRESS PAYMT #2
PROGRESS PAYMENT
Project Name: | North Valley Reservoir Improvements |  |  |  |  | Page: |  | 1 of 1
Project No: | 7587 |  |  |  |  | Date of Application: |  | 2016-01-21
Resolution #: | 2015-3231 |  |  |  |  | Invoice Date: |  | 2015-12-25
Purchase Order No's: |  | 8091 |  |  |  | Pay Period Through: |  | 2015-12-25
The contract was approved by City Council on October 22, 2015 per Resolution No. 2015-3231 with a contract value of $1,815,165.00. | [5 empty] | Contractor: | Ward-Henshaw Const
[6 empty] | Payment No: |  | 2
Purchase Order is attached
Application is made for Payment, as shown below, in connection with the Contract. Attached is the contractor's signed request for payment. Payment due date per Contract specification. The present status of the account(s) for this Contract is as follows:
THIS PAYMENT
Original Contract | Change Orders | Revised Contract | Total Completed & Stored To Date | Total Retainage |  | Total Earned Less Retainage | Less Previous Certificates for Payment | Balance To Finish
1815165 | 61268.26 | 1876433.26 | 160706.01 | 8035.3005 |  | 152670.7095 | 100917.5405 | 1723762.5505
PROGRESS INVOICE HISTORY |  |  |  |  | CHANGE ORDER SUMMARY
Pay No. / Date | Invoice Amount | Retention | % Complete |  | Change Order # | Date Approved | PO# | Total Value
1 | 51753.169 | 2723.851 | 2.903% |  | 1 | 2015-12-18 | N/A | 61268.26
2 | 100917.5405 | 5311.4495 | 5.661%
3 |  |  | 0%
4 |  |  | 0%
5 |  |  | 0%
6 |  |  | 0% |  |  |  | Total | 61268.26
7 |  |  | 0%
8 |  |  | 0%
9 |  |  | 0%
10 |  |  | 0%
11 |  |  | 0%
12 |  |  | 0% |  | CURRENT PAYMENT DUE
13 |  |  | 0%
14 |  |  | 0% |  | Account #: |  | Amount:
15 |  |  | 0% |  | 04-5150-707587 |  | 100917.5405
16 |  |  | 0%
17 |  |  | 0% | [5 empty] | Payment Due Matches In different cells
18 |  |  | 0% | [5 empty] | CHECKS
19 |  |  | 0% |  | Total Payment: |  | 100917.5405 |  | CHECKS
20 |  |  | 0% | [5 empty] | CHECKS
Total | 152670.7095 | 8035.3005 | 8.564%
Project Manager |  |  | Date |  | City Manager (Pro-Tem) (if over $5,000.00) |  |  | Date
City Engineer |  |  | Date
This certificate is not negotiable. It is payable only to the payee named herein and its issuance, payment and acceptance are without prejudice to any rights of the Owner or Contractor under their Contract.
Note on I4: Jason Wuertz: Add one number to the cell to move down one on the main page
Note on I10: Jason Wuertz: Add one number to the cell in the formula
Note on D19: Jason Wuertz: Add one number to the forumula cell
Note on B23: Jason Wuertz: When adding new tab, copy number from previous tab, not the formula
Note on C23: Jason Wuertz: =Total Retainage - sum of retention totals from previous payments
Note on K41: Jason Wuertz: This checks that Cell H42 matches H19 which it should
Note on K42: Jason Wuertz: Checks that H42 matches H24 which it should
Note on K43: Jason Wuertz: Checks that the total invoice history without retention, plus the balance to finish = the revised contract

## PROGRESS PAYMT #3
PROGRESS PAYMENT
Project Name: | North Valley Reservoir Improvements |  |  |  |  | Page: |  | 1 of 1
Project No: | 7587 |  |  |  |  | Date of Application: |  | 2016-02-25
Resolution #: | 2015-3231 |  |  |  |  | Invoice Date: |  | 2016-02-05
Purchase Order No's: |  | 8091 |  |  |  | Pay Period Through: |  | 2016-02-03
The contract was approved by City Council on October 22, 2015 per Resolution No. 2015-3231 with a contract value of $1,815,165.00. | [5 empty] | Contractor: | Ward-Henshaw Const
[6 empty] | Payment No: |  | 3
Purchase Order is attached
Application is made for Payment, as shown below, in connection with the Contract. Attached is the contractor's signed request for payment. Payment due date per Contract specification. The present status of the account(s) for this Contract is as follows:
THIS PAYMENT
Original Contract | Change Orders | Revised Contract | Total Completed & Stored To Date | Total Retainage |  | Total Earned Less Retainage | Less Previous Certificates for Payment | Balance To Finish
1815165 | 0 | 1815165 | 585934.18 | 29296.709 |  | 556637.471 | 403966.7615 | 1258527.529
PROGRESS INVOICE HISTORY |  |  |  |  | CHANGE ORDER SUMMARY
Pay No. / Date | Invoice Amount | Retention | % Complete |  | Change Order # | Date Approved | PO# | Total Value
1 | 51753.169 | 2723.851 | 3.001% |  | 1 | 2015-12-18 | N/A | 61268.26
2 | 100917.5405 | 5311.4495 | 5.852%
3 | 403966.7615 | 21261.4085 | 23.43%
4 |  |  | 0%
5 |  |  | 0%
6 |  |  | 0% |  |  |  | Total | 61268.26
7 |  |  | 0%
8 |  |  | 0%
9 |  |  | 0%
10 |  |  | 0%
11 |  |  | 0%
12 |  |  | 0% |  | CURRENT PAYMENT DUE
13 |  |  | 0%
14 |  |  | 0% |  | Account #: |  | Amount:
15 |  |  | 0% |  | 04-5150-707587 |  | 403966.7615
16 |  |  | 0%
17 |  |  | 0% | [5 empty] | Payment Due Matches In different cells
18 |  |  | 0% | [5 empty] | CHECKS
19 |  |  | 0% |  | Total Payment: |  | 403966.7615 |  | CHECKS
20 |  |  | 0% | [5 empty] | CHECKS
Total | 556637.471 | 29296.709 | 32.28%
Project Manager |  |  | Date |  | City Manager (Pro-Tem) (if over $5,000.00) |  |  | Date
City Engineer |  |  | Date
This certificate is not negotiable. It is payable only to the payee named herein and its issuance, payment and acceptance are without prejudice to any rights of the Owner or Contractor under their Contract.
Note on I4: Jason Wuertz: Add one number to the cell to move down one on the main page
Note on I10: Jason Wuertz: Add one number to the cell in the formula
Note on D19: Jason Wuertz: Add one number to the forumula cell
Note on B23: Jason Wuertz: When adding new tab, copy number from previous tab, not the formula
Note on C23: Jason Wuertz: =Total Retainage - sum of retention totals from previous payments
Note on K41: Jason Wuertz: This checks that Cell H42 matches H19 which it should
Note on K42: Jason Wuertz: Checks that H42 matches H24 which it should
Note on K43: Jason Wuertz: Checks that the total invoice history without retention, plus the balance to finish = the revised contract

## PROGRESS PAYMT #4
PROGRESS PAYMENT
Project Name: | North Valley Reservoir Improvements |  |  |  |  | Page: |  | 1 of 1
Project No: | 7587 |  |  |  |  | Date of Application: |  | 2016-03-23
Resolution #: | 2015-3231 |  |  |  |  | Invoice Date: |  | 2016-03-17
Purchase Order No's: |  | 8091 |  |  |  | Pay Period Through: |  | 2016-02-29
The contract was approved by City Council on October 22, 2015 per Resolution No. 2015-3231 with a contract value of $1,815,165.00. | [5 empty] | Contractor: | Ward-Henshaw Const
[6 empty] | Payment No: |  | 4
Purchase Order is attached
Application is made for Payment, as shown below, in connection with the Contract. Attached is the contractor's signed request for payment. Payment due date per Contract specification. The present status of the account(s) for this Contract is as follows:
THIS PAYMENT
Original Contract | Change Orders | Revised Contract | Total Completed & Stored To Date | Total Retainage |  | Total Earned Less Retainage | Less Previous Certificates for Payment | Balance To Finish
1815165 | 0 | 1815165 | 731716.04 | 36585.802 |  | 695130.238 | 138492.767 | 1120034.762
PROGRESS INVOICE HISTORY |  |  |  |  | CHANGE ORDER SUMMARY
Pay No. / Date | Invoice Amount | Retention | % Complete |  | Change Order # | Date Approved | PO# | Total Value
1 | 51753.169 | 2723.851 | 3.001% |  | 1 | 42356 | N/A | 61268.26
2 | 100917.5405 | 5311.4495 | 5.852%
3 | 403966.7615 | 21261.4085 | 23.43%
4 | 138492.767 | 7289.093 | 8.031%
5 |  |  | 0%
6 |  |  | 0% |  |  |  | Total | 0
7 |  |  | 0%
8 |  |  | 0%
9 |  |  | 0%
10 |  |  | 0%
11 |  |  | 0%
12 |  |  | 0% |  | CURRENT PAYMENT DUE
13 |  |  | 0%
14 |  |  | 0% |  | Account #: |  | Amount:
15 |  |  | 0% |  | 04-5150-707587 |  | 138492.767
16 |  |  | 0%
17 |  |  | 0% | [5 empty] | Payment Due Matches In different cells
18 |  |  | 0% | [5 empty] | CHECKS
19 |  |  | 0% |  | Total Payment: |  | 138492.767 |  | CHECKS
20 |  |  | 0% | [5 empty] | CHECKS
Total | 695130.238 | 36585.802 | 40.31%
Project Manager |  |  | Date |  | City Manager (Pro-Tem) (if over $5,000.00) |  |  | Date
City Engineer |  |  | Date
This certificate is not negotiable. It is payable only to the payee named herein and its issuance, payment and acceptance are without prejudice to any rights of the Owner or Contractor under their Contract.
Note on I4: Jason Wuertz: Add one number to the cell to move down one on the main page
Note on I10: Jason Wuertz: Add one number to the cell in the formula
Note on D19: Jason Wuertz: Add one number to the forumula cell
Note on B23: Jason Wuertz: When adding new tab, copy number from previous tab, not the formula
Note on C23: Jason Wuertz: =Total Retainage - sum of retention totals from previous payments
Note on K41: Jason Wuertz: This checks that Cell H42 matches H19 which it should
Note on K42: Jason Wuertz: Checks that H42 matches H24 which it should
Note on K43: Jason Wuertz: Checks that the total invoice history without retention, plus the balance to finish = the revised contract

## PROGRESS PAYMT #5
PROGRESS PAYMENT
Project Name: | North Valley Reservoir Improvements |  |  |  |  | Page: |  | 1 of 1
Project No: | 7587 |  |  |  |  | Date of Application: |  | 2016-04-04
Resolution #: | 2015-3231 |  |  |  |  | Invoice Date: |  | 2016-03-29
Purchase Order No's: |  | 8091 |  |  |  | Pay Period Through: |  | 2016-03-28
The contract was approved by City Council on October 22, 2015 per Resolution No. 2015-3231 with a contract value of $1,815,165.00. | [5 empty] | Contractor: | Ward-Henshaw Const
[6 empty] | Payment No: |  | 5
Purchase Order is attached
Application is made for Payment, as shown below, in connection with the Contract. Attached is the contractor's signed request for payment. Payment due date per Contract specification. The present status of the account(s) for this Contract is as follows:
THIS PAYMENT
Original Contract | Change Orders | Revised Contract | Total Completed & Stored To Date | Total Retainage |  | Total Earned Less Retainage | Less Previous Certificates for Payment | Balance To Finish
1815165 | 0 | 1815165 | 869551.99 | 43477.5995 |  | 826074.3905 | 130944.1525 | 989090.6095
PROGRESS INVOICE HISTORY |  |  |  |  | CHANGE ORDER SUMMARY
Pay No. / Date | Invoice Amount | Retention | % Complete |  | Change Order # | Date Approved | PO# | Total Value
1 | 51753.169 | 2723.851 | 3.001% |  | 1 | 42356 | N/A | 61268.26
2 | 100917.5405 | 5311.4495 | 5.852%
3 | 403966.7615 | 21261.4085 | 23.43%
4 | 138492.767 | 7289.093 | 8.031%
5 | 130944.1525 | 6891.7975 | 7.594%
6 |  |  | 0% |  |  |  | Total | 0
7 |  |  | 0%
8 |  |  | 0%
9 |  |  | 0%
10 |  |  | 0%
11 |  |  | 0%
12 |  |  | 0% |  | CURRENT PAYMENT DUE
13 |  |  | 0%
14 |  |  | 0% |  | Account #: |  | Amount:
15 |  |  | 0% |  | 04-5150-707587 |  | 130944.1525
16 |  |  | 0%
17 |  |  | 0% | [5 empty] | Payment Due Matches In different cells
18 |  |  | 0% | [5 empty] | CHECKS
19 |  |  | 0% |  | Total Payment: |  | 130944.1525 |  | CHECKS
20 |  |  | 0% | [5 empty] | CHECKS
Total | 826074.3905 | 43477.5995 | 47.9%
Project Manager |  |  | Date |  | City Manager (Pro-Tem) (if over $5,000.00) |  |  | Date
City Engineer |  |  | Date
This certificate is not negotiable. It is payable only to the payee named herein and its issuance, payment and acceptance are without prejudice to any rights of the Owner or Contractor under their Contract.
Note on I4: Jason Wuertz: Add one number to the cell to move down one on the main page
Note on I10: Jason Wuertz: Add one number to the cell in the formula
Note on D19: Jason Wuertz: Add one number to the forumula cell
Note on H19: Jason Wuertz: Change sheet number
Note on B23: Jason Wuertz: When adding new tab, copy number from previous tab, not the formula
Note on C23: Jason Wuertz: =Total Retainage - sum of retention totals from previous payments
Note on K41: Jason Wuertz: This checks that Cell H42 matches H19 which it should
Note on K42: Jason Wuertz: Checks that H42 matches H24 which it should
Note on K43: Jason Wuertz: Checks that the total invoice history without retention, plus the balance to finish = the revised contract

## PROGRESS PAYMT #6
PROGRESS PAYMENT
Project Name: | North Valley Reservoir Improvements |  |  |  |  | Page: |  | 1 of 1
Project No: | 7587 |  |  |  |  | Date of Application: |  | 2016-05-18
Resolution #: | 2015-3231 |  |  |  |  | Invoice Date: |  | 2016-04-29
Purchase Order No's: |  | 8091 |  |  |  | Pay Period Through: |  | 2016-04-28
The contract was approved by City Council on October 22, 2015 per Resolution No. 2015-3231 with a contract value of $1,815,165.00. | [5 empty] | Contractor: | Ward-Henshaw Const
[6 empty] | Payment No: |  | 6
Purchase Order is attached
Application is made for Payment, as shown below, in connection with the Contract. Attached is the contractor's signed request for payment. Payment due date per Contract specification. The present status of the account(s) for this Contract is as follows:
THIS PAYMENT
Original Contract | Change Orders | Revised Contract | Total Completed & Stored To Date | Total Retainage |  | Total Earned Less Retainage | Less Previous Certificates for Payment | Balance To Finish
1815165 | 0 | 1815165 | 1183716.72 | 59185.836 |  | 1124530.884 | 298456.4935 | 690634.116
PROGRESS INVOICE HISTORY |  |  |  |  | CHANGE ORDER SUMMARY
Pay No. / Date | Invoice Amount | Retention | % Complete |  | Change Order # | Date Approved | PO# | Total Value
1 | 51753.169 | 2723.851 | 3.001% |  | 1 | 2015-12-18 | N/A | 61268.26
2 | 100917.5405 | 5311.4495 | 5.852%
3 | 403966.7615 | 21261.4085 | 23.43%
4 | 138492.767 | 7289.093 | 8.031%
5 | 130944.1525 | 6891.7975 | 7.594%
6 | 298456.4935 | 15708.2365 | 17.31% |  |  |  | Total | 0
7 |  |  | 0%
8 |  |  | 0%
9 |  |  | 0%
10 |  |  | 0%
11 |  |  | 0%
12 |  |  | 0% |  | CURRENT PAYMENT DUE
13 |  |  | 0%
14 |  |  | 0% |  | Account #: |  | Amount:
15 |  |  | 0% |  | 04-5150-707587 |  | 298456.4935
16 |  |  | 0%
17 |  |  | 0% | [5 empty] | Payment Due Matches In different cells
18 |  |  | 0% | [5 empty] | CHECKS
19 |  |  | 0% |  | Total Payment: |  | 298456.4935 |  | CHECKS
20 |  |  | 0% | [5 empty] | CHECKS
Total | 1124530.884 | 59185.836 | 65.21%
Project Manager |  |  | Date |  | City Manager (Pro-Tem) (if over $5,000.00) |  |  | Date
City Engineer |  |  | Date
This certificate is not negotiable. It is payable only to the payee named herein and its issuance, payment and acceptance are without prejudice to any rights of the Owner or Contractor under their Contract.
Note on I4: Jason Wuertz: Add one number to the cell to move down one on the main page
Note on I10: Jason Wuertz: Add one number to the cell in the formula
Note on D19: Jason Wuertz: Add one number to the forumula cell
Note on H19: Jason Wuertz: Change sheet number
Note on B23: Jason Wuertz: When adding new tab, copy number from previous tab, not the formula
Note on C23: Jason Wuertz: =Total Retainage - sum of retention totals from previous payments
Note on K41: Jason Wuertz: This checks that Cell H42 matches H19 which it should
Note on K42: Jason Wuertz: Checks that H42 matches H24 which it should
Note on K43: Jason Wuertz: Checks that the total invoice history without retention, plus the balance to finish = the revised contract

## PROGRESS PAYMT #7
PROGRESS PAYMENT
Project Name: | North Valley Reservoir Improvements |  |  |  |  | Page: |  | 1 of 1
Project No: | 7587 |  |  |  |  | Date of Application: |  | 2016-06-10
Resolution #: | 2015-3231 |  |  |  |  | Invoice Date: |  | 2016-05-26
Purchase Order No's: |  | 8091 |  |  |  | Pay Period Through: |  | 2016-05-26
The contract was approved by City Council on October 22, 2015 per Resolution No. 2015-3231 with a contract value of $1,815,165.00. | [5 empty] | Contractor: | Ward-Henshaw Const
[6 empty] | Payment No: |  | 7
Purchase Order is attached
Application is made for Payment, as shown below, in connection with the Contract. Attached is the contractor's signed request for payment. Payment due date per Contract specification. The present status of the account(s) for this Contract is as follows:
THIS PAYMENT
Original Contract | Change Orders | Revised Contract | Total Completed & Stored To Date | Total Retainage |  | Total Earned Less Retainage | Less Previous Certificates for Payment | Balance To Finish
1815165 | 80506.66 | 1895671.66 | 1465955.37 | 73297.7685 |  | 1392657.6015 | 268126.7175 | 503014.0585
PROGRESS INVOICE HISTORY |  |  |  |  | CHANGE ORDER SUMMARY
Pay No. / Date | Invoice Amount | Retention | % Complete |  | Change Order # | Date Approved | PO# | Total Value
1 | 51753.169 | 2723.851 | 2.874% |  | 1 | 2015-12-18 | N/A | 61268.26
2 | 100917.5405 | 5311.4495 | 5.604% |  | 2 | 2016-03-25 | NA | 13486.63
3 | 403966.7615 | 21261.4085 | 22.43% |  | 3 | 2016-05-27 | NA | 5751.77
4 | 138492.767 | 7289.093 | 7.69%
5 | 130944.1525 | 6891.7975 | 7.271%
6 | 298456.4935 | 15708.2365 | 16.57% |  |  |  | Total | 80506.66
7 | 268126.7175 | 14111.9325 | 14.89%
8 |  |  | 0%
9 |  |  | 0%
10 |  |  | 0%
11 |  |  | 0%
12 |  |  | 0% |  | CURRENT PAYMENT DUE
13 |  |  | 0%
14 |  |  | 0% |  | Account #: |  | Amount:
15 |  |  | 0% |  | 04-5150-707587 |  | 268126.7175
16 |  |  | 0%
17 |  |  | 0% | [5 empty] | Payment Due Matches In different cells
18 |  |  | 0% | [5 empty] | CHECKS
19 |  |  | 0% |  | Total Payment: |  | 268126.7175 |  | CHECKS
20 |  |  | 0% | [5 empty] | CHECKS
Total | 1392657.6015 | 73297.7685 | 77.33%
Project Manager |  |  | Date |  | City Manager (if over $5,000.00) |  |  | Date
City Engineer |  |  | Date
This certificate is not negotiable. It is payable only to the payee named herein and its issuance, payment and acceptance are without prejudice to any rights of the Owner or Contractor under their Contract.
Note on I4: Jason Wuertz: Add one number to the cell to move down one on the main page
Note on I10: Jason Wuertz: Add one number to the cell in the formula
Note on D19: Jason Wuertz: Add one number to the forumula cell
Note on H19: Jason Wuertz: Change sheet number
Note on B23: Jason Wuertz: When adding new tab, copy number from previous tab, not the formula
Note on C23: Jason Wuertz: =Total Retainage - sum of retention totals from previous payments
Note on K41: Jason Wuertz: This checks that Cell H42 matches H19 which it should
Note on K42: Jason Wuertz: Checks that H42 matches H24 which it should
Note on K43: Jason Wuertz: Checks that the total invoice history without retention, plus the balance to finish = the revised contract

## PROGRESS PAYMT #8
PROGRESS PAYMENT
Project Name: | North Valley Reservoir Improvements |  |  |  |  | Page: |  | 1 of 1
Project No: | 7587 |  |  |  |  | Date of Application: |  | 2016-07-22
Resolution #: | 2015-3231 |  |  |  |  | Invoice Date: |  | 2016-06-28
Purchase Order No's: |  | 8091 |  |  |  | Pay Period Through: |  | 2016-06-28
The contract was approved by City Council on October 22, 2015 per Resolution No. 2015-3231 with a contract value of $1,815,165.00. | [5 empty] | Contractor: | Ward-Henshaw Const
[6 empty] | Payment No: |  | 8
Purchase Order is attached
Application is made for Payment, as shown below, in connection with the Contract. Attached is the contractor's signed request for payment. Payment due date per Contract specification. The present status of the account(s) for this Contract is as follows:
THIS PAYMENT
Original Contract | Change Orders | Revised Contract | Total Completed & Stored To Date | Total Retainage |  | Total Earned Less Retainage | Less Previous Certificates for Payment | Balance To Finish
1815165 | 80506.66 | 1895671.66 | 1607352.99 | 80367.6495 |  | 1526985.3405 | 134327.739 | 368686.3195
PROGRESS INVOICE HISTORY |  |  |  |  | CHANGE ORDER SUMMARY
Pay No. / Date | Invoice Amount | Retention | % Complete |  | Change Order # | Date Approved | PO# | Total Value
1 | 51753.169 | 2723.851 | 2.874% |  | 1 | 2015-12-18 | N/A | 61268.26
2 | 100917.5405 | 5311.4495 | 5.604% |  | 2 | 2016-03-25 | NA | 13486.63
3 | 403966.7615 | 21261.4085 | 22.43% |  | 3 | 2016-05-27 | NA | 5751.77
4 | 138492.767 | 7289.093 | 7.69%
5 | 130944.1525 | 6891.7975 | 7.271%
6 | 298456.4935 | 15708.2365 | 16.57% |  |  |  | Total | 80506.66
7 | 268126.7175 | 14111.9325 | 14.89%
8 | 134327.739 | 7069.881 | 7.459%
9 |  |  | 0%
10 |  |  | 0%
11 |  |  | 0%
12 |  |  | 0% |  | CURRENT PAYMENT DUE
13 |  |  | 0%
14 |  |  | 0% |  | Account #: |  | Amount:
15 |  |  | 0% |  | 04-5150-707587 |  | 134327.739
16 |  |  | 0%
17 |  |  | 0% | [5 empty] | Payment Due Matches In different cells
18 |  |  | 0% | [5 empty] | CHECKS
19 |  |  | 0% |  | Total Payment: |  | 134327.739 |  | CHECKS
20 |  |  | 0% | [5 empty] | CHECKS
Total | 1526985.3405 | 80367.6495 | 84.79%
Project Manager |  |  | Date |  | City Manager (Pro-Tem) (if over $5,000.00) |  |  | Date
City Engineer |  |  | Date |  | Finance Director |  |  | Date
This certificate is not negotiable. It is payable only to the payee named herein and its issuance, payment and acceptance are without prejudice to any rights of the Owner or Contractor under their Contract.
Note on I4: Jason Wuertz: Add one number to the cell to move down one on the main page
Note on I10: Jason Wuertz: Add one number to the cell in the formula
Note on D19: Jason Wuertz: Add one number to the forumula cell
Note on H19: Jason Wuertz: Change sheet number
Note on B23: Jason Wuertz: When adding new tab, copy number from previous tab, not the formula
Note on C23: Jason Wuertz: =Total Retainage - sum of retention totals from previous payments
Note on K41: Jason Wuertz: This checks that Cell H42 matches H19 which it should
Note on K42: Jason Wuertz: Checks that H42 matches H24 which it should
Note on K43: Jason Wuertz: Checks that the total invoice history without retention, plus the balance to finish = the revised contract

## PROGRESS PAYMT #9
PROGRESS PAYMENT
Project Name: | North Valley Reservoir Improvements |  |  |  |  | Page: |  | 1 of 1
Project No: | 7587 |  |  |  |  | Date of Application: |  | 2016-11-29
Resolution #: | 2015-3231 |  |  |  |  | Invoice Date: |  | 2016-10-26
Purchase Order No's: |  | 8091 |  |  |  | Pay Period Through: |  | 2016-10-26
The contract was approved by City Council on October 22, 2015 per Resolution No. 2015-3231 with a contract value of $1,815,165.00. | [5 empty] | Contractor: | Ward-Henshaw Const
[6 empty] | Payment No: |  | 9
Purchase Order is attached
Application is made for Payment, as shown below, in connection with the Contract. Attached is the contractor's signed request for payment. Payment due date per Contract specification. The present status of the account(s) for this Contract is as follows:
THIS PAYMENT
Original Contract | Change Orders | Revised Contract | Total Completed & Stored To Date | Total Retainage |  | Total Earned Less Retainage | Less Previous Certificates for Payment | Balance To Finish
1815165 | 80506.66 | 1895671.66 | 1648620.34 | 82431.017 |  | 1566189.323 | 39203.9825 | 329482.337
PROGRESS INVOICE HISTORY |  |  |  |  | CHANGE ORDER SUMMARY
Pay No. / Date | Invoice Amount | Retention | % Complete |  | Change Order # | Date Approved | PO# | Total Value
1 | 51753.169 | 2723.851 | 2.874% |  | 1 | 2015-12-18 | N/A | 61268.26
2 | 100917.5405 | 5311.4495 | 5.604% |  | 2 | 2016-03-25 | NA | 13486.63
3 | 403966.7615 | 21261.4085 | 22.43% |  | 3 | 2016-05-27 | NA | 5751.77
4 | 138492.767 | 7289.093 | 7.69%
5 | 130944.1525 | 6891.7975 | 7.271%
6 | 298456.4935 | 15708.2365 | 16.57% |  |  |  | Total | 80506.66
7 | 268126.7175 | 14111.9325 | 14.89%
8 | 134327.739 | 7069.881 | 7.459%
9 | 39203.9825 | 2063.3675 | 2.177%
10 |  |  | 0%
11 |  |  | 0%
12 |  |  | 0% |  | CURRENT PAYMENT DUE
13 |  |  | 0%
14 |  |  | 0% |  | Account #: |  | Amount:
15 |  |  | 0% |  | 04-5150-707587 |  | 39203.9825
16 |  |  | 0%
17 |  |  | 0% | [5 empty] | Payment Due Matches In different cells
18 |  |  | 0% | [5 empty] | CHECKS
19 |  |  | 0% |  | Total Payment: |  | 39203.9825 |  | CHECKS
20 |  |  | 0% | [5 empty] | CHECKS
Total | 1566189.323 | 82431.017 | 86.97%
Project Manager |  |  | Date |  | City Manager (Pro-Tem) (if over $5,000.00) |  |  | Date
City Engineer |  |  | Date |  | Finance Director |  |  | Date
This certificate is not negotiable. It is payable only to the payee named herein and its issuance, payment and acceptance are without prejudice to any rights of the Owner or Contractor under their Contract.
Note on I4: Jason Wuertz: Add one number to the cell to move down one on the main page
Note on I10: Jason Wuertz: Add one number to the cell in the formula
Note on D19: Jason Wuertz: Add one number to the forumula cell
Note on H19: Jason Wuertz: Change sheet number
Note on B23: Jason Wuertz: When adding new tab, copy number from previous tab, not the formula
Note on C23: Jason Wuertz: =Total Retainage - sum of retention totals from previous payments
Note on K41: Jason Wuertz: This checks that Cell H42 matches H19 which it should
Note on K42: Jason Wuertz: Checks that H42 matches H24 which it should
Note on K43: Jason Wuertz: Checks that the total invoice history without retention, plus the balance to finish = the revised contract

## PROGRESS PAYMT #10
PROGRESS PAYMENT
Project Name: | North Valley Reservoir Improvements |  |  |  |  | Page: |  | 1 of 1
Project No: | 7587 |  |  |  |  | Date of Application: |  | 2016-11-29
Resolution #: | 2015-3231 |  |  |  |  | Invoice Date: |  | 2016-11-29
Purchase Order No's: |  | 8091 |  |  |  | Pay Period Through: |  | 2016-11-28
The contract was approved by City Council on October 22, 2015 per Resolution No. 2015-3231 with a contract value of $1,815,165.00. | [5 empty] | Contractor: | Ward-Henshaw Const
[6 empty] | Payment No: |  | 10
Purchase Order is attached
Application is made for Payment, as shown below, in connection with the Contract. Attached is the contractor's signed request for payment. Payment due date per Contract specification. The present status of the account(s) for this Contract is as follows:
THIS PAYMENT
Original Contract | Change Orders | Revised Contract | Total Completed & Stored To Date | Total Retainage |  | Total Earned Less Retainage | Less Previous Certificates for Payment | Balance To Finish
1815165 | 80506.66 | 1895671.66 | 1758068.63 | 87903.4315 |  | 1670165.1985 | 103975.8755 | 225506.4615
PROGRESS INVOICE HISTORY |  |  |  |  | CHANGE ORDER SUMMARY
Pay No. / Date | Invoice Amount | Retention | % Complete |  | Change Order # | Date Approved | PO# | Total Value
1 | 51753.169 | 2723.851 | 2.874% |  | 1 | 2015-12-18 | N/A | 61268.26
2 | 100917.5405 | 5311.4495 | 5.604% |  | 2 | 2016-03-25 | NA | 13486.63
3 | 403966.7615 | 21261.4085 | 22.43% |  | 3 | 2016-05-27 | NA | 5751.77
4 | 138492.767 | 7289.093 | 7.69%
5 | 130944.1525 | 6891.7975 | 7.271%
6 | 298456.4935 | 15708.2365 | 16.57% |  |  |  | Total | 80506.66
7 | 268126.7175 | 14111.9325 | 14.89%
8 | 134327.739 | 7069.881 | 7.459%
9 | 39203.9825 | 2063.3675 | 2.177%
10 | 103975.8755 | 5472.4145 | 5.774%
11 |  |  | 0%
12 |  |  | 0% |  | CURRENT PAYMENT DUE
13 |  |  | 0%
14 |  |  | 0% |  | Account #: |  | Amount:
15 |  |  | 0% |  | 04-5150-707587 |  | 103975.8755
16 |  |  | 0%
17 |  |  | 0% | [5 empty] | Payment Due Matches In different cells
18 |  |  | 0% | [5 empty] | CHECKS
19 |  |  | 0% |  | Total Payment: |  | 103975.8755 |  | CHECKS
20 |  |  | 0% | [5 empty] | CHECKS
Total | 1670165.1985 | 87903.4315 | 92.74%
Project Manager |  |  | Date |  | City Manager (Pro-Tem) (if over $5,000.00) |  |  | Date
City Engineer |  |  | Date |  | Finance Director |  |  | Date
This certificate is not negotiable. It is payable only to the payee named herein and its issuance, payment and acceptance are without prejudice to any rights of the Owner or Contractor under their Contract.
Note on I4: Jason Wuertz: Add one number to the cell to move down one on the main page
Note on I10: Jason Wuertz: Add one number to the cell in the formula
Note on D19: Jason Wuertz: Add one number to the forumula cell
Note on H19: Jason Wuertz: Change sheet number
Note on B23: Jason Wuertz: When adding new tab, copy number from previous tab, not the formula
Note on C23: Jason Wuertz: =Total Retainage - sum of retention totals from previous payments
Note on K41: Jason Wuertz: This checks that Cell H42 matches H19 which it should
Note on K42: Jason Wuertz: Checks that H42 matches H24 which it should
Note on K43: Jason Wuertz: Checks that the total invoice history without retention, plus the balance to finish = the revised contract

## PROGRESS PAYMT #11
PROGRESS PAYMENT
Project Name: | North Valley Reservoir Improvements |  |  |  |  | Page: |  | 1 of 1
Project No: | 7587 |  |  |  |  | Date of Application: |  | 2016-12-29
Resolution #: | 2015-3231 |  |  |  |  | Invoice Date: |  | 2016-12-21
Purchase Order No's: |  | 8091 |  |  |  | Pay Period Through: |  | 2016-12-21
The contract was approved by City Council on October 22, 2015 per Resolution No. 2015-3231 with a contract value of $1,815,165.00. | [5 empty] | Contractor: | Ward-Henshaw Const
[6 empty] | Payment No: |  | 11
Purchase Order is attached
Application is made for Payment, as shown below, in connection with the Contract. Attached is the contractor's signed request for payment. Payment due date per Contract specification. The present status of the account(s) for this Contract is as follows:
THIS PAYMENT
Original Contract | Change Orders | Revised Contract | Total Completed & Stored To Date | Total Retainage |  | Total Earned Less Retainage | Less Previous Certificates for Payment | Balance To Finish
1815165 | 2180.47 | 1817345.47 | 1817345.47 | 90867.2735 |  | 1726478.1965 | 56312.998 | 90867.2735
PROGRESS INVOICE HISTORY |  |  |  |  | CHANGE ORDER SUMMARY
Pay No. / Date | Invoice Amount | Retention | % Complete |  | Change Order # | Date Approved | PO# | Total Value
1 | 51753.169 | 2723.851 | 2.998% |  | 1 | 2015-12-18 | N/A | 61268.26
2 | 100917.5405 | 5311.4495 | 5.845% |  | 2 | 2016-03-25 | NA | 13486.63
3 | 403966.7615 | 21261.4085 | 23.4% |  | 3 | 2016-05-27 | NA | 5751.77
4 | 138492.767 | 7289.093 | 8.022% |  | 4 | 2016-12-22 | N/A | -78326.19
5 | 130944.1525 | 6891.7975 | 7.584%
6 | 298456.4935 | 15708.2365 | 17.29% |  |  |  | Total | 2180.47
7 | 268126.7175 | 14111.9325 | 15.53%
8 | 134327.739 | 7069.881 | 7.78%
9 | 39203.9825 | 2063.3675 | 2.271%
10 | 103975.8755 | 5472.4145 | 6.022%
11 | 56312.998 | 2963.842 | 3.262%
12 |  |  | 0% |  | CURRENT PAYMENT DUE
13 |  |  | 0%
14 |  |  | 0% |  | Account #: |  | Amount:
15 |  |  | 0% |  | 04-5150-707587 |  | 56312.998
16 |  |  | 0%
17 |  |  | 0% | [5 empty] | Payment Due Matches In different cells
18 |  |  | 0% | [5 empty] | CHECKS
19 |  |  | 0% |  | Total Payment: |  | 56312.998 |  | WRONG
20 |  |  | 0% | [5 empty] | CHECKS
Total | 1726478.1965 | 90867.2735 | 100%
Project Manager |  |  | Date |  | City Manager (if over $5,000.00) |  |  | Date
City Engineer |  |  | Date |  | Finance Director |  |  | Date
This certificate is not negotiable. It is payable only to the payee named herein and its issuance, payment and acceptance are without prejudice to any rights of the Owner or Contractor under their Contract.
Note on I4: Jason Wuertz: Add one number to the cell to move down one on the main page
Note on I10: Jason Wuertz: Add one number to the cell in the formula
Note on D19: Jason Wuertz: Add one number to the forumula cell
Note on H19: Jason Wuertz: Change sheet number
Note on B23: Jason Wuertz: When adding new tab, copy number from previous tab, not the formula
Note on C23: Jason Wuertz: =Total Retainage - sum of retention totals from previous payments
Note on K41: Jason Wuertz: This checks that Cell H42 matches H19 which it should
Note on K42: Jason Wuertz: Checks that H42 matches H24 which it should
Note on K43: Jason Wuertz: Checks that the total invoice history without retention, plus the balance to finish = the revised contract

## PROGRESS PAYMT #12
PROGRESS PAYMENT
Project Name: | North Valley Reservoir Improvements |  |  |  |  | Page: |  | 1 of 1
Project No: | 7587 |  |  |  |  | Date of Application: |  | 2017-04-04
Resolution #: | 2015-3231 |  |  |  |  | Invoice Date: |  | 2016-12-21
Purchase Order No's: |  | 8091 |  |  |  | Pay Period Through: |  | Final
The contract was approved by City Council on October 22, 2015 per Resolution No. 2015-3231 with a contract value of $1,815,165.00. | [5 empty] | Contractor: | Ward-Henshaw Const
[6 empty] | Payment No: |  | 12
Purchase Order is attached
Application is made for Payment, as shown below, in connection with the Contract. Attached is the contractor's signed request for payment. Payment due date per Contract specification. The present status of the account(s) for this Contract is as follows:
THIS PAYMENT
Original Contract | Change Orders | Revised Contract | Total Completed & Stored To Date | Total Retainage |  | Total Earned Less Retainage | Less Previous Certificates for Payment | Balance To Finish
1815165 | 2180.47 | 1817345.47 | 1817345.47 | 90867.2735 |  | 1726478.1965 | 0 | 0
PROGRESS INVOICE HISTORY |  |  |  |  | CHANGE ORDER SUMMARY
Pay No. / Date | Invoice Amount | Retention | % Complete |  | Change Order # | Date Approved | PO# | Total Value
1 | 51753.169 | 2723.851 | 2.998% |  | 1 | 2015-12-18 | N/A | 61268.26
2 | 100917.5405 | 5311.4495 | 5.845% |  | 2 | 2016-03-25 | NA | 13486.63
3 | 403966.7615 | 21261.4085 | 23.4% |  | 3 | 2016-05-27 | NA | 5751.77
4 | 138492.767 | 7289.093 | 8.022% |  | 4 | 2016-12-22 | N/A | -78326.19
5 | 130944.1525 | 6891.7975 | 7.584%
6 | 298456.4935 | 15708.2365 | 17.29% |  |  |  | Total | 2180.47
7 | 268126.7175 | 14111.9325 | 15.53%
8 | 134327.739 | 7069.881 | 7.78%
9 | 39203.9825 | 2063.3675 | 2.271%
10 | 103975.8755 | 5472.4145 | 6.022%
11 | 56312.998 | 2963.842 | 3.262%
Retainage | 90867.27 | -90867.27 | 0% |  | CURRENT PAYMENT DUE
13 |  |  | 0%
14 |  |  | 0% |  | Account #: |  | Amount:
15 |  |  | 0% |  | 04-5150-707587 |  | 0
16 |  |  | 0%
17 |  |  | 0% | [5 empty] | Payment Due Matches In different cells
18 |  |  | 0% | [5 empty] | 0
19 |  |  | 0% |  | Total Payment: |  | 90867.27 |  | WRONG
20 |  |  | 0% | [5 empty] | WRONG
Total | 1817345.4665 | 0.0035 | 100%
Project Manager |  |  | Date |  | City Manager (Pro-Tem) (if over $5,000.00) |  |  | Date
City Engineer |  |  | Date
This certificate is not negotiable. It is payable only to the payee named herein and its issuance, payment and acceptance are without prejudice to any rights of the Owner or Contractor under their Contract.
Note on I4: Jason Wuertz: Add one number to the cell to move down one on the main page
Note on I10: Jason Wuertz: Add one number to the cell in the formula
Note on D19: Jason Wuertz: Add one number to the forumula cell
Note on H19: Jason Wuertz: Change sheet number
Note on B23: Jason Wuertz: When adding new tab, copy number from previous tab, not the formula
Note on C23: Jason Wuertz: =Total Retainage - sum of retention totals from previous payments
Note on K41: Jason Wuertz: This checks that Cell H42 matches H19 which it should
Note on K42: Jason Wuertz: Checks that H42 matches H24 which it should
Note on K43: Jason Wuertz: Checks that the total invoice history without retention, plus the balance to finish = the revised contract

## PROGRESS PAYMT #13
PROGRESS PAYMENT
Project Name: | North Valley Reservoir Improvements |  |  |  |  | Page: |  | 1 of 1
Project No: | 7587 |  |  |  |  | Date of Application: |  | 0
Resolution #: | 2015-3231 |  |  |  |  | Invoice Date: |  | 0
Purchase Order No's: |  | 8091 |  |  |  | Pay Period Through: |  | 0
The contract was approved by City Council on October 22, 2015 per Resolution No. 2015-3231 with a contract value of $1,815,165.00. | [5 empty] | Contractor: | Ward-Henshaw Const
[6 empty] | Payment No: |  | 13
Purchase Order is attached
Application is made for Payment, as shown below, in connection with the Contract. Attached is the contractor's signed request for payment. Payment due date per Contract specification. The present status of the account(s) for this Contract is as follows:
THIS PAYMENT
Original Contract | Change Orders | Revised Contract | Total Completed & Stored To Date | Total Retainage |  | Total Earned Less Retainage | Less Previous Certificates for Payment | Balance To Finish
1815165 | 0 | 1815165 | 0 | 0 |  | 0 | -1817345.4665 | 1815165
PROGRESS INVOICE HISTORY |  |  |  |  | CHANGE ORDER SUMMARY
Pay No. / Date | Invoice Amount | Retention | % Complete |  | Change Order # | Date Approved | PO# | Total Value
1 | 51753.169 | 2723.851 | 3.001% |  | 1 | 2015-12-18 | N/A | 61268.26
2 | 100917.5405 | 5311.4495 | 5.852% |  | 2 | 42454 | NA | 13486.63
3 | 403966.7615 | 21261.4085 | 23.43% |  | 3 | 42517 | NA | 5751.77
4 | 138492.767 | 7289.093 | 8.031% |  | 4 | 42726 | N/A | -78326.19
5 | 130944.1525 | 6891.7975 | 7.594%
6 | 298456.4935 | 15708.2365 | 17.31% |  |  |  | Total | 0
7 | 268126.7175 | 14111.9325 | 15.55%
8 | 134327.739 | 7069.881 | 7.79%
9 | 39203.9825 | 2063.3675 | 2.273%
10 | 103975.8755 | 5472.4145 | 6.03%
11 | 56312.998 | 2963.842 | 3.266%
12 | 90867.27 | -90867.27 | 0% |  | CURRENT PAYMENT DUE
13 | -1817345.4665 | -0.0035 | -100.1%
14 |  |  | 0% |  | Account #: |  | Amount:
15 |  |  | 0% |  | 04-5150-707587 |  | -1726478.1965
16 |  |  | 0%
17 |  |  | 0% | [5 empty] | Payment Due Matches In different cells
18 |  |  | 0% | [5 empty] | 0
19 |  |  | 0% |  | Total Payment: |  | -1726478.1965 |  | WRONG
20 |  |  | 0% | [5 empty] | CHECKS
Total | 0 | 0 | -2.22e-14%
Project Manager |  |  | Date |  | City Manager (Pro-Tem) (if over $5,000.00) |  |  | Date
City Engineer |  |  | Date
This certificate is not negotiable. It is payable only to the payee named herein and its issuance, payment and acceptance are without prejudice to any rights of the Owner or Contractor under their Contract.
Note on I4: Jason Wuertz: Add one number to the cell to move down one on the main page
Note on I10: Jason Wuertz: Add one number to the cell in the formula
Note on D19: Jason Wuertz: Add one number to the forumula cell
Note on H19: Jason Wuertz: Change sheet number
Note on B23: Jason Wuertz: When adding new tab, copy number from previous tab, not the formula
Note on C23: Jason Wuertz: =Total Retainage - sum of retention totals from previous payments
Note on K41: Jason Wuertz: This checks that Cell H42 matches H19 which it should
Note on K42: Jason Wuertz: Checks that H42 matches H24 which it should
Note on K43: Jason Wuertz: Checks that the total invoice history without retention, plus the balance to finish = the revised contract

## PROGRESS PAYMT #14
PROGRESS PAYMENT
Project Name: | North Valley Reservoir Improvements |  |  |  |  | Page: |  | 1 of 1
Project No: | 7587 |  |  |  |  | Date of Application: |  | 0
Resolution #: | 2015-3231 |  |  |  |  | Invoice Date: |  | 0
Purchase Order No's: |  | 8091 |  |  |  | Pay Period Through: |  | 0
The contract was approved by City Council on October 22, 2015 per Resolution No. 2015-3231 with a contract value of $1,815,165.00. | [5 empty] | Contractor: | Ward-Henshaw Const
[6 empty] | Payment No: |  | 14
Purchase Order is attached
Application is made for Payment, as shown below, in connection with the Contract. Attached is the contractor's signed request for payment. Payment due date per Contract specification. The present status of the account(s) for this Contract is as follows:
THIS PAYMENT
Original Contract | Change Orders | Revised Contract | Total Completed & Stored To Date | Total Retainage |  | Total Earned Less Retainage | Less Previous Certificates for Payment | Balance To Finish
1815165 | 0 | 1815165 | 0 | 0 |  | 0 | 0 | 1815165
PROGRESS INVOICE HISTORY |  |  |  |  | CHANGE ORDER SUMMARY
Pay No. / Date | Invoice Amount | Retention | % Complete |  | Change Order # | Date Approved | PO# | Total Value
1 | 51753.169 | 2723.851 | 3.001% |  | 1 | 2015-12-18 | N/A | 61268.26
2 | 100917.5405 | 5311.4495 | 5.852% |  | 2 | 42454 | NA | 13486.63
3 | 403966.7615 | 21261.4085 | 23.43% |  | 3 | 42517 | NA | 5751.77
4 | 138492.767 | 7289.093 | 8.031% |  | 4 | 42726 | N/A | -78326.19
5 | 130944.1525 | 6891.7975 | 7.594%
6 | 298456.4935 | 15708.2365 | 17.31% |  |  |  | Total | 0
7 | 268126.7175 | 14111.9325 | 15.55%
8 | 134327.739 | 7069.881 | 7.79%
9 | 39203.9825 | 2063.3675 | 2.273%
10 | 103975.8755 | 5472.4145 | 6.03%
11 | 56312.998 | 2963.842 | 3.266%
12 | 90867.27 | -90867.27 | 0% |  | CURRENT PAYMENT DUE
13 | -1817345.4665 | -0.0035 | -100.1%
14 | 0 | 0 | 0% |  | Account #: |  | Amount:
15 |  |  | 0% |  | 04-5150-707587 |  | 0
16 |  |  | 0%
17 |  |  | 0% | [5 empty] | Payment Due Matches In different cells
18 |  |  | 0% | [5 empty] | CHECKS
19 |  |  | 0% |  | Total Payment: |  | 0 |  | WRONG
20 |  |  | 0% | [5 empty] | CHECKS
Total | 0 | 0 | -2.22e-14%
Project Manager |  |  | Date |  | City Manager (Pro-Tem) (if over $5,000.00) |  |  | Date
City Engineer |  |  | Date
This certificate is not negotiable. It is payable only to the payee named herein and its issuance, payment and acceptance are without prejudice to any rights of the Owner or Contractor under their Contract.
Note on I4: Jason Wuertz: Add one number to the cell to move down one on the main page
Note on I10: Jason Wuertz: Add one number to the cell in the formula
Note on D19: Jason Wuertz: Add one number to the forumula cell
Note on H19: Jason Wuertz: Change sheet number
Note on B23: Jason Wuertz: When adding new tab, copy number from previous tab, not the formula
Note on C23: Jason Wuertz: =Total Retainage - sum of retention totals from previous payments
Note on K41: Jason Wuertz: This checks that Cell H42 matches H19 which it should
Note on K42: Jason Wuertz: Checks that H42 matches H24 which it should
Note on K43: Jason Wuertz: Checks that the total invoice history without retention, plus the balance to finish = the revised contract

## PROGRESS PAYMT #15
PROGRESS PAYMENT
Project Name: | North Valley Reservoir Improvements |  |  |  |  | Page: |  | 1 of 1
Project No: | 7587 |  |  |  |  | Date of Application: |  | 0
Resolution #: | 2015-3231 |  |  |  |  | Invoice Date: |  | 0
Purchase Order No's: |  | 8091 |  |  |  | Pay Period Through: |  | 0
The contract was approved by City Council on October 22, 2015 per Resolution No. 2015-3231 with a contract value of $1,815,165.00. | [5 empty] | Contractor: | Ward-Henshaw Const
[6 empty] | Payment No: |  | 15
Purchase Order is attached
Application is made for Payment, as shown below, in connection with the Contract. Attached is the contractor's signed request for payment. Payment due date per Contract specification. The present status of the account(s) for this Contract is as follows:
THIS PAYMENT
Original Contract | Change Orders | Revised Contract | Total Completed & Stored To Date | Total Retainage |  | Total Earned Less Retainage | Less Previous Certificates for Payment | Balance To Finish
1815165 | 0 | 1815165 | 0 | 0 |  | 0 | 0 | 1815165
PROGRESS INVOICE HISTORY |  |  |  |  | CHANGE ORDER SUMMARY
Pay No. / Date | Invoice Amount | Retention | % Complete |  | Change Order # | Date Approved | PO# | Total Value
1 | 51753.169 | 2723.851 | 3.001% |  | 1 | 2015-12-18 | N/A | 61268.26
2 | 100917.5405 | 5311.4495 | 5.852% |  | 2 | 42454 | NA | 13486.63
3 | 403966.7615 | 21261.4085 | 23.43% |  | 3 | 42517 | NA | 5751.77
4 | 138492.767 | 7289.093 | 8.031% |  | 4 | 42726 | N/A | -78326.19
5 | 130944.1525 | 6891.7975 | 7.594%
6 | 298456.4935 | 15708.2365 | 17.31% |  |  |  | Total | 0
7 | 268126.7175 | 14111.9325 | 15.55%
8 | 134327.739 | 7069.881 | 7.79%
9 | 39203.9825 | 2063.3675 | 2.273%
10 | 103975.8755 | 5472.4145 | 6.03%
11 | 56312.998 | 2963.842 | 3.266%
12 | 90867.27 | -90867.27 | 0% |  | CURRENT PAYMENT DUE
13 | -1817345.4665 | -0.0035 | -100.1%
14 | 0 | 0 | 0% |  | Account #: |  | Amount:
15 | 0 | 0 | 0% |  | 04-5150-707587 |  | 0
16 |  |  | 0%
17 |  |  | 0% | [5 empty] | Payment Due Matches In different cells
18 |  |  | 0% | [5 empty] | CHECKS
19 |  |  | 0% |  | Total Payment: |  | 0 |  | WRONG
20 |  |  | 0% | [5 empty] | CHECKS
Total | 0 | 0 | -2.22e-14%
Project Manager |  |  | Date |  | City Manager (Pro-Tem) (if over $5,000.00) |  |  | Date
City Engineer |  |  | Date
This certificate is not negotiable. It is payable only to the payee named herein and its issuance, payment and acceptance are without prejudice to any rights of the Owner or Contractor under their Contract.
Note on I4: Jason Wuertz: Add one number to the cell to move down one on the main page
Note on I10: Jason Wuertz: Add one number to the cell in the formula
Note on D19: Jason Wuertz: Add one number to the forumula cell
Note on H19: Jason Wuertz: Change sheet number
Note on B23: Jason Wuertz: When adding new tab, copy number from previous tab, not the formula
Note on C23: Jason Wuertz: =Total Retainage - sum of retention totals from previous payments
Note on K41: Jason Wuertz: This checks that Cell H42 matches H19 which it should
Note on K42: Jason Wuertz: Checks that H42 matches H24 which it should
Note on K43: Jason Wuertz: Checks that the total invoice history without retention, plus the balance to finish = the revised contract

## PROGRESS PAYMT #16
PROGRESS PAYMENT
Project Name: | North Valley Reservoir Improvements |  |  |  |  | Page: |  | 1 of 1
Project No: | 7587 |  |  |  |  | Date of Application: |  | 0
Resolution #: | 2015-3231 |  |  |  |  | Invoice Date: |  | 0
Purchase Order No's: |  | 8091 |  |  |  | Pay Period Through: |  | 0
The contract was approved by City Council on October 22, 2015 per Resolution No. 2015-3231 with a contract value of $1,815,165.00. | [5 empty] | Contractor: | Ward-Henshaw Const
[6 empty] | Payment No: |  | 16
Purchase Order is attached
Application is made for Payment, as shown below, in connection with the Contract. Attached is the contractor's signed request for payment. Payment due date per Contract specification. The present status of the account(s) for this Contract is as follows:
THIS PAYMENT
Original Contract | Change Orders | Revised Contract | Total Completed & Stored To Date | Total Retainage |  | Total Earned Less Retainage | Less Previous Certificates for Payment | Balance To Finish
1815165 | 0 | 1815165 | 0 | 0 |  | 0 | 0 | 1815165
PROGRESS INVOICE HISTORY |  |  |  |  | CHANGE ORDER SUMMARY
Pay No. / Date | Invoice Amount | Retention | % Complete |  | Change Order # | Date Approved | PO# | Total Value
1 | 51753.169 | 2723.851 | 3.001% |  | 1 | 2015-12-18 | N/A | 61268.26
2 | 100917.5405 | 5311.4495 | 5.852% |  | 2 | 42454 | NA | 13486.63
3 | 403966.7615 | 21261.4085 | 23.43% |  | 3 | 42517 | NA | 5751.77
4 | 138492.767 | 7289.093 | 8.031% |  | 4 | 42726 | N/A | -78326.19
5 | 130944.1525 | 6891.7975 | 7.594%
6 | 298456.4935 | 15708.2365 | 17.31% |  |  |  | Total | 0
7 | 268126.7175 | 14111.9325 | 15.55%
8 | 134327.739 | 7069.881 | 7.79%
9 | 39203.9825 | 2063.3675 | 2.273%
10 | 103975.8755 | 5472.4145 | 6.03%
11 | 56312.998 | 2963.842 | 3.266%
12 | 90867.27 | -90867.27 | 0% |  | CURRENT PAYMENT DUE
13 | -1817345.4665 | -0.0035 | -100.1%
14 | 0 | 0 | 0% |  | Account #: |  | Amount:
15 | 0 | 0 | 0% |  | 04-5150-707587 |  | 0
16 | 0 | 0 | 0%
17 |  |  | 0% | [5 empty] | Payment Due Matches In different cells
18 |  |  | 0% | [5 empty] | CHECKS
19 |  |  | 0% |  | Total Payment: |  | 0 |  | WRONG
20 |  |  | 0% | [5 empty] | CHECKS
Total | 0 | 0 | -2.22e-14%
Project Manager |  |  | Date |  | City Manager (Pro-Tem) (if over $5,000.00) |  |  | Date
City Engineer |  |  | Date
This certificate is not negotiable. It is payable only to the payee named herein and its issuance, payment and acceptance are without prejudice to any rights of the Owner or Contractor under their Contract.
Note on I4: Jason Wuertz: Add one number to the cell to move down one on the main page
Note on I10: Jason Wuertz: Add one number to the cell in the formula
Note on D19: Jason Wuertz: Add one number to the forumula cell
Note on H19: Jason Wuertz: Change sheet number
Note on B23: Jason Wuertz: When adding new tab, copy number from previous tab, not the formula
Note on C23: Jason Wuertz: =Total Retainage - sum of retention totals from previous payments
Note on K41: Jason Wuertz: This checks that Cell H42 matches H19 which it should
Note on K42: Jason Wuertz: Checks that H42 matches H24 which it should
Note on K43: Jason Wuertz: Checks that the total invoice history without retention, plus the balance to finish = the revised contract

## PROGRESS PAYMT #17
PROGRESS PAYMENT
Project Name: | North Valley Reservoir Improvements |  |  |  |  | Page: |  | 1 of 1
Project No: | 7587 |  |  |  |  | Date of Application: |  | 0
Resolution #: | 2015-3231 |  |  |  |  | Invoice Date: |  | 0
Purchase Order No's: |  | 8091 |  |  |  | Pay Period Through: |  | 0
The contract was approved by City Council on October 22, 2015 per Resolution No. 2015-3231 with a contract value of $1,815,165.00. | [5 empty] | Contractor: | Ward-Henshaw Const
[6 empty] | Payment No: |  | 17
Purchase Order is attached
Application is made for Payment, as shown below, in connection with the Contract. Attached is the contractor's signed request for payment. Payment due date per Contract specification. The present status of the account(s) for this Contract is as follows:
THIS PAYMENT
Original Contract | Change Orders | Revised Contract | Total Completed & Stored To Date | Total Retainage |  | Total Earned Less Retainage | Less Previous Certificates for Payment | Balance To Finish
1815165 | 0 | 1815165 | 0 | 0 |  | 0 | 0 | 1815165
PROGRESS INVOICE HISTORY |  |  |  |  | CHANGE ORDER SUMMARY
Pay No. / Date | Invoice Amount | Retention | % Complete |  | Change Order # | Date Approved | PO# | Total Value
1 | 51753.169 | 2723.851 | 3.001% |  | 1 | 2015-12-18 | N/A | 61268.26
2 | 100917.5405 | 5311.4495 | 5.852% |  | 2 | 42454 | NA | 13486.63
3 | 403966.7615 | 21261.4085 | 23.43% |  | 3 | 42517 | NA | 5751.77
4 | 138492.767 | 7289.093 | 8.031% |  | 4 | 42726 | N/A | -78326.19
5 | 130944.1525 | 6891.7975 | 7.594%
6 | 298456.4935 | 15708.2365 | 17.31% |  |  |  | Total | 0
7 | 268126.7175 | 14111.9325 | 15.55%
8 | 134327.739 | 7069.881 | 7.79%
9 | 39203.9825 | 2063.3675 | 2.273%
10 | 103975.8755 | 5472.4145 | 6.03%
11 | 56312.998 | 2963.842 | 3.266%
12 | 90867.27 | -90867.27 | 0% |  | CURRENT PAYMENT DUE
13 | -1817345.4665 | -0.0035 | -100.1%
14 | 0 | 0 | 0% |  | Account #: |  | Amount:
15 | 0 | 0 | 0% |  | 04-5150-707587 |  | 0
16 | 0 | 0 | 0%
17 | 0 | 0 | 0% | [5 empty] | Payment Due Matches In different cells
18 |  |  | 0% | [5 empty] | CHECKS
19 |  |  | 0% |  | Total Payment: |  | 0 |  | WRONG
20 |  |  | 0% | [5 empty] | CHECKS
Total | 0 | 0 | -2.22e-14%
Project Manager |  |  | Date |  | City Manager (Pro-Tem) (if over $5,000.00) |  |  | Date
City Engineer |  |  | Date
This certificate is not negotiable. It is payable only to the payee named herein and its issuance, payment and acceptance are without prejudice to any rights of the Owner or Contractor under their Contract.
Note on I4: Jason Wuertz: Add one number to the cell to move down one on the main page
Note on I10: Jason Wuertz: Add one number to the cell in the formula
Note on D19: Jason Wuertz: Add one number to the forumula cell
Note on H19: Jason Wuertz: Change sheet number
Note on B23: Jason Wuertz: When adding new tab, copy number from previous tab, not the formula
Note on C23: Jason Wuertz: =Total Retainage - sum of retention totals from previous payments
Note on K41: Jason Wuertz: This checks that Cell H42 matches H19 which it should
Note on K42: Jason Wuertz: Checks that H42 matches H24 which it should
Note on K43: Jason Wuertz: Checks that the total invoice history without retention, plus the balance to finish = the revised contract

## PROGRESS PAYMT #18
PROGRESS PAYMENT
Project Name: | North Valley Reservoir Improvements |  |  |  |  | Page: |  | 1 of 1
Project No: | 7587 |  |  |  |  | Date of Application: |  | 0
Resolution #: | 2015-3231 |  |  |  |  | Invoice Date: |  | 0
Purchase Order No's: |  | 8091 |  |  |  | Pay Period Through: |  | 0
The contract was approved by City Council on October 22, 2015 per Resolution No. 2015-3231 with a contract value of $1,815,165.00. | [5 empty] | Contractor: | Ward-Henshaw Const
[6 empty] | Payment No: |  | 18
Purchase Order is attached
Application is made for Payment, as shown below, in connection with the Contract. Attached is the contractor's signed request for payment. Payment due date per Contract specification. The present status of the account(s) for this Contract is as follows:
THIS PAYMENT
Original Contract | Change Orders | Revised Contract | Total Completed & Stored To Date | Total Retainage |  | Total Earned Less Retainage | Less Previous Certificates for Payment | Balance To Finish
1815165 | 0 | 1815165 | 0 | 0 |  | 0 | 0 | 1815165
PROGRESS INVOICE HISTORY |  |  |  |  | CHANGE ORDER SUMMARY
Pay No. / Date | Invoice Amount | Retention | % Complete |  | Change Order # | Date Approved | PO# | Total Value
1 | 51753.169 | 2723.851 | 3.001% |  | 1 | 2015-12-18 | N/A | 61268.26
2 | 100917.5405 | 5311.4495 | 5.852% |  | 2 | 42454 | NA | 13486.63
3 | 403966.7615 | 21261.4085 | 23.43% |  | 3 | 42517 | NA | 5751.77
4 | 138492.767 | 7289.093 | 8.031% |  | 4 | 42726 | N/A | -78326.19
5 | 130944.1525 | 6891.7975 | 7.594%
6 | 298456.4935 | 15708.2365 | 17.31% |  |  |  | Total | 0
7 | 268126.7175 | 14111.9325 | 15.55%
8 | 134327.739 | 7069.881 | 7.79%
9 | 39203.9825 | 2063.3675 | 2.273%
10 | 103975.8755 | 5472.4145 | 6.03%
11 | 56312.998 | 2963.842 | 3.266%
12 | 90867.27 | -90867.27 | 0% |  | CURRENT PAYMENT DUE
13 | -1817345.4665 | -0.0035 | -100.1%
14 | 0 | 0 | 0% |  | Account #: |  | Amount:
15 | 0 | 0 | 0% |  | 04-5150-707587 |  | 0
16 | 0 | 0 | 0%
17 | 0 | 0 | 0% | [5 empty] | Payment Due Matches In different cells
18 | 0 | 0 | 0% | [5 empty] | CHECKS
19 |  |  | 0% |  | Total Payment: |  | 0 |  | WRONG
20 |  |  | 0% | [5 empty] | CHECKS
Total | 0 | 0 | -2.22e-14%
Project Manager |  |  | Date |  | City Manager (Pro-Tem) (if over $5,000.00) |  |  | Date
City Engineer |  |  | Date
This certificate is not negotiable. It is payable only to the payee named herein and its issuance, payment and acceptance are without prejudice to any rights of the Owner or Contractor under their Contract.
Note on I4: Jason Wuertz: Add one number to the cell to move down one on the main page
Note on I10: Jason Wuertz: Add one number to the cell in the formula
Note on D19: Jason Wuertz: Add one number to the forumula cell
Note on H19: Jason Wuertz: Change sheet number
Note on B23: Jason Wuertz: When adding new tab, copy number from previous tab, not the formula
Note on C23: Jason Wuertz: =Total Retainage - sum of retention totals from previous payments
Note on K41: Jason Wuertz: This checks that Cell H42 matches H19 which it should
Note on K42: Jason Wuertz: Checks that H42 matches H24 which it should
Note on K43: Jason Wuertz: Checks that the total invoice history without retention, plus the balance to finish = the revised contract

## PROGRESS PAYMT #19
PROGRESS PAYMENT
Project Name: | North Valley Reservoir Improvements |  |  |  |  | Page: |  | 1 of 1
Project No: | 7587 |  |  |  |  | Date of Application: |  | 0
Resolution #: | 2015-3231 |  |  |  |  | Invoice Date: |  | 0
Purchase Order No's: |  | 8091 |  |  |  | Pay Period Through: |  | 0
The contract was approved by City Council on October 22, 2015 per Resolution No. 2015-3231 with a contract value of $1,815,165.00. | [5 empty] | Contractor: | Ward-Henshaw Const
[6 empty] | Payment No: |  | 19
Purchase Order is attached
Application is made for Payment, as shown below, in connection with the Contract. Attached is the contractor's signed request for payment. Payment due date per Contract specification. The present status of the account(s) for this Contract is as follows:
THIS PAYMENT
Original Contract | Change Orders | Revised Contract | Total Completed & Stored To Date | Total Retainage |  | Total Earned Less Retainage | Less Previous Certificates for Payment | Balance To Finish
1815165 | 0 | 1815165 | 0 | 0 |  | 0 | 0 | 1815165
PROGRESS INVOICE HISTORY |  |  |  |  | CHANGE ORDER SUMMARY
Pay No. / Date | Invoice Amount | Retention | % Complete |  | Change Order # | Date Approved | PO# | Total Value
1 | 51753.169 | 2723.851 | 3.001% |  | 1 | 2015-12-18 | N/A | 61268.26
2 | 100917.5405 | 5311.4495 | 5.852% |  | 2 | 42454 | NA | 13486.63
3 | 403966.7615 | 21261.4085 | 23.43% |  | 3 | 42517 | NA | 5751.77
4 | 138492.767 | 7289.093 | 8.031% |  | 4 | 42726 | N/A | -78326.19
5 | 130944.1525 | 6891.7975 | 7.594%
6 | 298456.4935 | 15708.2365 | 17.31% |  |  |  | Total | 0
7 | 268126.7175 | 14111.9325 | 15.55%
8 | 134327.739 | 7069.881 | 7.79%
9 | 39203.9825 | 2063.3675 | 2.273%
10 | 103975.8755 | 5472.4145 | 6.03%
11 | 56312.998 | 2963.842 | 3.266%
12 | 90867.27 | -90867.27 | 0% |  | CURRENT PAYMENT DUE
13 | -1817345.4665 | -0.0035 | -100.1%
14 | 0 | 0 | 0% |  | Account #: |  | Amount:
15 | 0 | 0 | 0% |  | 04-5150-707587 |  | 0
16 | 0 | 0 | 0%
17 | 0 | 0 | 0% | [5 empty] | Payment Due Matches In different cells
18 | 0 | 0 | 0% | [5 empty] | CHECKS
19 | 0 | 0 | 0% |  | Total Payment: |  | 0 |  | WRONG
20 |  |  | 0% | [5 empty] | CHECKS
Total | 0 | 0 | -2.22e-14%
Project Manager |  |  | Date |  | City Manager (Pro-Tem) (if over $5,000.00) |  |  | Date
City Engineer |  |  | Date
This certificate is not negotiable. It is payable only to the payee named herein and its issuance, payment and acceptance are without prejudice to any rights of the Owner or Contractor under their Contract.
Note on I4: Jason Wuertz: Add one number to the cell to move down one on the main page
Note on I10: Jason Wuertz: Add one number to the cell in the formula
Note on D19: Jason Wuertz: Add one number to the forumula cell
Note on H19: Jason Wuertz: Change sheet number
Note on B23: Jason Wuertz: When adding new tab, copy number from previous tab, not the formula
Note on C23: Jason Wuertz: =Total Retainage - sum of retention totals from previous payments
Note on K41: Jason Wuertz: This checks that Cell H42 matches H19 which it should
Note on K42: Jason Wuertz: Checks that H42 matches H24 which it should
Note on K43: Jason Wuertz: Checks that the total invoice history without retention, plus the balance to finish = the revised contract

## PROGRESS PAYMT #20
PROGRESS PAYMENT
Project Name: | North Valley Reservoir Improvements |  |  |  |  | Page: |  | 1 of 1
Project No: | 7587 |  |  |  |  | Date of Application: |  | 0
Resolution #: | 2015-3231 |  |  |  |  | Invoice Date: |  | 0
Purchase Order No's: |  | 8091 |  |  |  | Pay Period Through: |  | 0
The contract was approved by City Council on October 22, 2015 per Resolution No. 2015-3231 with a contract value of $1,815,165.00. | [5 empty] | Contractor: | Ward-Henshaw Const
[6 empty] | Payment No: |  | 20
Purchase Order is attached
Application is made for Payment, as shown below, in connection with the Contract. Attached is the contractor's signed request for payment. Payment due date per Contract specification. The present status of the account(s) for this Contract is as follows:
THIS PAYMENT
Original Contract | Change Orders | Revised Contract | Total Completed & Stored To Date | Total Retainage |  | Total Earned Less Retainage | Less Previous Certificates for Payment | Balance To Finish
1815165 | 0 | 1815165 | 0 | 0 |  | 0 | 0 | 1815165
PROGRESS INVOICE HISTORY |  |  |  |  | CHANGE ORDER SUMMARY
Pay No. / Date | Invoice Amount | Retention | % Complete |  | Change Order # | Date Approved | PO# | Total Value
1 | 51753.169 | 2723.851 | 3.001% |  | 1 | 2015-12-18 | N/A | 61268.26
2 | 100917.5405 | 5311.4495 | 5.852% |  | 2 | 42454 | NA | 13486.63
3 | 403966.7615 | 21261.4085 | 23.43% |  | 3 | 42517 | NA | 5751.77
4 | 138492.767 | 7289.093 | 8.031% |  | 4 | 42726 | N/A | -78326.19
5 | 130944.1525 | 6891.7975 | 7.594%
6 | 298456.4935 | 15708.2365 | 17.31% |  |  |  | Total | 0
7 | 268126.7175 | 14111.9325 | 15.55%
8 | 134327.739 | 7069.881 | 7.79%
9 | 39203.9825 | 2063.3675 | 2.273%
10 | 103975.8755 | 5472.4145 | 6.03%
11 | 56312.998 | 2963.842 | 3.266%
12 | 90867.27 | -90867.27 | 0% |  | CURRENT PAYMENT DUE
13 | -1817345.4665 | -0.0035 | -100.1%
14 | 0 | 0 | 0% |  | Account #: |  | Amount:
15 | 0 | 0 | 0% |  | 04-5150-707587 |  | 0
16 | 0 | 0 | 0%
17 | 0 | 0 | 0% | [5 empty] | Payment Due Matches In different cells
18 | 0 | 0 | 0% | [5 empty] | CHECKS
19 | 0 | 0 | 0% |  | Total Payment: |  | 0 |  | WRONG
20 | 0 | 0 | 0% | [5 empty] | CHECKS
Total | 0 | 0 | -2.22e-14%
Project Manager |  |  | Date |  | City Manager (Pro-Tem) (if over $5,000.00) |  |  | Date
City Engineer |  |  | Date
This certificate is not negotiable. It is payable only to the payee named herein and its issuance, payment and acceptance are without prejudice to any rights of the Owner or Contractor under their Contract.
Note on I4: Jason Wuertz: Add one number to the cell to move down one on the main page
Note on I10: Jason Wuertz: Add one number to the cell in the formula
Note on D19: Jason Wuertz: Add one number to the forumula cell
Note on H19: Jason Wuertz: Change sheet number
Note on B23: Jason Wuertz: When adding new tab, copy number from previous tab, not the formula
Note on C23: Jason Wuertz: =Total Retainage - sum of retention totals from previous payments
Note on K41: Jason Wuertz: This checks that Cell H42 matches H19 which it should
Note on K42: Jason Wuertz: Checks that H42 matches H24 which it should
Note on K43: Jason Wuertz: Checks that the total invoice history without retention, plus the balance to finish = the revised contract