## PROGRESS PAYMT #1
PROGRESS PAYMENT
Project Name: | N. Springbrook - N. Elliot Pavement Project |  |  |  |  | Page: |  | 1 of 1
Project No: | 702171 |  |  |  |  | Date of Application: |  | 2016-10-17
Resolution No: | 2016-3318 |  |  |  |  | Invoice Date: |  | 2016-09-30
Purchase Order No's: |  | 17-057 |  |  |  | Pay Period Through: |  | 2016-09-29
Amendment #
The Original Kodiak Pacific Construction Contract was approved by City Council per Resolution No.2016-3318. | [5 empty] | Contractor: | Kodiak Pacific Construction
[6 empty] | Payment No: 1 | 1
Purchase Order is attached
Application is made for Payment, as shown below, in connection with the Contract. Attached is the contractor's signed request for payment. Payment due date per Contract specification. The present status of the account(s) for this Contract is as follows:
THIS PAYMENT
Original Contract | Change Orders | Revised Contract | Total Completed & Stored To Date | Total Retainage |  | Total Earned Less Retainage | Less Previous Certificates for Payment | Balance To Finish
191400 | -1395 | 190005 | 144031.49 | 7201.6045 |  | 136829.8855 | 0 | 47368.51
PROGRESS INVOICE HISTORY |  |  |  |  | CHANGE ORDER SUMMARY
Pay No. / Date | Invoice Amount | Retention | % Complete |  | Change Order # | Date Approved | Total Value
1 | 144031.49 | 7201.6045 | 79.59% |  | 1 | 2016-09-19 | -1395
2 |  |  | 0%
3 |  |  | 0%
4 |  |  | 0%
5 |  |  | 0%
6 |  |  | 0% |  |  | Total | -1395
7 |  |  | 0%
8 |  |  | 0% |  | OWNER CONTINGENCY SUMMARY (Part of Original Contract)
9 |  |  | 0%
10 |  |  | 0% |  | Issue # | Date Approved | Total Value
11 |  |  | 0%
12 |  |  | 0%
13 |  |  | 0%
14 |  |  | 0%
15 |  |  | 0%
16 |  |  | 0%
17 |  |  | 0%
18 |  |  | 0%
19 |  |  | 0%
20 |  |  | 0%
Total | 144031.49 | 7201.6045 | 79.59%
[6 empty] | Total to Date | 0
[6 empty] | Total Available | 0
Project Manager |  |  | Date |  |  | Remaining | 0
City Engineer |  |  | Date |  |  | CURRENT PAYMENT DUE
Account Number:
City Manager (if over $5,000.00) |  |  | Date
136829.8855
Finance Director |  |  | Date
This certificate is not negotiable. It is payable only to the payee named herein and its issuance, payment and acceptance are without prejudice to any rights of the Owner or Contractor under their Contract.

## PROGRESS PAYMT #2
PROGRESS PAYMENT
Project Name: | N. Springbrook - N. Elliot Pavement Project |  |  |  |  | Page: |  | 1 of 1
Project No: | 702171 |  |  |  |  | Date of Application: |  | 2016-12-05
Resolution # | 2016-3318 |  |  |  |  | Invoice Date: |  | 2016-10-31
Purchase Order No's: |  | 17-057 |  |  |  | Pay Period Through: |  | 2016-10-21
Amendment # | 0
The Original Kodiak Pacific Construction Contract was approved by City Council per Resolution No.2016-3318. | [5 empty] | Contractor: | Kodiak Pacific Construction
[6 empty] | Payment No : | 2
Purchase Order is attached
Application is made for Payment, as shown below, in connection with the Contract. Attached is the contractor's signed request for payment. Payment due date per Contract specification. The present status of the account(s) for this Contract is as follows:
THIS PAYMENT
Original Contract | Change Orders | Revised Contract | Total Completed & Stored To Date | Total Retainage |  | Total Earned Less Retainage | Less Previous Certificates for Payment | Balance To Finish
191400 | -1395 | 190005 | 204879.44 | 10243.99 |  | 194635.45 | 136829.8855 | -14874.44
PROGRESS INVOICE HISTORY |  |  |  |  | CHANGE ORDER SUMMARY
Pay No. / Date | Invoice Amount | Retention | % Complete |  | Change Order # | Date Approved | Total Value
1 | 144031.69 | 7201.6045 | 79.59% |  | 1 | 2016-09-19 | -1395
2 | 60847.75 | 3042.39 | 33.63%
3 |  |  | 0%
4 |  |  | 0%
5 |  |  | 0%
6 |  |  | 0% |  |  | Total | -1395
7 |  |  | 0%
8 |  |  | 0% |  | OWNER CONTINGENCY SUMMARY (Part of Original Contract)
9 |  |  | 0%
10 |  |  | 0% |  | Issue # | Date Approved | Total Value
11 |  |  | 0%
12 |  |  | 0%
13 |  |  | 0%
14 |  |  | 0%
15 |  |  | 0%
16 |  |  | 0%
17 |  |  | 0%
18 |  |  | 0%
19 |  |  | 0%
20 |  |  | 0%
Total | 204879.44 | 10243.9945 | 113.2%
[6 empty] | Total to Date | 0
[6 empty] | Total Available | 0
Project Manager |  |  | Date |  |  | Remaining | 0
City Engineer |  |  | Date |  |  | CURRENT PAYMENT DUE
Account Number:
City Manager (if over $5,000.00) |  |  | Date
57805.36
Finance |  |  | Date
This certificate is not negotiable. It is payable only to the payee named herein and its issuance, payment and acceptance are without prejudice to any rights of the Owner or Contractor under their Contract.

## PROGRESS PAYMT #3
PROGRESS PAYMENT
Project Name: | N. Springbrook - N. Elliot Pavement Project |  |  |  |  | Page: |  | 1 of 1
Project No: | 702171 |  |  |  |  | Date of Application:
Resolution # | 2016-3318 |  |  |  |  | Invoice Date:
Purchase Order No's: |  | 17-057 |  |  |  | Pay Period Through:
Amendment # | 0
The Original Kodiak Pacific Construction Contract was approved by City Council per Resolution No.2016-3318. | [5 empty] | Contractor: | Kodiak Pacific Construction
[6 empty] | Payment No : | 3
Purchase Order is attached
Application is made for Payment, as shown below, in connection with the Contract. Attached is the contractor's signed request for payment. Payment due date per Contract specification. The present status of the account(s) for this Contract is as follows:
THIS PAYMENT
Original Contract | Change Orders | Revised Contract | Total Completed & Stored To Date | Total Retainage |  | Total Earned Less Retainage | Less Previous Certificates for Payment | Balance To Finish
0 | 0 | 0 | 0 | 0 |  | 0 | -204879.44 | 0
PROGRESS INVOICE HISTORY |  |  |  |  | CHANGE ORDER SUMMARY
Pay No. / Date | Invoice Amount | Retention | % Complete |  | Change Order # | Date Approved | Total Value
1 | 0 | 7201.6045 | #DIV/0!
2 | 0 | 3042.39 | #DIV/0!
3 | 0 | 0 | #DIV/0!
4 |  |  | #DIV/0!
5 |  |  | #DIV/0!
6 |  |  | #DIV/0! |  |  | Total | 0
7 |  |  | #DIV/0!
8 |  |  | #DIV/0! |  | OWNER CONTINGENCY SUMMARY (Part of Original Contract)
9 |  |  | #DIV/0!
10 |  |  | #DIV/0! |  | Issue # | Date Approved | Total Value
11 |  |  | #DIV/0!
12 |  |  | #DIV/0!
13 |  |  | #DIV/0!
14 |  |  | #DIV/0!
15 |  |  | #DIV/0!
16 |  |  | #DIV/0!
17 |  |  | #DIV/0!
18 |  |  | #DIV/0!
19 |  |  | #DIV/0!
20 |  |  | #DIV/0!
Total | 0 | 10243.9945 | #DIV/0!
[6 empty] | Total to Date | 0
[6 empty] | Total Available | 0
Project Manager |  |  | Date |  |  | Remaining | 0
City Engineer / Interim Public Works Director |  |  | Date |  |  | CURRENT PAYMENT DUE
Account Number:
City Manager (Pro-Tem) (if over $5,000.00) |  |  | Date
-204879.44
This certificate is not negotiable. It is payable only to the payee named herein and its issuance, payment and acceptance are without prejudice to any rights of the Owner or Contractor under their Contract.

## PROGRESS PAYMT #4
PROGRESS PAYMENT
Project Name: | N. Springbrook - N. Elliot Pavement Project |  |  |  |  | Page: |  | 1 of 1
Project No: | 702171 |  |  |  |  | Date of Application:
Resolution # | 2016-3318 |  |  |  |  | Invoice Date:
Purchase Order No's: |  | 17-057 |  |  |  | Pay Period Through:
Amendment # | 0
The Original Kodiak Pacific Construction Contract was approved by City Council per Resolution No.2016-3318. | [5 empty] | Contractor: | Kodiak Pacific Construction
[6 empty] | Payment No : | 4
Purchase Order is attached
Application is made for Payment, as shown below, in connection with the Contract. Attached is the contractor's signed request for payment. Payment due date per Contract specification. The present status of the account(s) for this Contract is as follows:
THIS PAYMENT
Original Contract | Change Orders | Revised Contract | Total Completed & Stored To Date | Total Retainage |  | Total Earned Less Retainage | Less Previous Certificates for Payment | Balance To Finish
0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
PROGRESS INVOICE HISTORY |  |  |  |  | CHANGE ORDER SUMMARY
Pay No. / Date | Invoice Amount | Retention | % Complete |  | Change Order # | Date Approved | Total Value
1 | 0 | 7201.6045 | #DIV/0!
2 | 0 | 3042.39 | #DIV/0!
3 | 0 | 0 | #DIV/0!
4 | 0 | -10243.9945 | #DIV/0!
5 |  |  | #DIV/0!
6 |  |  | #DIV/0! |  |  | Total | 0
7 |  |  | #DIV/0!
8 |  |  | #DIV/0! |  | OWNER CONTINGENCY SUMMARY (Part of Original Contract)
9 |  |  | #DIV/0!
10 |  |  | #DIV/0! |  | Issue # | Date Approved | Total Value
11 |  |  | #DIV/0!
12 |  |  | #DIV/0!
13 |  |  | #DIV/0!
14 |  |  | #DIV/0!
15 |  |  | #DIV/0!
16 |  |  | #DIV/0!
17 |  |  | #DIV/0!
18 |  |  | #DIV/0!
19 |  |  | #DIV/0!
20 |  |  | #DIV/0!
Total | 0 | 0 | #DIV/0!
[6 empty] | Total to Date | 0
[6 empty] | Total Available | 0
Project Manager |  |  | Date |  |  | Remaining | 0
City Engineer / Interim Public Works Director |  |  | Date |  |  | CURRENT PAYMENT DUE
Account Number:
City Manager (Pro-Tem) (if over $5,000.00) |  |  | Date
0
This certificate is not negotiable. It is payable only to the payee named herein and its issuance, payment and acceptance are without prejudice to any rights of the Owner or Contractor under their Contract.

## PROGRESS PAYMT #5
PROGRESS PAYMENT
Project Name: | N. Springbrook - N. Elliot Pavement Project |  |  |  |  | Page: |  | 1 of 1
Project No: | 702171 |  |  |  |  | Date of Application:
Resolution # | 2016-3318 |  |  |  |  | Invoice Date:
Purchase Order No's: |  | 17-057 |  |  |  | Pay Period Through:
Amendment # | 0
The Original Kodiak Pacific Construction Contract was approved by City Council per Resolution No.2016-3318. | [5 empty] | Contractor: | Kodiak Pacific Construction
[6 empty] | Payment No : | 5
Purchase Order is attached
Application is made for Payment, as shown below, in connection with the Contract. Attached is the contractor's signed request for payment. Payment due date per Contract specification. The present status of the account(s) for this Contract is as follows:
THIS PAYMENT
Original Contract | Change Orders | Revised Contract | Total Completed & Stored To Date | Total Retainage |  | Total Earned Less Retainage | Less Previous Certificates for Payment | Balance To Finish
0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
PROGRESS INVOICE HISTORY |  |  |  |  | CHANGE ORDER SUMMARY
Pay No. / Date | Invoice Amount | Retention | % Complete |  | Change Order # | Date Approved | Total Value
1 | 0 | 7201.6045 | #DIV/0!
2 | 0 | 3042.39 | #DIV/0!
3 | 0 | 0 | #DIV/0!
4 | 0 | -10243.9945 | #DIV/0!
5 | 0 | 0 | #DIV/0!
6 |  |  | #DIV/0! |  |  | Total | 0
7 |  |  | #DIV/0!
8 |  |  | #DIV/0! |  | OWNER CONTINGENCY SUMMARY (Part of Original Contract)
9 |  |  | #DIV/0!
10 |  |  | #DIV/0! |  | Issue # | Date Approved | Total Value
11 |  |  | #DIV/0!
12 |  |  | #DIV/0!
13 |  |  | #DIV/0!
14 |  |  | #DIV/0!
15 |  |  | #DIV/0!
16 |  |  | #DIV/0!
17 |  |  | #DIV/0!
18 |  |  | #DIV/0!
19 |  |  | #DIV/0!
20 |  |  | #DIV/0!
Total | 0 | 0 | #DIV/0!
[6 empty] | Total to Date | 0
[6 empty] | Total Available | 0
Project Manager |  |  | Date |  |  | Remaining | 0
City Engineer / Interim Public Works Director |  |  | Date |  |  | CURRENT PAYMENT DUE
Account Number:
City Manager (Pro-Tem) (if over $5,000.00) |  |  | Date
0
This certificate is not negotiable. It is payable only to the payee named herein and its issuance, payment and acceptance are without prejudice to any rights of the Owner or Contractor under their Contract.

## PROGRESS PAYMT #6
PROGRESS PAYMENT
Project Name: | N. Springbrook - N. Elliot Pavement Project |  |  |  |  | Page: |  | 1 of 1
Project No: | 702171 |  |  |  |  | Date of Application:
Resolution # | 2016-3318 |  |  |  |  | Invoice Date:
Purchase Order No's: |  | 17-057 |  |  |  | Pay Period Through:
Amendment # | 0
The Original Kodiak Pacific Construction Contract was approved by City Council per Resolution No.2016-3318. | [5 empty] | Contractor: | Kodiak Pacific Construction
[6 empty] | Payment No : | 6
Purchase Order is attached
Application is made for Payment, as shown below, in connection with the Contract. Attached is the contractor's signed request for payment. Payment due date per Contract specification. The present status of the account(s) for this Contract is as follows:
THIS PAYMENT
Original Contract | Change Orders | Revised Contract | Total Completed & Stored To Date | Total Retainage |  | Total Earned Less Retainage | Less Previous Certificates for Payment | Balance To Finish
0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
PROGRESS INVOICE HISTORY |  |  |  |  | CHANGE ORDER SUMMARY
Pay No. / Date | Invoice Amount | Retention | % Complete |  | Change Order # | Date Approved | Total Value
1 | 0 | 7201.6045 | #DIV/0!
2 | 0 | 3042.39 | #DIV/0!
3 | 0 | 0 | #DIV/0!
4 | 0 | -10243.9945 | #DIV/0!
5 | 0 | 0 | #DIV/0!
6 | 0 | 0 | #DIV/0! |  |  | Total | 0
7 |  |  | #DIV/0!
8 |  |  | #DIV/0! |  | OWNER CONTINGENCY SUMMARY (Part of Original Contract)
9 |  |  | #DIV/0!
10 |  |  | #DIV/0! |  | Issue # | Date Approved | Total Value
11 |  |  | #DIV/0!
12 |  |  | #DIV/0!
13 |  |  | #DIV/0!
14 |  |  | #DIV/0!
15 |  |  | #DIV/0!
16 |  |  | #DIV/0!
17 |  |  | #DIV/0!
18 |  |  | #DIV/0!
19 |  |  | #DIV/0!
20 |  |  | #DIV/0!
Total | 0 | 0 | #DIV/0!
[6 empty] | Total to Date | 0
[6 empty] | Total Available | 0
Project Manager |  |  | Date |  |  | Remaining | 0
City Engineer / Interim Public Works Director |  |  | Date |  |  | CURRENT PAYMENT DUE
Account Number:
City Manager (if over $5,000.00) |  |  | Date
0
This certificate is not negotiable. It is payable only to the payee named herein and its issuance, payment and acceptance are without prejudice to any rights of the Owner or Contractor under their Contract.

## PROGRESS PAYMT #7
PROGRESS PAYMENT
Project Name: | N. Springbrook - N. Elliot Pavement Project |  |  |  |  | Page: |  | 1 of 1
Project No: | 702171 |  |  |  |  | Date of Application:
Resolution # | 2016-3318 |  |  |  |  | Invoice Date:
Purchase Order No's: |  | 17-057 |  |  |  | Pay Period Through:
Amendment # | 0
The Original Kodiak Pacific Construction Contract was approved by City Council per Resolution No.2016-3318. | [5 empty] | Contractor: | Kodiak Pacific Construction
[6 empty] | Payment No : | 7
Purchase Order is attached
Application is made for Payment, as shown below, in connection with the Contract. Attached is the contractor's signed request for payment. Payment due date per Contract specification. The present status of the account(s) for this Contract is as follows:
THIS PAYMENT
Original Contract | Change Orders | Revised Contract | Total Completed & Stored To Date | Total Retainage |  | Total Earned Less Retainage | Less Previous Certificates for Payment | Balance To Finish
0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
PROGRESS INVOICE HISTORY |  |  |  |  | CHANGE ORDER SUMMARY
Pay No. / Date | Invoice Amount | Retention | % Complete |  | Change Order # | Date Approved | Total Value
1 | 0 | 7201.6045 | #DIV/0!
2 | 0 | 3042.39 | #DIV/0!
3 | 0 | 0 | #DIV/0!
4 | 0 | -10243.9945 | #DIV/0!
5 | 0 | 0 | #DIV/0!
6 | 0 | 0 | #DIV/0! |  |  | Total | 0
7 | 0 | 0 | #DIV/0!
8 |  |  | #DIV/0! |  | OWNER CONTINGENCY SUMMARY (Part of Original Contract)
9 |  |  | #DIV/0!
10 |  |  | #DIV/0! |  | Issue # | Date Approved | Total Value
11 |  |  | #DIV/0!
12 |  |  | #DIV/0!
13 |  |  | #DIV/0!
14 |  |  | #DIV/0!
15 |  |  | #DIV/0!
16 |  |  | #DIV/0!
17 |  |  | #DIV/0!
18 |  |  | #DIV/0!
19 |  |  | #DIV/0!
20 |  |  | #DIV/0!
Total | 0 | 0 | #DIV/0!
[6 empty] | Total to Date | 0
[6 empty] | Total Available | 0
Project Manager |  |  | Date |  |  | Remaining | 0
Public Works Director |  |  | Date |  |  | CURRENT PAYMENT DUE
Account Number:
City Manager (if over $5,000.00) |  |  | Date
0
This certificate is not negotiable. It is payable only to the payee named herein and its issuance, payment and acceptance are without prejudice to any rights of the Owner or Contractor under their Contract.

## PROGRESS PAYMT #8
PROGRESS PAYMENT
Project Name: | N. Springbrook - N. Elliot Pavement Project |  |  |  |  | Page: |  | 1 of 1
Project No: | 702171 |  |  |  |  | Date of Application:
Resolution # | 2016-3318 |  |  |  |  | Invoice Date:
Purchase Order No's: |  | 17-057 |  |  |  | Pay Period Through:
Amendment # | 0
The Original Kodiak Pacific Construction Contract was approved by City Council per Resolution No.2016-3318. | [5 empty] | Contractor: | Kodiak Pacific Construction
[6 empty] | Payment No : | 8
Purchase Order is attached
Application is made for Payment, as shown below, in connection with the Contract. Attached is the contractor's signed request for payment. Payment due date per Contract specification. The present status of the account(s) for this Contract is as follows:
THIS PAYMENT
Original Contract | Change Orders | Revised Contract | Total Completed & Stored To Date | Total Retainage |  | Total Earned Less Retainage | Less Previous Certificates for Payment | Balance To Finish
0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
PROGRESS INVOICE HISTORY |  |  |  |  | CHANGE ORDER SUMMARY
Pay No. / Date | Invoice Amount | Retention | % Complete |  | Change Order # | Date Approved | Total Value
1 | 0 | 7201.6045 | #DIV/0!
2 | 0 | 3042.39 | #DIV/0!
3 | 0 | 0 | #DIV/0!
4 | 0 | -10243.9945 | #DIV/0!
5 | 0 | 0 | #DIV/0!
6 | 0 | 0 | #DIV/0! |  |  | Total | 0
7 | 0 | 0 | #DIV/0!
8 | 0 | 0 | #DIV/0! |  | OWNER CONTINGENCY SUMMARY (Part of Original Contract)
9 |  |  | #DIV/0!
10 |  |  | #DIV/0! |  | Issue # | Date Approved | Total Value
11 |  |  | #DIV/0!
12 |  |  | #DIV/0!
13 |  |  | #DIV/0!
14 |  |  | #DIV/0!
15 |  |  | #DIV/0!
16 |  |  | #DIV/0!
17 |  |  | #DIV/0!
18 |  |  | #DIV/0!
19 |  |  | #DIV/0!
20 |  |  | #DIV/0!
Total | 0 | 0 | #DIV/0!
[6 empty] | Total to Date | 0
[6 empty] | Total Available | 0
Project Manager |  |  | Date |  |  | Remaining | 0
Public Works Director |  |  | Date |  |  | CURRENT PAYMENT DUE
Account Number:
City Manager (if over $5,000.00) |  |  | Date
0
This certificate is not negotiable. It is payable only to the payee named herein and its issuance, payment and acceptance are without prejudice to any rights of the Owner or Contractor under their Contract.

## PROGRESS PAYMT #9
PROGRESS PAYMENT
Project Name: | N. Springbrook - N. Elliot Pavement Project |  |  |  |  | Page: |  | 1 of 1
Project No: | 702171 |  |  |  |  | Date of Application:
Resolution # | 2016-3318 |  |  |  |  | Invoice Date:
Purchase Order No's: |  | 17-057 |  |  |  | Pay Period Through:
Amendment # | 0
The Original Kodiak Pacific Construction Contract was approved by City Council per Resolution No.2016-3318. | [5 empty] | Contractor: | Kodiak Pacific Construction
[6 empty] | Payment No : | 9
Purchase Order is attached
Application is made for Payment, as shown below, in connection with the Contract. Attached is the contractor's signed request for payment. Payment due date per Contract specification. The present status of the account(s) for this Contract is as follows:
THIS PAYMENT
Original Contract | Change Orders | Revised Contract | Total Completed & Stored To Date | Total Retainage |  | Total Earned Less Retainage | Less Previous Certificates for Payment | Balance To Finish
0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
PROGRESS INVOICE HISTORY |  |  |  |  | CHANGE ORDER SUMMARY
Pay No. / Date | Invoice Amount | Retention | % Complete |  | Change Order # | Date Approved | Total Value
1 | 0 | 7201.6045 | #DIV/0!
2 | 0 | 3042.39 | #DIV/0!
3 | 0 | 0 | #DIV/0!
4 | 0 | -10243.9945 | #DIV/0!
5 | 0 | 0 | #DIV/0!
6 | 0 | 0 | #DIV/0! |  |  | Total | 0
7 | 0 | 0 | #DIV/0!
8 | 0 | 0 | #DIV/0! |  | OWNER CONTINGENCY SUMMARY (Part of Original Contract)
9 | 0 | 0 | #DIV/0!
10 |  |  | #DIV/0! |  | Issue # | Date Approved | Total Value
11 |  |  | #DIV/0!
12 |  |  | #DIV/0!
13 |  |  | #DIV/0!
14 |  |  | #DIV/0!
15 |  |  | #DIV/0!
16 |  |  | #DIV/0!
17 |  |  | #DIV/0!
18 |  |  | #DIV/0!
19 |  |  | #DIV/0!
20 |  |  | #DIV/0!
Total | 0 | 0 | #DIV/0!
[6 empty] | Total to Date | 0
[6 empty] | Total Available | 0
Project Manager |  |  | Date |  |  | Remaining | 0
Public Works Director |  |  | Date |  |  | CURRENT PAYMENT DUE
Account Number:
City Manager (if over $5,000.00) |  |  | Date
0
This certificate is not negotiable. It is payable only to the payee named herein and its issuance, payment and acceptance are without prejudice to any rights of the Owner or Contractor under their Contract.

## PROGRESS PAYMT #10
PROGRESS PAYMENT
Project Name: | N. Springbrook - N. Elliot Pavement Project |  |  |  |  | Page: |  | 1 of 1
Project No: | 702171 |  |  |  |  | Date of Application:
Resolution # | 2016-3318 |  |  |  |  | Invoice Date:
Purchase Order No's: |  | 17-057 |  |  |  | Pay Period Through:
Amendment # | 0
The Original Kodiak Pacific Construction Contract was approved by City Council per Resolution No.2016-3318. | [5 empty] | Contractor: | Kodiak Pacific Construction
[6 empty] | Payment No : | 10
Purchase Order is attached
Application is made for Payment, as shown below, in connection with the Contract. Attached is the contractor's signed request for payment. Payment due date per Contract specification. The present status of the account(s) for this Contract is as follows:
THIS PAYMENT
Original Contract | Change Orders | Revised Contract | Total Completed & Stored To Date | Total Retainage |  | Total Earned Less Retainage | Less Previous Certificates for Payment | Balance To Finish
0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
PROGRESS INVOICE HISTORY |  |  |  |  | CHANGE ORDER SUMMARY
Pay No. / Date | Invoice Amount | Retention | % Complete |  | Change Order # | Date Approved | Total Value
1 | 0 | 7201.6045 | #DIV/0!
2 | 0 | 3042.39 | #DIV/0!
3 | 0 | 0 | #DIV/0!
4 | 0 | -10243.9945 | #DIV/0!
5 | 0 | 0 | #DIV/0!
6 | 0 | 0 | #DIV/0! |  |  | Total | 0
7 | 0 | 0 | #DIV/0!
8 | 0 | 0 | #DIV/0! |  | OWNER CONTINGENCY SUMMARY (Part of Original Contract)
9 | 0 | 0 | #DIV/0!
10 | 0 | 0 | #DIV/0! |  | Issue # | Date Approved | Total Value
11 |  |  | #DIV/0!
12 |  |  | #DIV/0!
13 |  |  | #DIV/0!
14 |  |  | #DIV/0!
15 |  |  | #DIV/0!
16 |  |  | #DIV/0!
17 |  |  | #DIV/0!
18 |  |  | #DIV/0!
19 |  |  | #DIV/0!
20 |  |  | #DIV/0!
Total | 0 | 0 | #DIV/0!
[6 empty] | Total to Date | 0
[6 empty] | Total Available | 0
Project Manager |  |  | Date |  |  | Remaining | 0
City Engineer |  |  | Date |  |  | CURRENT PAYMENT DUE
Account Number:
City Manager (if over $5,000.00) |  |  | Date
0
This certificate is not negotiable. It is payable only to the payee named herein and its issuance, payment and acceptance are without prejudice to any rights of the Owner or Contractor under their Contract.

## PROGRESS PAYMT #11
PROGRESS PAYMENT
Project Name: | N. Springbrook - N. Elliot Pavement Project |  |  |  |  | Page: |  | 1 of 1
Project No: | 702171 |  |  |  |  | Date of Application:
Resolution # | 2016-3318 |  |  |  |  | Invoice Date:
Purchase Order No's: |  | 17-057 |  |  |  | Pay Period Through:
Amendment # | 0
The Original Kodiak Pacific Construction Contract was approved by City Council per Resolution No.2016-3318. | [5 empty] | Contractor: | Kodiak Pacific Construction
[6 empty] | Payment No : | 11
Purchase Order is attached
Application is made for Payment, as shown below, in connection with the Contract. Attached is the contractor's signed request for payment. Payment due date per Contract specification. The present status of the account(s) for this Contract is as follows:
THIS PAYMENT
Original Contract | Change Orders | Revised Contract | Total Completed & Stored To Date | Total Retainage |  | Total Earned Less Retainage | Less Previous Certificates for Payment | Balance To Finish
0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
PROGRESS INVOICE HISTORY |  |  |  |  | CHANGE ORDER SUMMARY
Pay No. / Date | Invoice Amount | Retention | % Complete |  | Change Order # | Date Approved | Total Value
1 | 0 | 7201.6045 | #DIV/0!
2 | 0 | 3042.39 | #DIV/0!
3 | 0 | 0 | #DIV/0!
4 | 0 | -10243.9945 | #DIV/0!
5 | 0 | 0 | #DIV/0!
6 | 0 | 0 | #DIV/0!
7 | 0 | 0 | #DIV/0!
8 | 0 | 0 | #DIV/0!
9 | 0 | 0 | #DIV/0!
10 | 0 | 0 | #DIV/0! |  |  | Total | 0
11 | 0 | 0 | #DIV/0!
12 |  |  | #DIV/0! |  | OWNER CONTINGENCY SUMMARY (Part of Original Contract)
13 |  |  | #DIV/0!
14 |  |  | #DIV/0! |  | Issue # | Date Approved | Total Value
15 |  |  | #DIV/0!
16 |  |  | #DIV/0!
17 |  |  | #DIV/0!
18 |  |  | #DIV/0!
19 |  |  | #DIV/0!
20 |  |  | #DIV/0!
Total | 0 | 0 | #DIV/0!
[6 empty] | Total to Date | 0
[6 empty] | Total Available | 0
Project Manager |  |  | Date |  |  | Remaining | 0
City Engineer |  |  | Date |  |  | CURRENT PAYMENT DUE
Account Number:
City Manager (if over $5,000.00) |  |  | Date
0
This certificate is not negotiable. It is payable only to the payee named herein and its issuance, payment and acceptance are without prejudice to any rights of the Owner or Contractor under their Contract.

## PROGRESS PAYMT #12
PROGRESS PAYMENT
Project Name: | N. Springbrook - N. Elliot Pavement Project |  |  |  |  | Page: |  | 1 of 1
Project No: | 702171 |  |  |  |  | Date of Application:
Resolution # | 2016-3318 |  |  |  |  | Invoice Date:
Purchase Order No's: |  | 17-057 |  |  |  | Pay Period Through:
Amendment # | 0
The Original Kodiak Pacific Construction Contract was approved by City Council per Resolution No.2016-3318. | [5 empty] | Contractor: | Kodiak Pacific Construction
[6 empty] | Payment No : | 12
Purchase Order is attached
Application is made for Payment, as shown below, in connection with the Contract. Attached is the contractor's signed request for payment. Payment due date per Contract specification. The present status of the account(s) for this Contract is as follows:
THIS PAYMENT
Original Contract | Change Orders | Revised Contract | Total Completed & Stored To Date | Total Retainage |  | Total Earned Less Retainage | Less Previous Certificates for Payment | Balance To Finish
0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
PROGRESS INVOICE HISTORY |  |  |  |  | CHANGE ORDER SUMMARY
Pay No. / Date | Invoice Amount | Retention | % Complete |  | Change Order # | Date Approved | Total Value
1 | 0 | 7201.6045 | #DIV/0!
2 | 0 | 3042.39 | #DIV/0!
3 | 0 | 0 | #DIV/0!
4 | 0 | -10243.9945 | #DIV/0!
5 | 0 | 0 | #DIV/0!
6 | 0 | 0 | #DIV/0! |  |  | Total | 0
7 | 0 | 0 | #DIV/0!
8 | 0 | 0 | #DIV/0! |  | OWNER CONTINGENCY SUMMARY (Part of Original Contract)
9 | 0 | 0 | #DIV/0!
10 | 0 | 0 | #DIV/0! |  | Issue # | Date Approved | Total Value
11 | 0 | 0 | #DIV/0!
12 | 0 | 0 | #DIV/0!
13 |  |  | #DIV/0!
14 |  |  | #DIV/0!
15 |  |  | #DIV/0!
16 |  |  | #DIV/0!
17 |  |  | #DIV/0!
18 |  |  | #DIV/0!
19 |  |  | #DIV/0!
20 |  |  | #DIV/0!
Total | 0 | 0 | #DIV/0!
[6 empty] | Total to Date | 0
[6 empty] | Total Available | 0
Project Manager |  |  | Date |  |  | Remaining | 0
City Engineer |  |  | Date |  |  | CURRENT PAYMENT DUE
Account Number:
City Manager (if over $5,000.00) |  |  | Date
0
This certificate is not negotiable. It is payable only to the payee named herein and its issuance, payment and acceptance are without prejudice to any rights of the Owner or Contractor under their Contract.

## PROGRESS PAYMT #13-14
PROGRESS PAYMENT
Project Name: | N. Springbrook - N. Elliot Pavement Project |  |  |  |  | Page: |  | 1 of 1
Project No: | 702171 |  |  |  |  | Date of Application:
Resolution # | 2016-3318 |  |  |  |  | Invoice Date:
Purchase Order No's: |  | 17-057 |  |  |  | Pay Period Through:
Amendment # | 0
The Original Kodiak Pacific Construction Contract was approved by City Council per Resolution No.2016-3318. | [5 empty] | Contractor: | Kodiak Pacific Construction
[6 empty] | Payment No : | 13 + 14
Purchase Order is attached
Application is made for Payment, as shown below, in connection with the Contract. Attached is the contractor's signed request for payment. Payment due date per Contract specification. The present status of the account(s) for this Contract is as follows:
THIS PAYMENT
Original Contract | Change Orders | Revised Contract | Total Completed & Stored To Date | Total Retainage |  | Total Earned Less Retainage | Less Previous Certificates for Payment | Balance To Finish
0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
PROGRESS INVOICE HISTORY |  |  |  |  | CHANGE ORDER SUMMARY
Pay No. / Date | Invoice Amount | Retention | % Complete |  | Change Order # | Date Approved | Total Value
1 | 0 | 7201.6045 | #DIV/0!
2 | 0 | 3042.39 | #DIV/0!
3 | 0 | 0 | #DIV/0!
4 | 0 | -10243.9945 | #DIV/0!
5 | 0 | 0 | #DIV/0!
6 | 0 | 0 | #DIV/0! |  |  | Total | 0
7 | 0 | 0 | #DIV/0!
8 | 0 | 0 | #DIV/0! |  | OWNER CONTINGENCY SUMMARY (Part of Original Contract)
9 | 0 | 0 | #DIV/0!
10 | 0 | 0 | #DIV/0! |  | Issue # | Date Approved | Total Value
11 | 0 | 0 | #DIV/0!
12 | 0 | 0 | #DIV/0!
13 | 0 | #DIV/0! | #DIV/0!
14 | 0 | #DIV/0! | #DIV/0!
15 |  |  | #DIV/0!
16 |  |  | #DIV/0!
17 |  |  | #DIV/0!
18 |  |  | #DIV/0!
19 |  |  | #DIV/0!
20 |  |  | #DIV/0!
Total | -0.01 | #DIV/0! | #DIV/0!
[6 empty] | Total to Date | 0
[6 empty] | Total Available | 0
Project Manager |  |  | Date |  |  | Remaining | 0
City Engineer |  |  | Date |  |  | CURRENT PAYMENT DUE
Account Number:
City Manager (if over $5,000.00) |  |  | Date
0
This certificate is not negotiable. It is payable only to the payee named herein and its issuance, payment and acceptance are without prejudice to any rights of the Owner or Contractor under their Contract.

## RETEN1
PROGRESS PAYMENT
Project Name: | N. Springbrook - N. Elliot Pavement Project |  |  |  |  | Page: |  | 1 of 1
Project No: | 702171 |  |  |  |  | Date of Application:
Resolution # | 2016-3318 |  |  |  |  | Invoice Date:
Purchase Order No's: |  | 17-057 |  |  |  | Pay Period Through:
Amendment # | 0
The Original Kodiak Pacific Construction Contract was approved by City Council per Resolution No.2016-3318. | [5 empty] | Contractor: | Kodiak Pacific Construction
[6 empty] | Payment No : | RETEN1
Purchase Order is attached
Application is made for Payment, as shown below, in connection with the Contract. Attached is the contractor's signed request for payment. Payment due date per Contract specification. The present status of the account(s) for this Contract is as follows:
THIS PAYMENT
Original Contract | Change Orders | Revised Contract | Total Completed & Stored To Date | Total Retainage |  | Total Earned Less Retainage | Less Previous Certificates for Payment | Balance To Finish
0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
PROGRESS INVOICE HISTORY |  |  |  |  | CHANGE ORDER SUMMARY
Pay No. / Date | Invoice Amount | Retention | % Complete |  | Change Order # | Date Approved | Total Value
1 | 0 | 7201.6045 | #DIV/0!
2 | 0 | 3042.39 | #DIV/0!
3 | 0 | 0 | #DIV/0!
4 | 0 | -10243.9945 | #DIV/0!
5 | 0 | 0 | #DIV/0!
6 | 0 | 0 | #DIV/0! |  |  | Total | 0
7 | 0 | 0 | #DIV/0!
8 | 0 | 0 | #DIV/0! |  | OWNER CONTINGENCY SUMMARY (Part of Original Contract)
9 | 0 | 0 | #DIV/0!
10 | 0 | 0 | #DIV/0! |  | Issue # | Date Approved | Total Value
11 | 0 | 0 | #DIV/0!
12 | 0 | 0 | #DIV/0!
13 | 0 | #DIV/0! | #DIV/0!
14 | 0 | #DIV/0! | #DIV/0!
RETEN1 | 0 | 0 | #DIV/0!
15 |  |  | #DIV/0!
16 |  |  | #DIV/0!
17 |  |  | #DIV/0!
18 |  |  | #DIV/0!
19 |  |  | #DIV/0!
Total | -0.01 | #DIV/0! | #DIV/0!
[6 empty] | Total to Date | 0
[6 empty] | Total Available | 0
Project Manager |  |  | Date |  |  | Remaining | 0
City Engineer |  |  | Date |  |  | CURRENT PAYMENT DUE
Account Number:
City Manager (if over $5,000.00) |  |  | Date
0
This certificate is not negotiable. It is payable only to the payee named herein and its issuance, payment and acceptance are without prejudice to any rights of the Owner or Contractor under their Contract.

## PROGRESS PAYMT #15
PROGRESS PAYMENT
Project Name: | N. Springbrook - N. Elliot Pavement Project |  |  |  |  | Page: |  | 1 of 1
Project No: | 702171 |  |  |  |  | Date of Application:
Resolution # | 2016-3318 |  |  |  |  | Invoice Date:
Purchase Order No's: |  | 17-057 |  |  |  | Pay Period Through:
Amendment # | 0
The Original Kodiak Pacific Construction Contract was approved by City Council per Resolution No.2016-3318. | [5 empty] | Contractor: | Kodiak Pacific Construction
[6 empty] | Payment No : | 15
Purchase Order is attached
Application is made for Payment, as shown below, in connection with the Contract. Attached is the contractor's signed request for payment. Payment due date per Contract specification. The present status of the account(s) for this Contract is as follows:
THIS PAYMENT
Original Contract | Change Orders | Revised Contract | Total Completed & Stored To Date | Total Retainage |  | Total Earned Less Retainage | Less Previous Certificates for Payment | Balance To Finish
0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
PROGRESS INVOICE HISTORY |  |  |  |  | CHANGE ORDER SUMMARY
Pay No. / Date | Invoice Amount | Retention | % Complete |  | Change Order # | Date Approved | Total Value
1 | 0 | 7201.6045 | #DIV/0!
2 | 0 | 3042.39 | #DIV/0!
3 | 0 | 0 | #DIV/0!
4 | 0 | -10243.9945 | #DIV/0!
5 | 0 | 0 | #DIV/0!
6 | 0 | 0 | #DIV/0! |  |  | Total | 0
7 | 0 | 0 | #DIV/0!
8 | 0 | 0 | #DIV/0! |  | OWNER CONTINGENCY SUMMARY (Part of Original Contract)
9 | 0 | 0 | #DIV/0!
10 | 0 | 0 | #DIV/0! |  | Issue # | Date Approved | Total Value
11 | 0 | 0 | #DIV/0!
12 | 0 | 0 | #DIV/0!
13 | 0 | #DIV/0! | #DIV/0!
14 | 0 | #DIV/0! | #DIV/0!
RETEN | 0 | 0 | #DIV/0!
15 | 0 | #DIV/0! | #DIV/0!
17 |  |  | #DIV/0!
18 |  |  | #DIV/0!
19 |  |  | #DIV/0!
20 |  |  | #DIV/0!
Total | -0.01 | #DIV/0! | #DIV/0!
[6 empty] | Total to Date | 0
[6 empty] | Total Available | 0
Project Manager |  |  | Date |  |  | Remaining | 0
City Engineer |  |  | Date |  |  | CURRENT PAYMENT DUE
Account Number:
City Manager (if over $5,000.00) |  |  | Date
0
This certificate is not negotiable. It is payable only to the payee named herein and its issuance, payment and acceptance are without prejudice to any rights of the Owner or Contractor under their Contract.

## PROGRESS PAYMT #16
PROGRESS PAYMENT
Project Name: | N. Springbrook - N. Elliot Pavement Project |  |  |  |  | Page: |  | 1 of 1
Project No: | 702171 |  |  |  |  | Date of Application:
Resolution # | 2016-3318 |  |  |  |  | Invoice Date:
Purchase Order No's: |  | 17-057 |  |  |  | Pay Period Through:
Amendment # | 0
The Original Kodiak Pacific Construction Contract was approved by City Council per Resolution No.2016-3318. | [5 empty] | Contractor: | Kodiak Pacific Construction
[6 empty] | Payment No : | 16
Purchase Order is attached
Application is made for Payment, as shown below, in connection with the Contract. Attached is the contractor's signed request for payment. Payment due date per Contract specification. The present status of the account(s) for this Contract is as follows:
THIS PAYMENT
Original Contract | Change Orders | Revised Contract | Total Completed & Stored To Date | Total Retainage |  | Total Earned Less Retainage | Less Previous Certificates for Payment | Balance To Finish
0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
PROGRESS INVOICE HISTORY |  |  |  |  | CHANGE ORDER SUMMARY
Pay No. / Date | Invoice Amount | Retention | % Complete |  | Change Order # | Date Approved | Total Value
1 | 0 | 7201.6045 | #DIV/0!
2 | 0 | 3042.39 | #DIV/0!
3 | 0 | 0 | #DIV/0!
4 | 0 | -10243.9945 | #DIV/0!
5 | 0 | 0 | #DIV/0!
6 | 0 | 0 | #DIV/0! |  |  | Total | 0
7 | 0 | 0 | #DIV/0!
8 | 0 | 0 | #DIV/0! |  | OWNER CONTINGENCY SUMMARY (Part of Original Contract)
9 | 0 | 0 | #DIV/0!
10 | 0 | 0 | #DIV/0! |  | Issue # | Date Approved | Total Value
11 | 0 | 0 | #DIV/0!
12 | 0 | 0 | #DIV/0!
13 | 0 | #DIV/0! | #DIV/0!
14 | 0 | #DIV/0! | #DIV/0!
RETEN | 0 | 0 | #DIV/0!
15 | 0 | #DIV/0! | #DIV/0!
16 | 0 | #DIV/0! | #DIV/0!
17 |  |  | #DIV/0!
18 |  |  | #DIV/0!
19 |  |  | #DIV/0!
Total | -0.01 | #DIV/0! | #DIV/0!
[6 empty] | Total to Date | 0
[6 empty] | Total Available | 0
Project Manager |  |  | Date |  |  | Remaining | 0
City Engineer |  |  | Date |  |  | CURRENT PAYMENT DUE
Account Number:
City Manager (if over $5,000.00) |  |  | Date
0
This certificate is not negotiable. It is payable only to the payee named herein and its issuance, payment and acceptance are without prejudice to any rights of the Owner or Contractor under their Contract.

## PROGRESS PAYMT #17
PROGRESS PAYMENT
Project Name: | N. Springbrook - N. Elliot Pavement Project |  |  |  |  | Page: |  | 1 of 1
Project No: | 702171 |  |  |  |  | Date of Application:
Resolution # | 2016-3318 |  |  |  |  | Invoice Date:
Purchase Order No's: |  | 17-057 |  |  |  | Pay Period Through:
Amendment # | 0
The Original Kodiak Pacific Construction Contract was approved by City Council per Resolution No.2016-3318. | [5 empty] | Contractor: | Kodiak Pacific Construction
[6 empty] | Payment No : | 17
Purchase Order is attached
Application is made for Payment, as shown below, in connection with the Contract. Attached is the contractor's signed request for payment. Payment due date per Contract specification. The present status of the account(s) for this Contract is as follows:
THIS PAYMENT
Original Contract | Change Orders | Revised Contract | Total Completed & Stored To Date | Total Retainage |  | Total Earned Less Retainage | Less Previous Certificates for Payment | Balance To Finish
0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
PROGRESS INVOICE HISTORY |  |  |  |  | CHANGE ORDER SUMMARY
Pay No. / Date | Invoice Amount | Retention | % Complete |  | Change Order # | Date Approved | Total Value
1 | 0 | 7201.6045 | #DIV/0!
2 | 0 | 3042.39 | #DIV/0!
3 | 0 | 0 | #DIV/0!
4 | 0 | -10243.9945 | #DIV/0!
5 | 0 | 0 | #DIV/0!
6 | 0 | 0 | #DIV/0! |  |  | Total | 0
7 | 0 | 0 | #DIV/0!
8 | 0 | 0 | #DIV/0! |  | OWNER CONTINGENCY SUMMARY (Part of Original Contract)
9 | 0 | 0 | #DIV/0!
10 | 0 | 0 | #DIV/0! |  | Issue # | Date Approved | Total Value
11 | 0 | 0 | #DIV/0!
12 | 0 | 0 | #DIV/0!
13 | 0 | #DIV/0! | #DIV/0!
14 | 0 | #DIV/0! | #DIV/0!
RETEN | 0 | 0 | #DIV/0!
15 | 0 | #DIV/0! | #DIV/0!
16 | 0 | #DIV/0! | #DIV/0!
17 | 0 | #DIV/0! | #DIV/0!
18 |  |  | #DIV/0!
19 |  |  | #DIV/0!
Total | -0.01 | #DIV/0! | #DIV/0!
[6 empty] | Total to Date | 0
[6 empty] | Total Available | 0
Project Manager |  |  | Date |  |  | Remaining | 0
City Engineer |  |  | Date |  |  | CURRENT PAYMENT DUE
Account Number: 36-5150-706401
City Manager (if over $5,000.00) |  |  | Date
0
This certificate is not negotiable. It is payable only to the payee named herein and its issuance, payment and acceptance are without prejudice to any rights of the Owner or Contractor under their Contract.

## RETEN2
PROGRESS PAYMENT
Project Name: | N. Springbrook - N. Elliot Pavement Project |  |  |  |  | Page: |  | 1 of 1
Project No: | 702171 |  |  |  |  | Date of Application:
Resolution # | 2016-3318 |  |  |  |  | Invoice Date:
Purchase Order No's: |  | 17-057 |  |  |  | Pay Period Through:
Amendment # | 0
The Original Kodiak Pacific Construction Contract was approved by City Council per Resolution No.2016-3318. | [5 empty] | Contractor: | Kodiak Pacific Construction
[6 empty] | Payment No : | RETEN2
Purchase Order is attached
Application is made for Payment, as shown below, in connection with the Contract. Attached is the contractor's signed request for payment. Payment due date per Contract specification. The present status of the account(s) for this Contract is as follows:
THIS PAYMENT
Original Contract | Change Orders | Revised Contract | Total Completed & Stored To Date | Total Retainage |  | Total Earned Less Retainage | Less Previous Certificates for Payment | Balance To Finish
0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
PROGRESS INVOICE HISTORY |  |  |  |  | CHANGE ORDER SUMMARY
Pay No. / Date | Invoice Amount | Retention | % Complete |  | Change Order # | Date Approved | Total Value
1 | 0 | 7201.6045 | #DIV/0!
2 | 0 | 3042.39 | #DIV/0!
3 | 0 | 0 | #DIV/0!
4 | 0 | -10243.9945 | #DIV/0!
5 | 0 | 0 | #DIV/0!
6 | 0 | 0 | #DIV/0! |  |  | Total | 0
7 | 0 | 0 | #DIV/0!
8 | 0 | 0 | #DIV/0! |  | OWNER CONTINGENCY SUMMARY (Part of Original Contract)
9 | 0 | 0 | #DIV/0!
10 | 0 | 0 | #DIV/0! |  | Issue # | Date Approved | Total Value
11 | 0 | 0 | #DIV/0!
12 | 0 | 0 | #DIV/0!
13 | 0 | #DIV/0! | #DIV/0!
14 | 0 | #DIV/0! | #DIV/0!
RETEN | 0 | 0 | #DIV/0!
15 | 0 | #DIV/0! | #DIV/0!
16 | 0 | #DIV/0! | #DIV/0!
17 | 0 | #DIV/0! | #DIV/0!
18 | 0 | 0 | #DIV/0!
19 |  |  | #DIV/0!
Total | 0 | #DIV/0! | #DIV/0!
[6 empty] | Total to Date | 0
[6 empty] | Total Available | 0
Project Manager |  |  | Date |  |  | Remaining | 0
City Engineer |  |  | Date |  |  | CURRENT PAYMENT DUE
Account Number:
City Manager (if over $5,000.00) |  |  | Date
0
This certificate is not negotiable. It is payable only to the payee named herein and its issuance, payment and acceptance are without prejudice to any rights of the Owner or Contractor under their Contract.

## PROGRESS PAYMT #18
PROGRESS PAYMENT
Project Name: | N. Springbrook - N. Elliot Pavement Project |  |  |  |  | Page: |  | 1 of 1
Project No: | 702171 |  |  |  |  | Date of Application:
Resolution # | 2016-3318 |  |  |  |  | Invoice Date:
Purchase Order No's: |  | 17-057 |  |  |  | Pay Period Through:
Amendment # | 0
The Original Kodiak Pacific Construction Contract was approved by City Council per Resolution No.2016-3318. | [5 empty] | Contractor: | Kodiak Pacific Construction
[6 empty] | Payment No : | 18
Purchase Order is attached
Application is made for Payment, as shown below, in connection with the Contract. Attached is the contractor's signed request for payment. Payment due date per Contract specification. The present status of the account(s) for this Contract is as follows:
THIS PAYMENT
Original Contract | Change Orders | Revised Contract | Total Completed & Stored To Date | Total Retainage |  | Total Earned Less Retainage | Less Previous Certificates for Payment | Balance To Finish
0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
PROGRESS INVOICE HISTORY |  |  |  |  | CHANGE ORDER SUMMARY
Pay No. / Date | Invoice Amount | Retention | % Complete |  | Change Order # | Date Approved | Total Value
1 | 0 | 7201.6045 | #DIV/0!
2 | 0 | 3042.39 | #DIV/0!
3 | 0 | 0 | #DIV/0!
4 | 0 | -10243.9945 | #DIV/0!
5 | 0 | 0 | #DIV/0!
6 | 0 | 0 | #DIV/0! |  |  | Total | 0
7 | 0 | 0 | #DIV/0!
8 | 0 | 0 | #DIV/0! |  | OWNER CONTINGENCY SUMMARY (Part of Original Contract)
9 | 0 | 0 | #DIV/0!
10 | 0 | 0 | #DIV/0! |  | Issue # | Date Approved | Total Value
11 | 0 | 0 | #DIV/0!
12 | 0 | 0 | #DIV/0!
13 | 0 | #DIV/0! | #DIV/0!
14 | 0 | #DIV/0! | #DIV/0!
RETEN1 | 0 | 0 | #DIV/0!
15 | 0 | #DIV/0! | #DIV/0!
16 | 0 | #DIV/0! | #DIV/0!
17 | 0 | #DIV/0! | #DIV/0!
RETEN2 | 0 |  | #DIV/0!
18 | 0 | #DIV/0! | #DIV/0!
0
Total | 0 | #DIV/0! | #DIV/0! |  |  | Total to Date | 0
[6 empty] | Total Available | 0
[6 empty] | Remaining | 0
Project Manager |  |  | Date
City Engineer |  |  | Date |  |  | CURRENT PAYMENT DUE
Account Number:
City Manager (if over $5,000.00) |  |  | Date
0
This certificate is not negotiable. It is payable only to the payee named herein and its issuance, payment and acceptance are without prejudice to any rights of the Owner or Contractor under their Contract.

## PROGRESS PAYMT #19
PROGRESS PAYMENT
Project Name: | N. Springbrook - N. Elliot Pavement Project |  |  |  |  | Page: |  | 1 of 1
Project No: | 702171 |  |  |  |  | Date of Application:
Resolution # | 2016-3318 |  |  |  |  | Invoice Date:
Purchase Order No's: |  | 17-057 |  |  |  | Pay Period Through:
Amendment # | 0
The Original Kodiak Pacific Construction Contract was approved by City Council per Resolution No.2016-3318. | [5 empty] | Contractor: | Kodiak Pacific Construction
[6 empty] | Payment No : | 19
Purchase Order is attached
Application is made for Payment, as shown below, in connection with the Contract. Attached is the contractor's signed request for payment. Payment due date per Contract specification. The present status of the account(s) for this Contract is as follows:
THIS PAYMENT
Original Contract | Change Orders | Revised Contract | Total Completed & Stored To Date | Total Retainage |  | Total Earned Less Retainage | Less Previous Certificates for Payment | Balance To Finish
0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
PROGRESS INVOICE HISTORY |  |  |  |  | CHANGE ORDER SUMMARY
Pay No. / Date | Invoice Amount | Retention | % Complete |  | Change Order # | Date Approved | Total Value
1 | 0 | 7201.6045 | #DIV/0!
2 | 0 | 3042.39 | #DIV/0!
3 | 0 | 0 | #DIV/0!
4 | 0 | -10243.9945 | #DIV/0!
5 | 0 | 0 | #DIV/0!
6 | 0 | 0 | #DIV/0! |  |  | Total | 0
7 | 0 | 0 | #DIV/0!
8 | 0 | 0 | #DIV/0! |  | OWNER CONTINGENCY SUMMARY (Part of Original Contract)
9 | 0 | 0 | #DIV/0!
10 | 0 | 0 | #DIV/0! |  | Issue # | Date Approved | Total Value
11 | 0 | 0 | #DIV/0!
12 | 0 | 0 | #DIV/0!
13 | 0 | #DIV/0! | #DIV/0!
14 | 0 | #DIV/0! | #DIV/0!
RETEN1 | 0 | 0 | #DIV/0!
15 | 0 | #DIV/0! | #DIV/0!
16 | 0 | #DIV/0! | #DIV/0!
17 | 0 | #DIV/0! | #DIV/0!
RETEN2 | 0 | 0 | #DIV/0!
18 | 0 | 0 | #DIV/0!
19 | 0 | #DIV/0! | #DIV/0!
Total | 0 | #DIV/0! | #DIV/0! |  |  | Total to Date | 0
[6 empty] | Total Available | 0
[6 empty] | Remaining | 0
Project Manager |  |  | Date
City Engineer |  |  | Date |  |  | CURRENT PAYMENT DUE
Account Number:
City Manager (if over $5,000.00) |  |  | Date
0
This certificate is not negotiable. It is payable only to the payee named herein and its issuance, payment and acceptance are without prejudice to any rights of the Owner or Contractor under their Contract.

## PROGRESS PAYMT #20
PROGRESS PAYMENT
Project Name: | N. Springbrook - N. Elliot Pavement Project |  |  |  |  | Page: |  | 1 of 1
Project No: | 702171 |  |  |  |  | Date of Application:
Resolution # | 2016-3318 |  |  |  |  | Invoice Date:
Purchase Order No's: |  | 17-057 |  |  |  | Pay Period Through:
Amendment # | 0
The Original Kodiak Pacific Construction Contract was approved by City Council per Resolution No.2016-3318. | [5 empty] | Contractor: | Kodiak Pacific Construction
[6 empty] | Payment No : | 20
Purchase Order is attached
Application is made for Payment, as shown below, in connection with the Contract. Attached is the contractor's signed request for payment. Payment due date per Contract specification. The present status of the account(s) for this Contract is as follows:
THIS PAYMENT
Original Contract | Change Orders | Revised Contract | Total Completed & Stored To Date | Total Retainage |  | Total Earned Less Retainage | Less Previous Certificates for Payment | Balance To Finish
0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
PROGRESS INVOICE HISTORY |  |  |  |  | CHANGE ORDER SUMMARY
Pay No. / Date | Invoice Amount | Retention | % Complete |  | Change Order # | Date Approved | Total Value
1 | 0 | 0 | #DIV/0!
2 | 0 | 0 | #DIV/0!
3 | 0 | 0 | #DIV/0!
4 | 0 | 0 | #DIV/0!
5 | 0 | 0 | #DIV/0!
6 | 0 | 0 | #DIV/0! |  |  | Total | 0
7 | 0 | 0 | #DIV/0!
8 | 0 | 0 | #DIV/0! |  | OWNER CONTINGENCY SUMMARY (Part of Original Contract)
9 | 0 | 0 | #DIV/0!
10 | 0 | 0 | #DIV/0! |  | Issue # | Date Approved | Total Value
11 | 0 | 0 | #DIV/0!
12 | 0 | 0 | #DIV/0!
13 | 0 | 0 | #DIV/0!
14 | 0 | 0 | #DIV/0!
RETEN1 | 0 | 0 | #DIV/0!
15 | 0 | 0 | #DIV/0!
16 | 0 | 0 | #DIV/0!
17 | 0 | 0 | #DIV/0!
RETEN2 | 0 | 0 | #DIV/0!
18 | 0 | 0 | #DIV/0!
19 | 0 | 0 | #DIV/0!
20 | 0 | 0 | #DIV/0! |  |  | Total to Date | 0
Total | 0 | 0 | #DIV/0! |  |  | Total | 0
[6 empty] | Remaining | 0
Project Manager |  |  | Date
City Engineer |  |  | Date |  |  | CURRENT PAYMENT DUE
Account Number:
City Manager (if over $5,000.00) |  |  | Date
0
This certificate is not negotiable. It is payable only to the payee named herein and its issuance, payment and acceptance are without prejudice to any rights of the Owner or Contractor under their Contract.