## DATA
INPUT DATA
Project Name: |  | Creekside & Fernwood Pump Stn Coating
Project No:
Resolution No: |  | 2020-3692
Purchase Order No's: |  | 21-052
Contractor |  | R. L. Reimers Company
Resolution Information |  | The contract was approved by City Council on 9/9/2020 per Resolution No. 2020-3692 with a contract value of $119,285.00. Resolution No. 2020-3691 was approved by City Council on July 23, 2020 (contract in the amount of $121,950.00).
Original Contract Value |  | 121950
Account Number Splits
[6 empty] | Water | Storm | Sanitary | Street
|  | Total Completed & Stored to Date | Date of Application | Invoice Date | Pay Period Through | 04-5150-706329
Progress Payment | 1 | 127152.85 | 2020-11-16 | 2020-11-11 | 2020-11-11 | 127152.85
Progress Payment | 2
Progress Payment | 3
Progress Payment | 4
Progress Payment | 5
Progress Payment | 6
Progress Payment | 7
Progress Payment | 8
Progress Payment | 9
Progress Payment | 10
Progress Payment | 11
Progress Payment | 12
Progress Payment | 13
Progress Payment | 14
Progress Payment | 15
Progress Payment | 16
Progress Payment | 17
Progress Payment | 18
Progress Payment | 19
Progress Payment | 20
Note on H11: Jason Wuertz: Insert numbers from "work completed THIS PERIOD." Do not remove retention in these cells as it is removed on the progress payment page

## PROGRESS PAYMT #1
PROGRESS PAYMENT
Project Name: | Creekside & Fernwood Pump Stn Coating |  |  |  |  | Page: |  | 1 of 1
Project No: | [5 empty] | Date of Application: |  | 2020-11-16
Resolution #: |  | 2020-3692 |  |  |  | Invoice Date: |  | 2020-11-11
Purchase Order No's: |  | 21-052 |  |  |  | Pay Period Through: |  | 2020-11-11
The contract was approved by City Council on 9/9/2020 per Resolution No. 2020-3692 with a contract value of $119,285.00. Resolution No. 2020-3691 was approved by City Council on July 23, 2020 (contract in the amount of $121,950.00). | [5 empty] | Contractor: | R. L. Reimers Company
[6 empty] | Payment No: |  | 1
Purchase Order is attached
Application is made for Payment, as shown below, in connection with the Contract. Attached is the contractor's signed request for payment. Payment due date per Contract specification. The present status of the account(s) for this Contract is as follows:
THIS PAYMENT
Original Contract | Change Orders | Revised Contract | Total Completed & Stored To Date | Total Retainage |  | Total Earned Less Retainage | Less Previous Certificates for Payment | Balance To Finish
121950 | 11895 | 133845 | 127152.85 | 6692.25 |  | 120460.6 | 120460.6 | 13384.4
PROGRESS INVOICE HISTORY |  |  |  |  | CHANGE ORDER SUMMARY
Pay No. / Date | Invoice Amount | Retention | % Complete |  | Change Order # | Date Approved | PO# | Total Value
1 | 127152.85 | 6692.25 | 100%
2 |  |  | 0%
3 |  |  | 0%
4 |  |  | 0%
5 |  |  | 0%
6 |  |  | 0% |  |  |  | Total | 0
7 |  |  | 0%
8 |  |  | 0%
9 |  |  | 0%
10 |  |  | 0%
11 |  |  | 0%
12 |  |  | 0% |  | CURRENT PAYMENT DUE
13 |  |  | 0%
14 |  |  | 0% |  | Account #: |  | Amount:
15 |  |  | 0% |  | 04-5150-706329 |  | 127152.85
16 |  |  | 0%
17 |  |  | 0%
18 |  |  | 0% | [5 empty] | Payment Due Matches In different cells
19 |  |  | 0% |  | Total Payment: |  | 127152.85 |  | WRONG
20 |  |  | 0% | [5 empty] | CHECKS
Total | 127152.85 | 6692.25 | 100%
Project Manager |  |  | Date |  | Director of Finance |  |  | Date
City Engineer |  |  | Date |  | City Manager (if over $5,000.00) |  |  | Date
This certificate is not negotiable. It is payable only to the payee named herein and its issuance, payment and acceptance are without prejudice to any rights of the Owner or Contractor under their Contract.
Note on K42: Jason Wuertz: This checks that Cell H42 matches H19 which it should
Note on K43: Jason Wuertz: Checks that H42 matches H24 which it should

## PROGRESS PAYMT #2
PROGRESS PAYMENT
Project Name: | Creekside & Fernwood Pump Stn Coating |  |  |  |  | Page: |  | 1 of 1
Project No: | [5 empty] | Date of Application: |  | 0
Resolution #: | 2020-3692 |  |  |  |  | Invoice Date: |  | 0
Purchase Order No's: |  | 21-052 |  |  |  | Pay Period Through: |  | 0
The contract was approved by City Council on 9/9/2020 per Resolution No. 2020-3692 with a contract value of $119,285.00. Resolution No. 2020-3691 was approved by City Council on July 23, 2020 (contract in the amount of $121,950.00). | [5 empty] | Contractor: | R. L. Reimers Company
[6 empty] | Payment No: |  | 2
Purchase Order is attached
Application is made for Payment, as shown below, in connection with the Contract. Attached is the contractor's signed request for payment. Payment due date per Contract specification. The present status of the account(s) for this Contract is as follows:
THIS PAYMENT
Original Contract | Change Orders | Revised Contract | Total Completed & Stored To Date | Total Retainage |  | Total Earned Less Retainage | Less Previous Certificates for Payment | Balance To Finish
121950 | 0 | 121950 | 0 | 0 |  | 0 | -127152.85 | 121950
PROGRESS INVOICE HISTORY |  |  |  |  | CHANGE ORDER SUMMARY
Pay No. / Date | Invoice Amount | Retention | % Complete |  | Change Order # | Date Approved | PO# | Total Value
1 | 127152.85 | 6692.25 | 109.8%
2 | -127152.85 | -6692.25 | -109.8%
3 |  |  | 0%
4 |  |  | 0%
5 |  |  | 0%
6 |  |  | 0% |  |  |  | Total | 0
7 |  |  | 0%
8 |  |  | 0%
9 |  |  | 0%
10 |  |  | 0%
11 |  |  | 0%
12 |  |  | 0% |  | CURRENT PAYMENT DUE
13 |  |  | 0%
14 |  |  | 0% |  | Account #: |  | Amount:
15 |  |  | 0% |  | 04-5150-706329
16 |  |  | 0%
17 |  |  | 0% | [5 empty] | Payment Due Matches In different cells
18 |  |  | 0% | [5 empty] | WRONG
19 |  |  | 0% |  | Total Payment: |  | 0 |  | WRONG
20 |  |  | 0% | [5 empty] | CHECKS
Total | 0 | 0 | 0%
Project Manager |  |  | Date |  | City Manager (if over $5,000.00) |  |  | Date
City Engineer |  |  | Date
This certificate is not negotiable. It is payable only to the payee named herein and its issuance, payment and acceptance are without prejudice to any rights of the Owner or Contractor under their Contract.
Note on I4: Jason Wuertz: Add one number to the cell to move down one on the main page
Note on I10: Jason Wuertz: Add one number to the cell in the formula
Note on D19: Jason Wuertz: Add one number to the forumula cell
Note on B23: Jason Wuertz: When adding new tab, copy number from previous tab, not the formula
Note on C23: Jason Wuertz: =Total Retainage - sum of retention totals from previous payments
Note on K41: Jason Wuertz: This checks that Cell H42 matches H19 which it should
Note on K42: Jason Wuertz: Checks that H42 matches H24 which it should
Note on K43: Jason Wuertz: Checks that the total invoice history without retention, plus the balance to finish = the revised contract

## PROGRESS PAYMT #3
PROGRESS PAYMENT
Project Name: | Creekside & Fernwood Pump Stn Coating |  |  |  |  | Page: |  | 1 of 1
Project No: | [5 empty] | Date of Application: |  | 0
Resolution #: | 2020-3692 |  |  |  |  | Invoice Date: |  | 0
Purchase Order No's: |  | 21-052 |  |  |  | Pay Period Through: |  | 0
The contract was approved by City Council on 9/9/2020 per Resolution No. 2020-3692 with a contract value of $119,285.00. Resolution No. 2020-3691 was approved by City Council on July 23, 2020 (contract in the amount of $121,950.00). | [5 empty] | Contractor: | R. L. Reimers Company
[6 empty] | Payment No: |  | 3
Purchase Order is attached
Application is made for Payment, as shown below, in connection with the Contract. Attached is the contractor's signed request for payment. Payment due date per Contract specification. The present status of the account(s) for this Contract is as follows:
THIS PAYMENT
Original Contract | Change Orders | Revised Contract | Total Completed & Stored To Date | Total Retainage |  | Total Earned Less Retainage | Less Previous Certificates for Payment | Balance To Finish
121950 | 0 | 121950 | 0 | 0 |  | 0 | 0 | 121950
PROGRESS INVOICE HISTORY |  |  |  |  | CHANGE ORDER SUMMARY
Pay No. / Date | Invoice Amount | Retention | % Complete |  | Change Order # | Date Approved | PO# | Total Value
1 | 127152.85 | 6692.25 | 109.8%
2 | -127152.85 | -6692.25 | -109.8%
3 | 0 | 0 | 0%
4 |  |  | 0%
5 |  |  | 0%
6 |  |  | 0% |  |  |  | Total | 0
7 |  |  | 0%
8 |  |  | 0%
9 |  |  | 0%
10 |  |  | 0%
11 |  |  | 0%
12 |  |  | 0% |  | CURRENT PAYMENT DUE
13 |  |  | 0%
14 |  |  | 0% |  | Account #: |  | Amount:
15 |  |  | 0% |  | 04-5150-706329
16 |  |  | 0%
17 |  |  | 0% | [5 empty] | Payment Due Matches In different cells
18 |  |  | 0% | [5 empty] | CHECKS
19 |  |  | 0% |  | Total Payment: |  | 0 |  | CHECKS
20 |  |  | 0% | [5 empty] | CHECKS
Total | 0 | 0 | 0%
Project Manager |  |  | Date |  | City Manager (if over $5,000.00) |  |  | Date
City Engineer |  |  | Date
This certificate is not negotiable. It is payable only to the payee named herein and its issuance, payment and acceptance are without prejudice to any rights of the Owner or Contractor under their Contract.
Note on I4: Jason Wuertz: Add one number to the cell to move down one on the main page
Note on I10: Jason Wuertz: Add one number to the cell in the formula
Note on D19: Jason Wuertz: Add one number to the forumula cell
Note on B23: Jason Wuertz: When adding new tab, copy number from previous tab, not the formula
Note on C23: Jason Wuertz: =Total Retainage - sum of retention totals from previous payments
Note on K41: Jason Wuertz: This checks that Cell H42 matches H19 which it should
Note on K42: Jason Wuertz: Checks that H42 matches H24 which it should
Note on K43: Jason Wuertz: Checks that the total invoice history without retention, plus the balance to finish = the revised contract

## PROGRESS PAYMT #4
PROGRESS PAYMENT
Project Name: | Creekside & Fernwood Pump Stn Coating |  |  |  |  | Page: |  | 1 of 1
Project No: | [5 empty] | Date of Application: |  | 0
Resolution #: | 2020-3692 |  |  |  |  | Invoice Date: |  | 0
Purchase Order No's: |  | 21-052 |  |  |  | Pay Period Through: |  | 0
The contract was approved by City Council on 9/9/2020 per Resolution No. 2020-3692 with a contract value of $119,285.00. Resolution No. 2020-3691 was approved by City Council on July 23, 2020 (contract in the amount of $121,950.00). | [5 empty] | Contractor: | R. L. Reimers Company
[6 empty] | Payment No: |  | 4
Purchase Order is attached
Application is made for Payment, as shown below, in connection with the Contract. Attached is the contractor's signed request for payment. Payment due date per Contract specification. The present status of the account(s) for this Contract is as follows:
THIS PAYMENT
Original Contract | Change Orders | Revised Contract | Total Completed & Stored To Date | Total Retainage |  | Total Earned Less Retainage | Less Previous Certificates for Payment | Balance To Finish
121950 | 0 | 121950 | 0 | 0 |  | 0 | 0 | 121950
PROGRESS INVOICE HISTORY |  |  |  |  | CHANGE ORDER SUMMARY
Pay No. / Date | Invoice Amount | Retention | % Complete |  | Change Order # | Date Approved | PO# | Total Value
1 | 127152.85 | 6692.25 | 109.8%
2 | -127152.85 | -6692.25 | -109.8%
3 | 0 | 0 | 0%
4 | 0 | 0 | 0%
5 |  |  | 0%
6 |  |  | 0% |  |  |  | Total | 0
7 |  |  | 0%
8 |  |  | 0%
9 |  |  | 0%
10 |  |  | 0%
11 |  |  | 0%
12 |  |  | 0% |  | CURRENT PAYMENT DUE
13 |  |  | 0%
14 |  |  | 0% |  | Account #: |  | Amount:
15 |  |  | 0% |  | 04-5150-706329
16 |  |  | 0%
17 |  |  | 0% | [5 empty] | Payment Due Matches In different cells
18 |  |  | 0% | [5 empty] | CHECKS
19 |  |  | 0% |  | Total Payment: |  | 0 |  | CHECKS
20 |  |  | 0% | [5 empty] | CHECKS
Total | 0 | 0 | 0%
Project Manager |  |  | Date |  | City Manager (if over $5,000.00) |  |  | Date
City Engineer |  |  | Date
This certificate is not negotiable. It is payable only to the payee named herein and its issuance, payment and acceptance are without prejudice to any rights of the Owner or Contractor under their Contract.
Note on I4: Jason Wuertz: Add one number to the cell to move down one on the main page
Note on I10: Jason Wuertz: Add one number to the cell in the formula
Note on D19: Jason Wuertz: Add one number to the forumula cell
Note on B23: Jason Wuertz: When adding new tab, copy number from previous tab, not the formula
Note on C23: Jason Wuertz: =Total Retainage - sum of retention totals from previous payments
Note on K41: Jason Wuertz: This checks that Cell H42 matches H19 which it should
Note on K42: Jason Wuertz: Checks that H42 matches H24 which it should
Note on K43: Jason Wuertz: Checks that the total invoice history without retention, plus the balance to finish = the revised contract

## PROGRESS PAYMT #5
PROGRESS PAYMENT
Project Name: | Creekside & Fernwood Pump Stn Coating |  |  |  |  | Page: |  | 1 of 1
Project No: | [5 empty] | Date of Application: |  | 0
Resolution #: | 2020-3692 |  |  |  |  | Invoice Date: |  | 0
Purchase Order No's: |  | 21-052 |  |  |  | Pay Period Through: |  | 0
The contract was approved by City Council on 9/9/2020 per Resolution No. 2020-3692 with a contract value of $119,285.00. Resolution No. 2020-3691 was approved by City Council on July 23, 2020 (contract in the amount of $121,950.00). | [5 empty] | Contractor: | R. L. Reimers Company
[6 empty] | Payment No: |  | 5
Purchase Order is attached
Application is made for Payment, as shown below, in connection with the Contract. Attached is the contractor's signed request for payment. Payment due date per Contract specification. The present status of the account(s) for this Contract is as follows:
THIS PAYMENT
Original Contract | Change Orders | Revised Contract | Total Completed & Stored To Date | Total Retainage |  | Total Earned Less Retainage | Less Previous Certificates for Payment | Balance To Finish
121950 | 0 | 121950 | 0 | 0 |  | 0 | 0 | 121950
PROGRESS INVOICE HISTORY |  |  |  |  | CHANGE ORDER SUMMARY
Pay No. / Date | Invoice Amount | Retention | % Complete |  | Change Order # | Date Approved | PO# | Total Value
1 | 127152.85 | 6692.25 | 109.8%
2 | -127152.85 | -6692.25 | -109.8%
3 | 0 | 0 | 0%
4 | 0 | 0 | 0%
5 | 0 | 0 | 0%
6 |  |  | 0% |  |  |  | Total | 0
7 |  |  | 0%
8 |  |  | 0%
9 |  |  | 0%
10 |  |  | 0%
11 |  |  | 0%
12 |  |  | 0% |  | CURRENT PAYMENT DUE
13 |  |  | 0%
14 |  |  | 0% |  | Account #: |  | Amount:
15 |  |  | 0% |  | 04-5150-706329
16 |  |  | 0%
17 |  |  | 0% | [5 empty] | Payment Due Matches In different cells
18 |  |  | 0% | [5 empty] | CHECKS
19 |  |  | 0% |  | Total Payment: |  | 0 |  | CHECKS
20 |  |  | 0% | [5 empty] | CHECKS
Total | 0 | 0 | 0%
Project Manager |  |  | Date |  | City Manager (if over $5,000.00) |  |  | Date
City Engineer |  |  | Date
This certificate is not negotiable. It is payable only to the payee named herein and its issuance, payment and acceptance are without prejudice to any rights of the Owner or Contractor under their Contract.
Note on I4: Jason Wuertz: Add one number to the cell to move down one on the main page
Note on I10: Jason Wuertz: Add one number to the cell in the formula
Note on D19: Jason Wuertz: Add one number to the forumula cell
Note on H19: Jason Wuertz: Change sheet number
Note on B23: Jason Wuertz: When adding new tab, copy number from previous tab, not the formula
Note on C23: Jason Wuertz: =Total Retainage - sum of retention totals from previous payments
Note on K41: Jason Wuertz: This checks that Cell H42 matches H19 which it should
Note on K42: Jason Wuertz: Checks that H42 matches H24 which it should
Note on K43: Jason Wuertz: Checks that the total invoice history without retention, plus the balance to finish = the revised contract

## PROGRESS PAYMT #6
PROGRESS PAYMENT
Project Name: | Creekside & Fernwood Pump Stn Coating |  |  |  |  | Page: |  | 1 of 1
Project No: | [5 empty] | Date of Application: |  | 0
Resolution #: | 2020-3692 |  |  |  |  | Invoice Date: |  | 0
Purchase Order No's: |  | 21-052 |  |  |  | Pay Period Through: |  | 0
The contract was approved by City Council on 9/9/2020 per Resolution No. 2020-3692 with a contract value of $119,285.00. Resolution No. 2020-3691 was approved by City Council on July 23, 2020 (contract in the amount of $121,950.00). | [5 empty] | Contractor: | R. L. Reimers Company
[6 empty] | Payment No: |  | 6
Purchase Order is attached
Application is made for Payment, as shown below, in connection with the Contract. Attached is the contractor's signed request for payment. Payment due date per Contract specification. The present status of the account(s) for this Contract is as follows:
THIS PAYMENT
Original Contract | Change Orders | Revised Contract | Total Completed & Stored To Date | Total Retainage |  | Total Earned Less Retainage | Less Previous Certificates for Payment | Balance To Finish
121950 | 0 | 121950 | 0 | 0 |  | 0 | 0 | 121950
PROGRESS INVOICE HISTORY |  |  |  |  | CHANGE ORDER SUMMARY
Pay No. / Date | Invoice Amount | Retention | % Complete |  | Change Order # | Date Approved | PO# | Total Value
1 | 127152.85 | 6692.25 | 109.8%
2 | -127152.85 | -6692.25 | -109.8%
3 | 0 | 0 | 0%
4 | 0 | 0 | 0%
5 | 0 | 0 | 0%
6 | 0 | 0 | 0% |  |  |  | Total | 0
7 |  |  | 0%
8 |  |  | 0%
9 |  |  | 0%
10 |  |  | 0%
11 |  |  | 0%
12 |  |  | 0% |  | CURRENT PAYMENT DUE
13 |  |  | 0%
14 |  |  | 0% |  | Account #: |  | Amount:
15 |  |  | 0% |  | 04-5150-706329
16 |  |  | 0%
17 |  |  | 0% | [5 empty] | Payment Due Matches In different cells
18 |  |  | 0% | [5 empty] | CHECKS
19 |  |  | 0% |  | Total Payment: |  | 0 |  | CHECKS
20 |  |  | 0% | [5 empty] | CHECKS
Total | 0 | 0 | 0%
Project Manager |  |  | Date |  | City Manager (if over $5,000.00) |  |  | Date
City Engineer |  |  | Date
This certificate is not negotiable. It is payable only to the payee named herein and its issuance, payment and acceptance are without prejudice to any rights of the Owner or Contractor under their Contract.
Note on I4: Jason Wuertz: Add one number to the cell to move down one on the main page
Note on I10: Jason Wuertz: Add one number to the cell in the formula
Note on D19: Jason Wuertz: Add one number to the forumula cell
Note on H19: Jason Wuertz: Change sheet number
Note on B23: Jason Wuertz: When adding new tab, copy number from previous tab, not the formula
Note on C23: Jason Wuertz: =Total Retainage - sum of retention totals from previous payments
Note on K41: Jason Wuertz: This checks that Cell H42 matches H19 which it should
Note on K42: Jason Wuertz: Checks that H42 matches H24 which it should
Note on K43: Jason Wuertz: Checks that the total invoice history without retention, plus the balance to finish = the revised contract

## PROGRESS PAYMT #7
PROGRESS PAYMENT
Project Name: | Creekside & Fernwood Pump Stn Coating |  |  |  |  | Page: |  | 1 of 1
Project No: | [5 empty] | Date of Application: |  | 0
Resolution #: | 2020-3692 |  |  |  |  | Invoice Date: |  | 0
Purchase Order No's: |  | 21-052 |  |  |  | Pay Period Through: |  | 0
The contract was approved by City Council on 9/9/2020 per Resolution No. 2020-3692 with a contract value of $119,285.00. Resolution No. 2020-3691 was approved by City Council on July 23, 2020 (contract in the amount of $121,950.00). | [5 empty] | Contractor: | R. L. Reimers Company
[6 empty] | Payment No: |  | 7
Purchase Order is attached
Application is made for Payment, as shown below, in connection with the Contract. Attached is the contractor's signed request for payment. Payment due date per Contract specification. The present status of the account(s) for this Contract is as follows:
THIS PAYMENT
Original Contract | Change Orders | Revised Contract | Total Completed & Stored To Date | Total Retainage |  | Total Earned Less Retainage | Less Previous Certificates for Payment | Balance To Finish
121950 | 0 | 121950 | 0 | 0 |  | 0 | 0 | 121950
PROGRESS INVOICE HISTORY |  |  |  |  | CHANGE ORDER SUMMARY
Pay No. / Date | Invoice Amount | Retention | % Complete |  | Change Order # | Date Approved | PO# | Total Value
1 | 127152.85 | 6692.25 | 109.8%
2 | -127152.85 | -6692.25 | -109.8%
3 | 0 | 0 | 0%
4 | 0 | 0 | 0%
5 | 0 | 0 | 0%
6 | 0 | 0 | 0% |  |  |  | Total | 0
7 | 0 | 0 | 0%
8 |  |  | 0%
9 |  |  | 0%
10 |  |  | 0%
11 |  |  | 0%
12 |  |  | 0% |  | CURRENT PAYMENT DUE
13 |  |  | 0%
14 |  |  | 0% |  | Account #: |  | Amount:
15 |  |  | 0% |  | 04-5150-706329
16 |  |  | 0%
17 |  |  | 0% | [5 empty] | Payment Due Matches In different cells
18 |  |  | 0% | [5 empty] | CHECKS
19 |  |  | 0% |  | Total Payment: |  | 0 |  | CHECKS
20 |  |  | 0% | [5 empty] | CHECKS
Total | 0 | 0 | 0%
Project Manager |  |  | Date |  | City Manager (if over $5,000.00) |  |  | Date
City Engineer |  |  | Date
This certificate is not negotiable. It is payable only to the payee named herein and its issuance, payment and acceptance are without prejudice to any rights of the Owner or Contractor under their Contract.
Note on I4: Jason Wuertz: Add one number to the cell to move down one on the main page
Note on I10: Jason Wuertz: Add one number to the cell in the formula
Note on D19: Jason Wuertz: Add one number to the forumula cell
Note on H19: Jason Wuertz: Change sheet number
Note on B23: Jason Wuertz: When adding new tab, copy number from previous tab, not the formula
Note on C23: Jason Wuertz: =Total Retainage - sum of retention totals from previous payments
Note on K41: Jason Wuertz: This checks that Cell H42 matches H19 which it should
Note on K42: Jason Wuertz: Checks that H42 matches H24 which it should
Note on K43: Jason Wuertz: Checks that the total invoice history without retention, plus the balance to finish = the revised contract

## PROGRESS PAYMT #8
PROGRESS PAYMENT
Project Name: | Creekside & Fernwood Pump Stn Coating |  |  |  |  | Page: |  | 1 of 1
Project No: | [5 empty] | Date of Application: |  | 0
Resolution #: | 2020-3692 |  |  |  |  | Invoice Date: |  | 0
Purchase Order No's: |  | 21-052 |  |  |  | Pay Period Through: |  | 0
The contract was approved by City Council on 9/9/2020 per Resolution No. 2020-3692 with a contract value of $119,285.00. Resolution No. 2020-3691 was approved by City Council on July 23, 2020 (contract in the amount of $121,950.00). | [5 empty] | Contractor: | R. L. Reimers Company
[6 empty] | Payment No: |  | 8
Purchase Order is attached
Application is made for Payment, as shown below, in connection with the Contract. Attached is the contractor's signed request for payment. Payment due date per Contract specification. The present status of the account(s) for this Contract is as follows:
THIS PAYMENT
Original Contract | Change Orders | Revised Contract | Total Completed & Stored To Date | Total Retainage |  | Total Earned Less Retainage | Less Previous Certificates for Payment | Balance To Finish
121950 | 0 | 121950 | 0 | 0 |  | 0 | 0 | 121950
PROGRESS INVOICE HISTORY |  |  |  |  | CHANGE ORDER SUMMARY
Pay No. / Date | Invoice Amount | Retention | % Complete |  | Change Order # | Date Approved | PO# | Total Value
1 | 127152.85 | 6692.25 | 109.8%
2 | -127152.85 | -6692.25 | -109.8%
3 | 0 | 0 | 0%
4 | 0 | 0 | 0%
5 | 0 | 0 | 0%
6 | 0 | 0 | 0% |  |  |  | Total | 0
7 | 0 | 0 | 0%
8 | 0 | 0 | 0%
9 |  |  | 0%
10 |  |  | 0%
11 |  |  | 0%
12 |  |  | 0% |  | CURRENT PAYMENT DUE
13 |  |  | 0%
14 |  |  | 0% |  | Account #: |  | Amount:
15 |  |  | 0% |  | 04-5150-706329
16 |  |  | 0%
17 |  |  | 0% | [5 empty] | Payment Due Matches In different cells
18 |  |  | 0% | [5 empty] | CHECKS
19 |  |  | 0% |  | Total Payment: |  | 0 |  | CHECKS
20 |  |  | 0% | [5 empty] | CHECKS
Total | 0 | 0 | 0%
Project Manager |  |  | Date |  | City Manager (if over $5,000.00) |  |  | Date
City Engineer |  |  | Date
This certificate is not negotiable. It is payable only to the payee named herein and its issuance, payment and acceptance are without prejudice to any rights of the Owner or Contractor under their Contract.
Note on I4: Jason Wuertz: Add one number to the cell to move down one on the main page
Note on I10: Jason Wuertz: Add one number to the cell in the formula
Note on D19: Jason Wuertz: Add one number to the forumula cell
Note on H19: Jason Wuertz: Change sheet number
Note on B23: Jason Wuertz: When adding new tab, copy number from previous tab, not the formula
Note on C23: Jason Wuertz: =Total Retainage - sum of retention totals from previous payments
Note on K41: Jason Wuertz: This checks that Cell H42 matches H19 which it should
Note on K42: Jason Wuertz: Checks that H42 matches H24 which it should
Note on K43: Jason Wuertz: Checks that the total invoice history without retention, plus the balance to finish = the revised contract

## PROGRESS PAYMT #9
PROGRESS PAYMENT
Project Name: | Creekside & Fernwood Pump Stn Coating |  |  |  |  | Page: |  | 1 of 1
Project No: | [5 empty] | Date of Application: |  | 0
Resolution #: | 2020-3692 |  |  |  |  | Invoice Date: |  | 0
Purchase Order No's: |  | 21-052 |  |  |  | Pay Period Through: |  | 0
The contract was approved by City Council on 9/9/2020 per Resolution No. 2020-3692 with a contract value of $119,285.00. Resolution No. 2020-3691 was approved by City Council on July 23, 2020 (contract in the amount of $121,950.00). | [5 empty] | Contractor: | R. L. Reimers Company
[6 empty] | Payment No: |  | 9
Purchase Order is attached
Application is made for Payment, as shown below, in connection with the Contract. Attached is the contractor's signed request for payment. Payment due date per Contract specification. The present status of the account(s) for this Contract is as follows:
THIS PAYMENT
Original Contract | Change Orders | Revised Contract | Total Completed & Stored To Date | Total Retainage |  | Total Earned Less Retainage | Less Previous Certificates for Payment | Balance To Finish
121950 | 0 | 121950 | 0 | 0 |  | 0 | 0 | 121950
PROGRESS INVOICE HISTORY |  |  |  |  | CHANGE ORDER SUMMARY
Pay No. / Date | Invoice Amount | Retention | % Complete |  | Change Order # | Date Approved | PO# | Total Value
1 | 127152.85 | 6692.25 | 109.8%
2 | -127152.85 | -6692.25 | -109.8%
3 | 0 | 0 | 0%
4 | 0 | 0 | 0%
5 | 0 | 0 | 0%
6 | 0 | 0 | 0% |  |  |  | Total | 0
7 | 0 | 0 | 0%
8 | 0 | 0 | 0%
9 | 0 | 0 | 0%
10 |  |  | 0%
11 |  |  | 0%
12 |  |  | 0% |  | CURRENT PAYMENT DUE
13 |  |  | 0%
14 |  |  | 0% |  | Account #: |  | Amount:
15 |  |  | 0% |  | 04-5150-706329
16 |  |  | 0%
17 |  |  | 0% | [5 empty] | Payment Due Matches In different cells
18 |  |  | 0% | [5 empty] | CHECKS
19 |  |  | 0% |  | Total Payment: |  | 0 |  | CHECKS
20 |  |  | 0% | [5 empty] | CHECKS
Total | 0 | 0 | 0%
Project Manager |  |  | Date |  | City Manager (if over $5,000.00) |  |  | Date
City Engineer |  |  | Date
This certificate is not negotiable. It is payable only to the payee named herein and its issuance, payment and acceptance are without prejudice to any rights of the Owner or Contractor under their Contract.
Note on I4: Jason Wuertz: Add one number to the cell to move down one on the main page
Note on I10: Jason Wuertz: Add one number to the cell in the formula
Note on D19: Jason Wuertz: Add one number to the forumula cell
Note on H19: Jason Wuertz: Change sheet number
Note on B23: Jason Wuertz: When adding new tab, copy number from previous tab, not the formula
Note on C23: Jason Wuertz: =Total Retainage - sum of retention totals from previous payments
Note on K41: Jason Wuertz: This checks that Cell H42 matches H19 which it should
Note on K42: Jason Wuertz: Checks that H42 matches H24 which it should
Note on K43: Jason Wuertz: Checks that the total invoice history without retention, plus the balance to finish = the revised contract

## PROGRESS PAYMT #10
PROGRESS PAYMENT
Project Name: | Creekside & Fernwood Pump Stn Coating |  |  |  |  | Page: |  | 1 of 1
Project No: | [5 empty] | Date of Application: |  | 0
Resolution #: | 2020-3692 |  |  |  |  | Invoice Date: |  | 0
Purchase Order No's: |  | 21-052 |  |  |  | Pay Period Through: |  | 0
The contract was approved by City Council on 9/9/2020 per Resolution No. 2020-3692 with a contract value of $119,285.00. Resolution No. 2020-3691 was approved by City Council on July 23, 2020 (contract in the amount of $121,950.00). | [5 empty] | Contractor: | R. L. Reimers Company
[6 empty] | Payment No: |  | 10
Purchase Order is attached
Application is made for Payment, as shown below, in connection with the Contract. Attached is the contractor's signed request for payment. Payment due date per Contract specification. The present status of the account(s) for this Contract is as follows:
THIS PAYMENT
Original Contract | Change Orders | Revised Contract | Total Completed & Stored To Date | Total Retainage |  | Total Earned Less Retainage | Less Previous Certificates for Payment | Balance To Finish
121950 | 0 | 121950 | 0 | 0 |  | 0 | 0 | 121950
PROGRESS INVOICE HISTORY |  |  |  |  | CHANGE ORDER SUMMARY
Pay No. / Date | Invoice Amount | Retention | % Complete |  | Change Order # | Date Approved | PO# | Total Value
1 | 127152.85 | 6692.25 | 109.8%
2 | -127152.85 | -6692.25 | -109.8%
3 | 0 | 0 | 0%
4 | 0 | 0 | 0%
5 | 0 | 0 | 0%
6 | 0 | 0 | 0% |  |  |  | Total | 0
7 | 0 | 0 | 0%
8 | 0 | 0 | 0%
9 | 0 | 0 | 0%
10 | 0 | 0 | 0%
11 |  |  | 0%
12 |  |  | 0% |  | CURRENT PAYMENT DUE
13 |  |  | 0%
14 |  |  | 0% |  | Account #: |  | Amount:
15 |  |  | 0% |  | 04-5150-706329
16 |  |  | 0%
17 |  |  | 0% | [5 empty] | Payment Due Matches In different cells
18 |  |  | 0% | [5 empty] | CHECKS
19 |  |  | 0% |  | Total Payment: |  | 0 |  | CHECKS
20 |  |  | 0% | [5 empty] | CHECKS
Total | 0 | 0 | 0%
Project Manager |  |  | Date |  | City Manager (if over $5,000.00) |  |  | Date
City Engineer |  |  | Date
This certificate is not negotiable. It is payable only to the payee named herein and its issuance, payment and acceptance are without prejudice to any rights of the Owner or Contractor under their Contract.
Note on I4: Jason Wuertz: Add one number to the cell to move down one on the main page
Note on I10: Jason Wuertz: Add one number to the cell in the formula
Note on D19: Jason Wuertz: Add one number to the forumula cell
Note on H19: Jason Wuertz: Change sheet number
Note on B23: Jason Wuertz: When adding new tab, copy number from previous tab, not the formula
Note on C23: Jason Wuertz: =Total Retainage - sum of retention totals from previous payments
Note on K41: Jason Wuertz: This checks that Cell H42 matches H19 which it should
Note on K42: Jason Wuertz: Checks that H42 matches H24 which it should
Note on K43: Jason Wuertz: Checks that the total invoice history without retention, plus the balance to finish = the revised contract

## PROGRESS PAYMT #11
PROGRESS PAYMENT
Project Name: | Creekside & Fernwood Pump Stn Coating |  |  |  |  | Page: |  | 1 of 1
Project No: | [5 empty] | Date of Application: |  | 0
Resolution #: | 2020-3692 |  |  |  |  | Invoice Date: |  | 0
Purchase Order No's: |  | 21-052 |  |  |  | Pay Period Through: |  | 0
The contract was approved by City Council on 9/9/2020 per Resolution No. 2020-3692 with a contract value of $119,285.00. Resolution No. 2020-3691 was approved by City Council on July 23, 2020 (contract in the amount of $121,950.00). | [5 empty] | Contractor: | R. L. Reimers Company
[6 empty] | Payment No: |  | 11
Purchase Order is attached
Application is made for Payment, as shown below, in connection with the Contract. Attached is the contractor's signed request for payment. Payment due date per Contract specification. The present status of the account(s) for this Contract is as follows:
THIS PAYMENT
Original Contract | Change Orders | Revised Contract | Total Completed & Stored To Date | Total Retainage |  | Total Earned Less Retainage | Less Previous Certificates for Payment | Balance To Finish
121950 | 0 | 121950 | 0 | 0 |  | 0 | 0 | 121950
PROGRESS INVOICE HISTORY |  |  |  |  | CHANGE ORDER SUMMARY
Pay No. / Date | Invoice Amount | Retention | % Complete |  | Change Order # | Date Approved | PO# | Total Value
1 | 127152.85 | 6692.25 | 109.8%
2 | -127152.85 | -6692.25 | -109.8%
3 | 0 | 0 | 0%
4 | 0 | 0 | 0%
5 | 0 | 0 | 0%
6 | 0 | 0 | 0% |  |  |  | Total | 0
7 | 0 | 0 | 0%
8 | 0 | 0 | 0%
9 | 0 | 0 | 0%
10 | 0 | 0 | 0%
11 | 0 | 0 | 0%
12 |  |  | 0% |  | CURRENT PAYMENT DUE
13 |  |  | 0%
14 |  |  | 0% |  | Account #: |  | Amount:
15 |  |  | 0% |  | 04-5150-706329
16 |  |  | 0%
17 |  |  | 0% | [5 empty] | Payment Due Matches In different cells
18 |  |  | 0% | [5 empty] | CHECKS
19 |  |  | 0% |  | Total Payment: |  | 0 |  | CHECKS
20 |  |  | 0% | [5 empty] | CHECKS
Total | 0 | 0 | 0%
Project Manager |  |  | Date |  | City Manager (if over $5,000.00) |  |  | Date
City Engineer |  |  | Date
This certificate is not negotiable. It is payable only to the payee named herein and its issuance, payment and acceptance are without prejudice to any rights of the Owner or Contractor under their Contract.
Note on I4: Jason Wuertz: Add one number to the cell to move down one on the main page
Note on I10: Jason Wuertz: Add one number to the cell in the formula
Note on D19: Jason Wuertz: Add one number to the forumula cell
Note on H19: Jason Wuertz: Change sheet number
Note on B23: Jason Wuertz: When adding new tab, copy number from previous tab, not the formula
Note on C23: Jason Wuertz: =Total Retainage - sum of retention totals from previous payments
Note on K41: Jason Wuertz: This checks that Cell H42 matches H19 which it should
Note on K42: Jason Wuertz: Checks that H42 matches H24 which it should
Note on K43: Jason Wuertz: Checks that the total invoice history without retention, plus the balance to finish = the revised contract

## PROGRESS PAYMT #12
PROGRESS PAYMENT
Project Name: | Creekside & Fernwood Pump Stn Coating |  |  |  |  | Page: |  | 1 of 1
Project No: | [5 empty] | Date of Application: |  | 0
Resolution #: | 2020-3692 |  |  |  |  | Invoice Date: |  | 0
Purchase Order No's: |  | 21-052 |  |  |  | Pay Period Through: |  | 0
The contract was approved by City Council on 9/9/2020 per Resolution No. 2020-3692 with a contract value of $119,285.00. Resolution No. 2020-3691 was approved by City Council on July 23, 2020 (contract in the amount of $121,950.00). | [5 empty] | Contractor: | R. L. Reimers Company
[6 empty] | Payment No: |  | 12
Purchase Order is attached
Application is made for Payment, as shown below, in connection with the Contract. Attached is the contractor's signed request for payment. Payment due date per Contract specification. The present status of the account(s) for this Contract is as follows:
THIS PAYMENT
Original Contract | Change Orders | Revised Contract | Total Completed & Stored To Date | Total Retainage |  | Total Earned Less Retainage | Less Previous Certificates for Payment | Balance To Finish
121950 | 0 | 121950 | 0 | 0 |  | 0 | 0 | 121950
PROGRESS INVOICE HISTORY |  |  |  |  | CHANGE ORDER SUMMARY
Pay No. / Date | Invoice Amount | Retention | % Complete |  | Change Order # | Date Approved | PO# | Total Value
1 | 127152.85 | 6692.25 | 109.8%
2 | -127152.85 | -6692.25 | -109.8%
3 | 0 | 0 | 0%
4 | 0 | 0 | 0%
5 | 0 | 0 | 0%
6 | 0 | 0 | 0% |  |  |  | Total | 0
7 | 0 | 0 | 0%
8 | 0 | 0 | 0%
9 | 0 | 0 | 0%
10 | 0 | 0 | 0%
11 | 0 | 0 | 0%
12 | 0 | 0 | 0% |  | CURRENT PAYMENT DUE
13 |  |  | 0%
14 |  |  | 0% |  | Account #: |  | Amount:
15 |  |  | 0% |  | 04-5150-706329
16 |  |  | 0%
17 |  |  | 0% | [5 empty] | Payment Due Matches In different cells
18 |  |  | 0% | [5 empty] | CHECKS
19 |  |  | 0% |  | Total Payment: |  | 0 |  | CHECKS
20 |  |  | 0% | [5 empty] | CHECKS
Total | 0 | 0 | 0%
Project Manager |  |  | Date |  | City Manager (if over $5,000.00) |  |  | Date
City Engineer |  |  | Date
This certificate is not negotiable. It is payable only to the payee named herein and its issuance, payment and acceptance are without prejudice to any rights of the Owner or Contractor under their Contract.
Note on I4: Jason Wuertz: Add one number to the cell to move down one on the main page
Note on I10: Jason Wuertz: Add one number to the cell in the formula
Note on D19: Jason Wuertz: Add one number to the forumula cell
Note on H19: Jason Wuertz: Change sheet number
Note on B23: Jason Wuertz: When adding new tab, copy number from previous tab, not the formula
Note on C23: Jason Wuertz: =Total Retainage - sum of retention totals from previous payments
Note on K41: Jason Wuertz: This checks that Cell H42 matches H19 which it should
Note on K42: Jason Wuertz: Checks that H42 matches H24 which it should
Note on K43: Jason Wuertz: Checks that the total invoice history without retention, plus the balance to finish = the revised contract

## PROGRESS PAYMT #13
PROGRESS PAYMENT
Project Name: | Creekside & Fernwood Pump Stn Coating |  |  |  |  | Page: |  | 1 of 1
Project No: | [5 empty] | Date of Application: |  | 0
Resolution #: | 2020-3692 |  |  |  |  | Invoice Date: |  | 0
Purchase Order No's: |  | 21-052 |  |  |  | Pay Period Through: |  | 0
The contract was approved by City Council on 9/9/2020 per Resolution No. 2020-3692 with a contract value of $119,285.00. Resolution No. 2020-3691 was approved by City Council on July 23, 2020 (contract in the amount of $121,950.00). | [5 empty] | Contractor: | R. L. Reimers Company
[6 empty] | Payment No: |  | 13
Purchase Order is attached
Application is made for Payment, as shown below, in connection with the Contract. Attached is the contractor's signed request for payment. Payment due date per Contract specification. The present status of the account(s) for this Contract is as follows:
THIS PAYMENT
Original Contract | Change Orders | Revised Contract | Total Completed & Stored To Date | Total Retainage |  | Total Earned Less Retainage | Less Previous Certificates for Payment | Balance To Finish
121950 | 0 | 121950 | 0 | 0 |  | 0 | 0 | 121950
PROGRESS INVOICE HISTORY |  |  |  |  | CHANGE ORDER SUMMARY
Pay No. / Date | Invoice Amount | Retention | % Complete |  | Change Order # | Date Approved | PO# | Total Value
1 | 127152.85 | 6692.25 | 109.8%
2 | -127152.85 | -6692.25 | -109.8%
3 | 0 | 0 | 0%
4 | 0 | 0 | 0%
5 | 0 | 0 | 0%
6 | 0 | 0 | 0% |  |  |  | Total | 0
7 | 0 | 0 | 0%
8 | 0 | 0 | 0%
9 | 0 | 0 | 0%
10 | 0 | 0 | 0%
11 | 0 | 0 | 0%
12 | 0 | 0 | 0% |  | CURRENT PAYMENT DUE
13 | 0 | 0 | 0%
14 |  |  | 0% |  | Account #: |  | Amount:
15 |  |  | 0% |  | 04-5150-706329
16 |  |  | 0%
17 |  |  | 0% | [5 empty] | Payment Due Matches In different cells
18 |  |  | 0% | [5 empty] | CHECKS
19 |  |  | 0% |  | Total Payment: |  | 0 |  | CHECKS
20 |  |  | 0% | [5 empty] | CHECKS
Total | 0 | 0 | 0%
Project Manager |  |  | Date |  | City Manager (if over $5,000.00) |  |  | Date
City Engineer |  |  | Date
This certificate is not negotiable. It is payable only to the payee named herein and its issuance, payment and acceptance are without prejudice to any rights of the Owner or Contractor under their Contract.
Note on I4: Jason Wuertz: Add one number to the cell to move down one on the main page
Note on I10: Jason Wuertz: Add one number to the cell in the formula
Note on D19: Jason Wuertz: Add one number to the forumula cell
Note on H19: Jason Wuertz: Change sheet number
Note on B23: Jason Wuertz: When adding new tab, copy number from previous tab, not the formula
Note on C23: Jason Wuertz: =Total Retainage - sum of retention totals from previous payments
Note on K41: Jason Wuertz: This checks that Cell H42 matches H19 which it should
Note on K42: Jason Wuertz: Checks that H42 matches H24 which it should
Note on K43: Jason Wuertz: Checks that the total invoice history without retention, plus the balance to finish = the revised contract

## PROGRESS PAYMT #14
PROGRESS PAYMENT
Project Name: | Creekside & Fernwood Pump Stn Coating |  |  |  |  | Page: |  | 1 of 1
Project No: | [5 empty] | Date of Application: |  | 0
Resolution #: | 2020-3692 |  |  |  |  | Invoice Date: |  | 0
Purchase Order No's: |  | 21-052 |  |  |  | Pay Period Through: |  | 0
The contract was approved by City Council on 9/9/2020 per Resolution No. 2020-3692 with a contract value of $119,285.00. Resolution No. 2020-3691 was approved by City Council on July 23, 2020 (contract in the amount of $121,950.00). | [5 empty] | Contractor: | R. L. Reimers Company
[6 empty] | Payment No: |  | 14
Purchase Order is attached
Application is made for Payment, as shown below, in connection with the Contract. Attached is the contractor's signed request for payment. Payment due date per Contract specification. The present status of the account(s) for this Contract is as follows:
THIS PAYMENT
Original Contract | Change Orders | Revised Contract | Total Completed & Stored To Date | Total Retainage |  | Total Earned Less Retainage | Less Previous Certificates for Payment | Balance To Finish
121950 | 0 | 121950 | 0 | 0 |  | 0 | 0 | 121950
PROGRESS INVOICE HISTORY |  |  |  |  | CHANGE ORDER SUMMARY
Pay No. / Date | Invoice Amount | Retention | % Complete |  | Change Order # | Date Approved | PO# | Total Value
1 | 127152.85 | 6692.25 | 109.8%
2 | -127152.85 | -6692.25 | -109.8%
3 | 0 | 0 | 0%
4 | 0 | 0 | 0%
5 | 0 | 0 | 0%
6 | 0 | 0 | 0% |  |  |  | Total | 0
7 | 0 | 0 | 0%
8 | 0 | 0 | 0%
9 | 0 | 0 | 0%
10 | 0 | 0 | 0%
11 | 0 | 0 | 0%
12 | 0 | 0 | 0% |  | CURRENT PAYMENT DUE
13 | 0 | 0 | 0%
14 | 0 | 0 | 0% |  | Account #: |  | Amount:
15 |  |  | 0% |  | 04-5150-706329
16 |  |  | 0%
17 |  |  | 0% | [5 empty] | Payment Due Matches In different cells
18 |  |  | 0% | [5 empty] | CHECKS
19 |  |  | 0% |  | Total Payment: |  | 0 |  | CHECKS
20 |  |  | 0% | [5 empty] | CHECKS
Total | 0 | 0 | 0%
Project Manager |  |  | Date |  | City Manager (if over $5,000.00) |  |  | Date
City Engineer |  |  | Date
This certificate is not negotiable. It is payable only to the payee named herein and its issuance, payment and acceptance are without prejudice to any rights of the Owner or Contractor under their Contract.
Note on I4: Jason Wuertz: Add one number to the cell to move down one on the main page
Note on I10: Jason Wuertz: Add one number to the cell in the formula
Note on D19: Jason Wuertz: Add one number to the forumula cell
Note on H19: Jason Wuertz: Change sheet number
Note on B23: Jason Wuertz: When adding new tab, copy number from previous tab, not the formula
Note on C23: Jason Wuertz: =Total Retainage - sum of retention totals from previous payments
Note on K41: Jason Wuertz: This checks that Cell H42 matches H19 which it should
Note on K42: Jason Wuertz: Checks that H42 matches H24 which it should
Note on K43: Jason Wuertz: Checks that the total invoice history without retention, plus the balance to finish = the revised contract

## PROGRESS PAYMT #15
PROGRESS PAYMENT
Project Name: | Creekside & Fernwood Pump Stn Coating |  |  |  |  | Page: |  | 1 of 1
Project No: | [5 empty] | Date of Application: |  | 0
Resolution #: | 2020-3692 |  |  |  |  | Invoice Date: |  | 0
Purchase Order No's: |  | 21-052 |  |  |  | Pay Period Through: |  | 0
The contract was approved by City Council on 9/9/2020 per Resolution No. 2020-3692 with a contract value of $119,285.00. Resolution No. 2020-3691 was approved by City Council on July 23, 2020 (contract in the amount of $121,950.00). | [5 empty] | Contractor: | R. L. Reimers Company
[6 empty] | Payment No: |  | 15
Purchase Order is attached
Application is made for Payment, as shown below, in connection with the Contract. Attached is the contractor's signed request for payment. Payment due date per Contract specification. The present status of the account(s) for this Contract is as follows:
THIS PAYMENT
Original Contract | Change Orders | Revised Contract | Total Completed & Stored To Date | Total Retainage |  | Total Earned Less Retainage | Less Previous Certificates for Payment | Balance To Finish
121950 | 0 | 121950 | 0 | 0 |  | 0 | 0 | 121950
PROGRESS INVOICE HISTORY |  |  |  |  | CHANGE ORDER SUMMARY
Pay No. / Date | Invoice Amount | Retention | % Complete |  | Change Order # | Date Approved | PO# | Total Value
1 | 127152.85 | 6692.25 | 109.8%
2 | -127152.85 | -6692.25 | -109.8%
3 | 0 | 0 | 0%
4 | 0 | 0 | 0%
5 | 0 | 0 | 0%
6 | 0 | 0 | 0% |  |  |  | Total | 0
7 | 0 | 0 | 0%
8 | 0 | 0 | 0%
9 | 0 | 0 | 0%
10 | 0 | 0 | 0%
11 | 0 | 0 | 0%
12 | 0 | 0 | 0% |  | CURRENT PAYMENT DUE
13 | 0 | 0 | 0%
14 | 0 | 0 | 0% |  | Account #: |  | Amount:
15 | 0 | 0 | 0% |  | 04-5150-706329
16 |  |  | 0%
17 |  |  | 0% | [5 empty] | Payment Due Matches In different cells
18 |  |  | 0% | [5 empty] | CHECKS
19 |  |  | 0% |  | Total Payment: |  | 0 |  | CHECKS
20 |  |  | 0% | [5 empty] | CHECKS
Total | 0 | 0 | 0%
Project Manager |  |  | Date |  | City Manager (if over $5,000.00) |  |  | Date
City Engineer |  |  | Date
This certificate is not negotiable. It is payable only to the payee named herein and its issuance, payment and acceptance are without prejudice to any rights of the Owner or Contractor under their Contract.
Note on I4: Jason Wuertz: Add one number to the cell to move down one on the main page
Note on I10: Jason Wuertz: Add one number to the cell in the formula
Note on D19: Jason Wuertz: Add one number to the forumula cell
Note on H19: Jason Wuertz: Change sheet number
Note on B23: Jason Wuertz: When adding new tab, copy number from previous tab, not the formula
Note on C23: Jason Wuertz: =Total Retainage - sum of retention totals from previous payments
Note on K41: Jason Wuertz: This checks that Cell H42 matches H19 which it should
Note on K42: Jason Wuertz: Checks that H42 matches H24 which it should
Note on K43: Jason Wuertz: Checks that the total invoice history without retention, plus the balance to finish = the revised contract

## PROGRESS PAYMT #16
PROGRESS PAYMENT
Project Name: | Creekside & Fernwood Pump Stn Coating |  |  |  |  | Page: |  | 1 of 1
Project No: | [5 empty] | Date of Application: |  | 0
Resolution #: | 2020-3692 |  |  |  |  | Invoice Date: |  | 0
Purchase Order No's: |  | 21-052 |  |  |  | Pay Period Through: |  | 0
The contract was approved by City Council on 9/9/2020 per Resolution No. 2020-3692 with a contract value of $119,285.00. Resolution No. 2020-3691 was approved by City Council on July 23, 2020 (contract in the amount of $121,950.00). | [5 empty] | Contractor: | R. L. Reimers Company
[6 empty] | Payment No: |  | 16
Purchase Order is attached
Application is made for Payment, as shown below, in connection with the Contract. Attached is the contractor's signed request for payment. Payment due date per Contract specification. The present status of the account(s) for this Contract is as follows:
THIS PAYMENT
Original Contract | Change Orders | Revised Contract | Total Completed & Stored To Date | Total Retainage |  | Total Earned Less Retainage | Less Previous Certificates for Payment | Balance To Finish
121950 | 0 | 121950 | 0 | 0 |  | 0 | 0 | 121950
PROGRESS INVOICE HISTORY |  |  |  |  | CHANGE ORDER SUMMARY
Pay No. / Date | Invoice Amount | Retention | % Complete |  | Change Order # | Date Approved | PO# | Total Value
1 | 127152.85 | 6692.25 | 109.8%
2 | -127152.85 | -6692.25 | -109.8%
3 | 0 | 0 | 0%
4 | 0 | 0 | 0%
5 | 0 | 0 | 0%
6 | 0 | 0 | 0% |  |  |  | Total | 0
7 | 0 | 0 | 0%
8 | 0 | 0 | 0%
9 | 0 | 0 | 0%
10 | 0 | 0 | 0%
11 | 0 | 0 | 0%
12 | 0 | 0 | 0% |  | CURRENT PAYMENT DUE
13 | 0 | 0 | 0%
14 | 0 | 0 | 0% |  | Account #: |  | Amount:
15 | 0 | 0 | 0% |  | 04-5150-706329
16 | 0 | 0 | 0%
17 |  |  | 0% | [5 empty] | Payment Due Matches In different cells
18 |  |  | 0% | [5 empty] | CHECKS
19 |  |  | 0% |  | Total Payment: |  | 0 |  | CHECKS
20 |  |  | 0% | [5 empty] | CHECKS
Total | 0 | 0 | 0%
Project Manager |  |  | Date |  | City Manager (if over $5,000.00) |  |  | Date
City Engineer |  |  | Date
This certificate is not negotiable. It is payable only to the payee named herein and its issuance, payment and acceptance are without prejudice to any rights of the Owner or Contractor under their Contract.
Note on I4: Jason Wuertz: Add one number to the cell to move down one on the main page
Note on I10: Jason Wuertz: Add one number to the cell in the formula
Note on D19: Jason Wuertz: Add one number to the forumula cell
Note on H19: Jason Wuertz: Change sheet number
Note on B23: Jason Wuertz: When adding new tab, copy number from previous tab, not the formula
Note on C23: Jason Wuertz: =Total Retainage - sum of retention totals from previous payments
Note on K41: Jason Wuertz: This checks that Cell H42 matches H19 which it should
Note on K42: Jason Wuertz: Checks that H42 matches H24 which it should
Note on K43: Jason Wuertz: Checks that the total invoice history without retention, plus the balance to finish = the revised contract

## PROGRESS PAYMT #17
PROGRESS PAYMENT
Project Name: | Creekside & Fernwood Pump Stn Coating |  |  |  |  | Page: |  | 1 of 1
Project No: | [5 empty] | Date of Application: |  | 0
Resolution #: | 2020-3692 |  |  |  |  | Invoice Date: |  | 0
Purchase Order No's: |  | 21-052 |  |  |  | Pay Period Through: |  | 0
The contract was approved by City Council on 9/9/2020 per Resolution No. 2020-3692 with a contract value of $119,285.00. Resolution No. 2020-3691 was approved by City Council on July 23, 2020 (contract in the amount of $121,950.00). | [5 empty] | Contractor: | R. L. Reimers Company
[6 empty] | Payment No: |  | 17
Purchase Order is attached
Application is made for Payment, as shown below, in connection with the Contract. Attached is the contractor's signed request for payment. Payment due date per Contract specification. The present status of the account(s) for this Contract is as follows:
THIS PAYMENT
Original Contract | Change Orders | Revised Contract | Total Completed & Stored To Date | Total Retainage |  | Total Earned Less Retainage | Less Previous Certificates for Payment | Balance To Finish
121950 | 0 | 121950 | 0 | 0 |  | 0 | 0 | 121950
PROGRESS INVOICE HISTORY |  |  |  |  | CHANGE ORDER SUMMARY
Pay No. / Date | Invoice Amount | Retention | % Complete |  | Change Order # | Date Approved | PO# | Total Value
1 | 127152.85 | 6692.25 | 109.8%
2 | -127152.85 | -6692.25 | -109.8%
3 | 0 | 0 | 0%
4 | 0 | 0 | 0%
5 | 0 | 0 | 0%
6 | 0 | 0 | 0% |  |  |  | Total | 0
7 | 0 | 0 | 0%
8 | 0 | 0 | 0%
9 | 0 | 0 | 0%
10 | 0 | 0 | 0%
11 | 0 | 0 | 0%
12 | 0 | 0 | 0% |  | CURRENT PAYMENT DUE
13 | 0 | 0 | 0%
14 | 0 | 0 | 0% |  | Account #: |  | Amount:
15 | 0 | 0 | 0% |  | 04-5150-706329
16 | 0 | 0 | 0%
17 | 0 | 0 | 0% | [5 empty] | Payment Due Matches In different cells
18 |  |  | 0% | [5 empty] | CHECKS
19 |  |  | 0% |  | Total Payment: |  | 0 |  | CHECKS
20 |  |  | 0% | [5 empty] | CHECKS
Total | 0 | 0 | 0%
Project Manager |  |  | Date |  | City Manager (if over $5,000.00) |  |  | Date
City Engineer |  |  | Date
This certificate is not negotiable. It is payable only to the payee named herein and its issuance, payment and acceptance are without prejudice to any rights of the Owner or Contractor under their Contract.
Note on I4: Jason Wuertz: Add one number to the cell to move down one on the main page
Note on I10: Jason Wuertz: Add one number to the cell in the formula
Note on D19: Jason Wuertz: Add one number to the forumula cell
Note on H19: Jason Wuertz: Change sheet number
Note on B23: Jason Wuertz: When adding new tab, copy number from previous tab, not the formula
Note on C23: Jason Wuertz: =Total Retainage - sum of retention totals from previous payments
Note on K41: Jason Wuertz: This checks that Cell H42 matches H19 which it should
Note on K42: Jason Wuertz: Checks that H42 matches H24 which it should
Note on K43: Jason Wuertz: Checks that the total invoice history without retention, plus the balance to finish = the revised contract

## PROGRESS PAYMT #18
PROGRESS PAYMENT
Project Name: | Creekside & Fernwood Pump Stn Coating |  |  |  |  | Page: |  | 1 of 1
Project No: | [5 empty] | Date of Application: |  | 0
Resolution #: | 2020-3692 |  |  |  |  | Invoice Date: |  | 0
Purchase Order No's: |  | 21-052 |  |  |  | Pay Period Through: |  | 0
The contract was approved by City Council on 9/9/2020 per Resolution No. 2020-3692 with a contract value of $119,285.00. Resolution No. 2020-3691 was approved by City Council on July 23, 2020 (contract in the amount of $121,950.00). | [5 empty] | Contractor: | R. L. Reimers Company
[6 empty] | Payment No: |  | 18
Purchase Order is attached
Application is made for Payment, as shown below, in connection with the Contract. Attached is the contractor's signed request for payment. Payment due date per Contract specification. The present status of the account(s) for this Contract is as follows:
THIS PAYMENT
Original Contract | Change Orders | Revised Contract | Total Completed & Stored To Date | Total Retainage |  | Total Earned Less Retainage | Less Previous Certificates for Payment | Balance To Finish
121950 | 0 | 121950 | 0 | 0 |  | 0 | 0 | 121950
PROGRESS INVOICE HISTORY |  |  |  |  | CHANGE ORDER SUMMARY
Pay No. / Date | Invoice Amount | Retention | % Complete |  | Change Order # | Date Approved | PO# | Total Value
1 | 127152.85 | 6692.25 | 109.8%
2 | -127152.85 | -6692.25 | -109.8%
3 | 0 | 0 | 0%
4 | 0 | 0 | 0%
5 | 0 | 0 | 0%
6 | 0 | 0 | 0% |  |  |  | Total | 0
7 | 0 | 0 | 0%
8 | 0 | 0 | 0%
9 | 0 | 0 | 0%
10 | 0 | 0 | 0%
11 | 0 | 0 | 0%
12 | 0 | 0 | 0% |  | CURRENT PAYMENT DUE
13 | 0 | 0 | 0%
14 | 0 | 0 | 0% |  | Account #: |  | Amount:
15 | 0 | 0 | 0% |  | 04-5150-706329
16 | 0 | 0 | 0%
17 | 0 | 0 | 0% | [5 empty] | Payment Due Matches In different cells
18 | 0 | 0 | 0% | [5 empty] | CHECKS
19 |  |  | 0% |  | Total Payment: |  | 0 |  | CHECKS
20 |  |  | 0% | [5 empty] | CHECKS
Total | 0 | 0 | 0%
Project Manager |  |  | Date |  | City Manager (if over $5,000.00) |  |  | Date
City Engineer |  |  | Date
This certificate is not negotiable. It is payable only to the payee named herein and its issuance, payment and acceptance are without prejudice to any rights of the Owner or Contractor under their Contract.
Note on I4: Jason Wuertz: Add one number to the cell to move down one on the main page
Note on I10: Jason Wuertz: Add one number to the cell in the formula
Note on D19: Jason Wuertz: Add one number to the forumula cell
Note on H19: Jason Wuertz: Change sheet number
Note on B23: Jason Wuertz: When adding new tab, copy number from previous tab, not the formula
Note on C23: Jason Wuertz: =Total Retainage - sum of retention totals from previous payments
Note on K41: Jason Wuertz: This checks that Cell H42 matches H19 which it should
Note on K42: Jason Wuertz: Checks that H42 matches H24 which it should
Note on K43: Jason Wuertz: Checks that the total invoice history without retention, plus the balance to finish = the revised contract

## PROGRESS PAYMT #19
PROGRESS PAYMENT
Project Name: | Creekside & Fernwood Pump Stn Coating |  |  |  |  | Page: |  | 1 of 1
Project No: | [5 empty] | Date of Application: |  | 0
Resolution #: | 2020-3692 |  |  |  |  | Invoice Date: |  | 0
Purchase Order No's: |  | 21-052 |  |  |  | Pay Period Through: |  | 0
The contract was approved by City Council on 9/9/2020 per Resolution No. 2020-3692 with a contract value of $119,285.00. Resolution No. 2020-3691 was approved by City Council on July 23, 2020 (contract in the amount of $121,950.00). | [5 empty] | Contractor: | R. L. Reimers Company
[6 empty] | Payment No: |  | 19
Purchase Order is attached
Application is made for Payment, as shown below, in connection with the Contract. Attached is the contractor's signed request for payment. Payment due date per Contract specification. The present status of the account(s) for this Contract is as follows:
THIS PAYMENT
Original Contract | Change Orders | Revised Contract | Total Completed & Stored To Date | Total Retainage |  | Total Earned Less Retainage | Less Previous Certificates for Payment | Balance To Finish
121950 | 0 | 121950 | 0 | 0 |  | 0 | 0 | 121950
PROGRESS INVOICE HISTORY |  |  |  |  | CHANGE ORDER SUMMARY
Pay No. / Date | Invoice Amount | Retention | % Complete |  | Change Order # | Date Approved | PO# | Total Value
1 | 127152.85 | 6692.25 | 109.8%
2 | -127152.85 | -6692.25 | -109.8%
3 | 0 | 0 | 0%
4 | 0 | 0 | 0%
5 | 0 | 0 | 0%
6 | 0 | 0 | 0% |  |  |  | Total | 0
7 | 0 | 0 | 0%
8 | 0 | 0 | 0%
9 | 0 | 0 | 0%
10 | 0 | 0 | 0%
11 | 0 | 0 | 0%
12 | 0 | 0 | 0% |  | CURRENT PAYMENT DUE
13 | 0 | 0 | 0%
14 | 0 | 0 | 0% |  | Account #: |  | Amount:
15 | 0 | 0 | 0% |  | 04-5150-706329
16 | 0 | 0 | 0%
17 | 0 | 0 | 0% | [5 empty] | Payment Due Matches In different cells
18 | 0 | 0 | 0% | [5 empty] | CHECKS
19 | 0 | 0 | 0% |  | Total Payment: |  | 0 |  | CHECKS
20 |  |  | 0% | [5 empty] | CHECKS
Total | 0 | 0 | 0%
Project Manager |  |  | Date |  | City Manager (if over $5,000.00) |  |  | Date
City Engineer |  |  | Date
This certificate is not negotiable. It is payable only to the payee named herein and its issuance, payment and acceptance are without prejudice to any rights of the Owner or Contractor under their Contract.
Note on I4: Jason Wuertz: Add one number to the cell to move down one on the main page
Note on I10: Jason Wuertz: Add one number to the cell in the formula
Note on D19: Jason Wuertz: Add one number to the forumula cell
Note on H19: Jason Wuertz: Change sheet number
Note on B23: Jason Wuertz: When adding new tab, copy number from previous tab, not the formula
Note on C23: Jason Wuertz: =Total Retainage - sum of retention totals from previous payments
Note on K41: Jason Wuertz: This checks that Cell H42 matches H19 which it should
Note on K42: Jason Wuertz: Checks that H42 matches H24 which it should
Note on K43: Jason Wuertz: Checks that the total invoice history without retention, plus the balance to finish = the revised contract

## PROGRESS PAYMT #20
PROGRESS PAYMENT
Project Name: | Creekside & Fernwood Pump Stn Coating |  |  |  |  | Page: |  | 1 of 1
Project No: | [5 empty] | Date of Application: |  | 0
Resolution #: | 2020-3692 |  |  |  |  | Invoice Date: |  | 0
Purchase Order No's: |  | 21-052 |  |  |  | Pay Period Through: |  | 0
The contract was approved by City Council on 9/9/2020 per Resolution No. 2020-3692 with a contract value of $119,285.00. Resolution No. 2020-3691 was approved by City Council on July 23, 2020 (contract in the amount of $121,950.00). | [5 empty] | Contractor: | R. L. Reimers Company
[6 empty] | Payment No: |  | 20
Purchase Order is attached
Application is made for Payment, as shown below, in connection with the Contract. Attached is the contractor's signed request for payment. Payment due date per Contract specification. The present status of the account(s) for this Contract is as follows:
THIS PAYMENT
Original Contract | Change Orders | Revised Contract | Total Completed & Stored To Date | Total Retainage |  | Total Earned Less Retainage | Less Previous Certificates for Payment | Balance To Finish
121950 | 0 | 121950 | 0 | 0 |  | 0 | 0 | 121950
PROGRESS INVOICE HISTORY |  |  |  |  | CHANGE ORDER SUMMARY
Pay No. / Date | Invoice Amount | Retention | % Complete |  | Change Order # | Date Approved | PO# | Total Value
1 | 127152.85 | 6692.25 | 109.8%
2 | -127152.85 | -6692.25 | -109.8%
3 | 0 | 0 | 0%
4 | 0 | 0 | 0%
5 | 0 | 0 | 0%
6 | 0 | 0 | 0% |  |  |  | Total | 0
7 | 0 | 0 | 0%
8 | 0 | 0 | 0%
9 | 0 | 0 | 0%
10 | 0 | 0 | 0%
11 | 0 | 0 | 0%
12 | 0 | 0 | 0% |  | CURRENT PAYMENT DUE
13 | 0 | 0 | 0%
14 | 0 | 0 | 0% |  | Account #: |  | Amount:
15 | 0 | 0 | 0% |  | 04-5150-706329
16 | 0 | 0 | 0%
17 | 0 | 0 | 0% | [5 empty] | Payment Due Matches In different cells
18 | 0 | 0 | 0% | [5 empty] | CHECKS
19 | 0 | 0 | 0% |  | Total Payment: |  | 0 |  | CHECKS
20 | 0 | 0 | 0% | [5 empty] | CHECKS
Total | 0 | 0 | 0%
Project Manager |  |  | Date |  | City Manager (if over $5,000.00) |  |  | Date
City Engineer |  |  | Date
This certificate is not negotiable. It is payable only to the payee named herein and its issuance, payment and acceptance are without prejudice to any rights of the Owner or Contractor under their Contract.
Note on I4: Jason Wuertz: Add one number to the cell to move down one on the main page
Note on I10: Jason Wuertz: Add one number to the cell in the formula
Note on D19: Jason Wuertz: Add one number to the forumula cell
Note on H19: Jason Wuertz: Change sheet number
Note on B23: Jason Wuertz: When adding new tab, copy number from previous tab, not the formula
Note on C23: Jason Wuertz: =Total Retainage - sum of retention totals from previous payments
Note on K41: Jason Wuertz: This checks that Cell H42 matches H19 which it should
Note on K42: Jason Wuertz: Checks that H42 matches H24 which it should
Note on K43: Jason Wuertz: Checks that the total invoice history without retention, plus the balance to finish = the revised contract