## Modified_worksheet
Oregon Department of Environmental Quality | [5 empty] | Yes
Cleanup Project Cost Estimate | [5 empty] | No
Project Estimate Assume GW Monitoring Has No Significant Pathway to SCD
Project Name: | NW Pipe |  |  | ECSI # : | 138
Project Manager: | Jim Orr |  |  | Q-Time # : |  | 0%
Project Team Members: | JO, AL, MR, MP, SM, and MM |  |  | Bus. Office # : |  | 3%
5%
Project office/region: | NWR |  |  |  |  | 8%
This estimate covers the period starting: |  | 2016-03-01 |  |  |  | 10%
and ending: |  | 2017-03-01 |  |  |  | 15%
General Scope and Assumptions: | [5 empty] | 20%
ESTIMATE OF PROJECT COST: |  | 32016.184
PERSONAL SERVICES (see breakdown, below) |  |  |  |  | 32016.184
OTHER DIRECT CHARGES
Attorney General ($175/hour) |  |  |  |  | 0
Travel ($0.575/mile + food, lodging, tax) |  |  |  |  | 0
Contract Payments |  |  |  |  | 0
Capital Outlay |  |  |  |  | 0
Lab |  |  |  |  | 0
TOTAL estimated project costs |  |  |  |  | 32016.184
Personal services (technical staff)
Activity |  | Staff | Hours | Rate ($/hr) (1) | Total $
Project Administration |  | NRS-4 | 15 | 187.12 | 2806.8
File Review |  | NRS-3 |  | 165.6 | 0
Groundwater Site Investigation Work Plan |  | NRS-4 | 12 | 187.12 | 2245.44
Draft Site Investigation Work Plan |  | NRS-4 |  | 187.12 | 0
|  | NRS-3 |  | 165.6 | 0
Final SCD Complete All Staff |  | NRS-4 | 60 | 187.12 | 11227.2
SC Implementation |  | NRS-4 |  | 187.12 | 0
|  | NRS-3 |  | 165.6 | 0
Draft SC Report Review |  | NRS-4 | 25 | 187.12 | 4678
SC Decision |  | NRS-4 |  | 187.12 | 0
|  | NRS-4 Hydro |  | 187
|  | NRS-4 |  | 187.12 | 0
|  | NRS-4 |  | 187.12 | 0
Lead Worker and Manager Review |  | NRS-5 Hydro | 30 | 211 | 6330
142
Total, Technical Staff |  |  |  |  | 27287.44
Clerical Staff, Regional Manager, HQ Staff [0 - 20% of project budget] |  |  |  | 10% | 2728.744
Contingency (added complexity, quality of work products) [20%] |  |  |  | 1 | 2000
|  |  |  | Total, Personal Services | 32016.184
Notes:
1. Select staff level.
2. Select hours for task.
3. Select contingency for staff or other complexity.
4. Add or change tasks or sub-tasks to address project specific needs.
Top-Step Salary Schedule, 2015-16 (incorporates new LQ Indirect as of Oct. 2015)
Classification | Cost/hr.
NRS-1 | 130.35
NRS-2 | 146.69
NRS-3 | 165.6
NRS-4 | 187.12
OPA-3 | 187.12
NRS-4 Hydro | 194.82
NRS-5 | 202.91
NRS-5 Hydro | 211.24
EE3 and NRS-4 Tox | 194.82
Template updated 9/9/15 by Sandra James and Gil Wistar
Note on C66: NRS3 BA, AD
Note on C67: NRS4 AA, AD
Note on B68: Cheyenne is OPA-3
Note on C69: NRS4 BA, AD
Note on C70: NRS5 AA,AD
Note on C71: NRS5 BA,AD
Note on C72: EE3 AA, AD NRS4 CA, AD

## source info
Rates updated based on "Cost Estimator for 2014 (2014-09-01).xlsx"
"Fiscal Year 14" tab with COLA at 2% for 9/1/2014 pay rates
NRS-4 = | NRS 4 AA, AD
NRS-4 Hydro = | NRS 4 BA, AD
NRS-4 Tox = | NRS 4 CA, AD
NRS-4 Sanitarian = | NRS 4 DA, AD
OPA-3 Mgmt Non-supervisory = | OPA 3 AA, MMN
AG rates are for 2013-2015 biennium
When this spreadsheet gets updated, we should probably also update the webpage at http://www.deq.state.or.us/lq/cu/invoicing.htm