PHONE LOGS – SANTOSH LANDFILL
June 18, 2007 Steve Campbell, Jill Kiernan
Per earlier discussion today with Rod Weick and Tim Spencer, we will do the seep work on south side and hold everything else until next summer.

To do seep work, do we need to rebid?

Steve: Yes.

Can we limit invited bidders to the three we got bids from? SC: yes, or can add a few more. Have a mandatory site walk, optional for the three who attended the last one.

Do we need a smaller constructed road? JK: probably not.

Does wetland mitigation need to be done before the wetland destruction happens? JK will check with Celina.

Phone message left for Tina Teed:

May 14: has Corps decided if they will exercise jurisdiction on this site? If so, will manmade wetlands on top of LF be considered in mitigation calcs?

May 17, 2007: left same message as on May 14.

May 21, 2007: I reached Tina. She apologized for not calling back. She was sick. I explained that we will pursue wetland mitigation, rather than payment to provide. However, need to know if Corps will require us to mitigate for manmade wetlands on top of the landfill. Main concern is that the decision doesn’t delay construction of fixing the envl problem. She understands and will get back to me as soon as possible.

May 24, 2007. Tina called. Onsite wetlands may be subject to their jurisdiction. She will check with wetland specialist and call me on Tuesday.

xxxxxxxxxxxxxxxx

May 16, 2007

Janelle St Pierre called following the e-mail from Don Mehlhoff. Since working with NRCS on the Hogan Ranch site seems to not be an option,  she thought we can either work on a nearby site being worked on by ducks Unlimited.  Or we can go back to the wetland enhancement concept next to the south side of the landfill that we originally considered. Celina will call Chuck Lobdell at Ducks Unlimited (360-885-2011 extension 18).

Celena noted that the Department of State lands will not allow a project that only involves vegetative enhancement.  There needs to be a hydrologic component to it as well.

May 1, 2007

I spoke to Joy Freibaum, Dept of State Lands, 503-687-3805 x 268. She needs to know what our wetland mitigation plan will be and whether we plan to do actual mitigation or pursue the payment to provide approach (just paying money to compensate for destroying wetlands). Until we specify one or the other, our application is incomplete. The Army Corps does not accept payment to provide so if they plan to be involved, this is not an option. If we go the mitigation route, we have to submit a mitigation plan.

Corps contact is Tina Teed, 503-808-4384. I just left her a voice mail asking whether the Army Corps plans to be involved.

Dept of State Lands schedule:

· They have until May 19 to determine if the application is complete. If yes, they go to public comment for 30 days (June 18).

· If no public comments, they have up to 60 days for final review (around August 15 or earlier).

If we pursue mitigation, there are three options recognized by Dept of State Lands:

· wetland creation (1.5 to 1 ratio; ie, if we destroy 1 acre, need to create 1.5 acres)

· wetland restoration (1:1 ratio)

· wetland enhancement (3:1 ratio)

Army Corps has a different formula that depends on “functional gain”. We would need to satisfy both agencies, assuming again that the Corps will be involved.

Wetland mitigation includes monitoring for at least five years.

